## Summary
Workflow Document Tracker
Row Labels | Count of (Helper) Doc Status | Project Name: HB Test | Total number of documents: 2
A - Accepted | 1 | Date Generated: 23/03/2025
Pending | 1 | Summary Page
Grand Total | 2
Total number of documents: 2

## Tracker
Workflow Document Tracker |  |  |  |  | Click here to go to your outstanding workflows
Project Name: HB Test
Date Generated: 23/03/2025
| Date In | Step Name | Step Outcome | Date of Comments | Comments
DRW-000001 Dummy 1
P02 | 2024-11-25 | Step 1 | Approved with Comments | 2024-12-05 | Please can the drawing be updated to show the man writing in his left hand as this would be more exciting
P03 | 2025-03-22 | DFE Review | C - Rejected | 2025-03-23 | 1. this drawing shows the phase 1 construction area but uses the phase 3 car park layout (final configuration). HB need to show 2 construction phases and the different car park layouts as presented in the logistics CEM.
| 2025-03-23 | Designer Response | Pending | (blank) | (blank)
DRW-000002 Dummy 2 New Title
P01 | 2024-11-25 | Step 1 | Rejected | 2024-12-05 | The cow is brown and suspicious-looking
P02 | 2025-03-22 | DFE Review | A - Accepted | 2025-03-23 | This document shows the correct car park layouts for this phase. therefore can FS1018-HBC-XX-XX-D-X-0001 be removed?

## RawData
Project Name | Date Generated
HB Test | 2025-03-23
Document Number | Title | Revision | Workflow Status | Date In | Step Name | Step Outcome | Date of Comments | Comments | Latest revision? | (Helper) Num + Title | (Helper) Hyperlink
DRW-000001 | Dummy 1 | P02 | Completed | 2024-11-25 | Step 1 | Approved with Comments | 2024-12-05 | Please can the drawing be updated to show the man writing in his left hand as this would be more exciting | FALSE | DRW-000001 Dummy 1 | DRW-000001
DRW-000001 | Dummy 1 | P03 | In Progress | 2025-03-22 | DFE Review | C - Rejected | 2025-03-23 | 1. this drawing shows the phase 1 construction area but uses the phase 3 car park layout (final configuration). HB need to show 2 construction phases and the different car park layouts as presented in the logistics CEM. | TRUE | DRW-000001 Dummy 1 | DRW-000001
DRW-000001 | Dummy 1 | P03 | In Progress | 2025-03-23 | Designer Response | Pending |  |  | TRUE | DRW-000001 Dummy 1 | DRW-000001
DRW-000002 | Dummy 2 New Title | P01 | Completed | 2024-11-25 | Step 1 | Rejected | 2024-12-05 | The cow is brown and suspicious-looking | FALSE | DRW-000002 Dummy 2 New Title | DRW-000002
DRW-000002 | Dummy 2 New Title | P02 | Completed | 2025-03-22 | DFE Review | A - Accepted | 2025-03-23 | This document shows the correct car park layouts for this phase. therefore can FS1018-HBC-XX-XX-D-X-0001 be removed? | TRUE | DRW-000002 Dummy 2 New Title | DRW-000002