## Summary
Workflow Document Tracker
Row Labels | Count of (Helper) Doc Status | Project Name: FS1018 DfE Wisbech Free School | Total number of documents: 211
Pending | 123 | Date Generated: 23/03/2025
B3 - Partially Accepted with Comments | 72 | Summary Page
C - Rejected | 4
B - Approved with Comments | 1
A3 - Accepted | 11
Grand Total | 211
Total number of documents: 211

## Tracker
Workflow Document Tracker |  |  |  |  | Click here to go to your outstanding workflows
Project Name: FS1018 DfE Wisbech Free School
Date Generated: 23/03/2025
| Date In | Step Name | Step Outcome | Date of Comments | Comments
FS1018-ADT-ZZ-00-D-J-0001 BB93 Acoustic Criteria Ground Floor
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ADT-ZZ-00-D-J-0004 Acoustic Wall Types Ground Floor
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ADT-ZZ-01-D-J-0002 BB93 Acoustic Criteria First Floor
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ADT-ZZ-01-D-J-0005 Acoustic Wall Types First Floor
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ADT-ZZ-02-D-J-0003 BB93 Acoustic Criteria Second Floor
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ADT-ZZ-02-D-J-0006 Acoustic Wall Types Second Floor
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ADT-ZZ-ZZ-T-J-0001 Acoustic Strategy
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ADT-ZZ-ZZ-T-Y-0002 Environmental Noise Impact Assessment
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6110 Level 00 Containment Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6111 Level 00 Containment Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6112 Level 00 Containment Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6114 Building Electrical Switchroom Details
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6210 Level 00 Small Power And Data Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6211 Level 00 Small Power And Data Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6212 Level 00 Small Power And Data Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6213 Level 00 MSER Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6214 Level 00 MSER Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6215 Level 00 MSER Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6310 Level 00 Lighting Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6311 Level 00 Lighting Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6312 Level 00 Lighting Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6810 Level 00 Fire Alarm Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6811 Level 00 Fire Alarm Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6812 Level 00 Fire Alarm Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6820 Level 00 Fire Alarm Zoning Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6821 Level 00 Fire Alarm Zoning Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6822 Level 00 Fire Alarm Zoning Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6840 Level 00 Security Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6841 Level 00 Security Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-6842 Level 00 Security Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-E-9001 Photovoltaic Canopies
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5210 Level 00 Above Ground Drainage Sheet 1
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5211 Level 00 Above Ground Drainage Sheet 2
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5212 Level 00 Above Ground Drainage Sheet 3
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5310 Level 00 Domestic Water Services Sheet 1
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5311 Level 00 Domestic Water Services Sheet 2
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5312 Level 00 Domestic Water Services Sheet 3
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5410 Level 00 Gas
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5610 Level 00 Heating and Cooling Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5611 Level 00 Heating and Cooling Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5612 Level 00 Heating and Cooling Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5710 Level 00 Ventilation Sheet 1
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5711 Level 00 Ventilation Sheet 2
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5712 Level 00 Ventilation Sheet 3
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5810 Level 00 Plantroom Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-M-5811 Level 00 Plantroom Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-Z-6010 Level 00 Builderswork Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-Z-6011 Level 00 Builderswork Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-Z-6012 Level 00 Builderswork Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-Z-9610 Level 00 Reflected Ceiling Plan Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-Z-9611 Level 00 Reflected Ceiling Plan Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-00-D-Z-9612 Level 00 Reflected Ceiling Plan Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6110 Level 01 Containment Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6111 Level 01 Containment Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6210 Level 01 Small Power And Data Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6211 Level 01 Small Power And Data Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6212 Level 01 MSER Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6213 Level 01 MSER Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6310 Level 01 Lighting Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6311 Level 01 Lighting Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6810 Level 01 Fire Alarm Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6811 Level 01 Fire Alarm Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6820 Level 01 Fire Alarm Zoning Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6821 Level 01 Fire Alarm Zoning Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6840 Level 01 Security Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-E-6841 Level 01 Security Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-M-5210 Level 01 Above Ground Drainage Sheet 1
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-M-5211 Level 01 Above Ground Drainage Sheet 2
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-M-5310 Level 01 Domestic Water Services Sheet 1
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-M-5311 Level 01 Domestic Water Services Sheet 2
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-M-5410 Level 01 Gas
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-M-5610 Level 01 Heating and Cooling Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-M-5611 Level 01 Heating and Cooling Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-M-5710 Level 01 Ventilation Sheet 1
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-M-5711 Level 01 Ventilation Sheet 2
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-Z-6010 Level 01 Builderswork Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-Z-6011 Level 01 Builderswork Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-Z-9610 Level 01 Reflected Ceiling Plan Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-01-D-Z-9611 Level 01 Reflected Ceiling Plan Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6110 Level 02 Containment Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6111 Level 02 Containment Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6210 Level 02 Small Power And Data Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6211 Level 02 Small Power And Data Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6212 Level 02 MSER Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6213 Level 02 MSER Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6310 Level 02 Lighting Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6311 Level 02 Lighting Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6810 Level 02 Fire Alarm Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6811 Level 02 Fire Alarm Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6820 Level 02 Fire Alarm Zoning Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6821 Level 02 Fire Alarm Zoning Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6840 Level 02 Security Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-E-6841 Level 02 Security Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-M-5210 Level 02 Above Ground Drainage Sheet 1
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-M-5211 Level 02 Above Ground Drainage Sheet 2
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-M-5310 Level 02 Domestic Water Services Sheet 1
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-M-5311 Level 02 Domestic Water Services Sheet 2
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-M-5410 Level 02 Gas
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-M-5610 Level 02 Heating and Cooling Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-M-5611 Level 02 Heating and Cooling Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-M-5710 Level 02 Ventilation Sheet 1
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-M-5711 Level 02 Ventilation Sheet 2
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-Z-6010 Level 02 Builderswork Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-Z-6011 Level 02 Builderswork Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-Z-9610 Level 02 Reflected Ceiling Plan Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-02-D-Z-9611 Level 02 Reflected Ceiling Plan Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-E-6213 Roof Level MSER
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-E-6810 Roof Level Fire Alarm Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-E-6811 Roof Level Fire Alarm Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-E-6840 Roof Level Security Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-E-6841 Roof Level Security Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-E-6842 Roof Level Security Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-E-9001 Photovoltaic
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-M-5210 Roof Level Above Ground Drainage Sheet 1
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-M-5211 Roof Level Above Ground Drainage Sheet 2
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-M-5212 Roof Level Above Ground Drainage Sheet 3
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-M-5310 Roof Level Domestic Water Services Sheet 1
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-M-5311 Roof Level Domestic Water Services Sheet 2
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-M-5312 Roof Level Domestic Water Services Sheet 3
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-M-5710 Roof Level Ventilation Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-M-5711 Roof Level Ventilation Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-M-5712 Roof Level Ventilation Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-Z-5810 Roof Level Plantroom Sheet 1
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-Z-5811 Roof Level Plantroom Sheet 2
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-Z-5812 Roof Level Plantroom Sheet 3
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-Z-6010 Roof Level Builderswork Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-Z-6011 Roof Level Builderswork Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-RF-D-Z-6012 Roof Level Builderswork Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-D-E-9001 External Lighting
P04 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-D-E-9002 External Lighting Lux Levels
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-D-E-9511 DNO Services Drawing and Proposal
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-D-Z-5810 External Compound
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-D-Z-9510 External Services
P03 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-E-0001 Proposed Manufacturers Electrical Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-E-0002 Cable Calculation & Schedule Report
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-E-0003 Containment Calculations
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-E-0004 Lighting Calculations
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-E-0005 Exit Signage Calculation
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-E-9602 Luminaire Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-0003 Domestic Water Services Calculations
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-0004 Ventilation Calculations
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-0005 Gas Calculations
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-0006 Above Ground Drainage Calculations
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-0007 Heating Calculations
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-0008 Heat Source Calculations
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9604 Heat Pump Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9605 Buffer Vessel Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9607 Plate Heat Exchanger Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9608 Water Heater Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9609 Air & Dirt Separator Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9610 Dosing Pot Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9613 Water Filter Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9614 Water Softener Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9617 Leak Detection Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9619 Gas Meter Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9620 Water Meter Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9621 Heat Meter Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9623 Gas Solenoid Valve Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9624 Gas Detection & Proving Panel Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9625 Pressurisation Unit Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9627 Storage Tank Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9628 Booster Set Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9630 Pump Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9634 Local Water Heater Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9637 Radiator Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9641 Underfloor Heating Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9642 Underfloor Heating Manifold Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9644 Overdoor Heater Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9647 Electric Heater Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9649 Fan Convector Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9652 Air Handling Unit Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9653 Heat Recovery Unit Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9654 Hybrid Ventilation Unit Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9655 Fan Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9658 Louvre Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9659 Supply Diffuser Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9660 Extract Grille Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9661 Attenuator Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9662 Transfer Grille Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9671 Heating Coil Schedule (LTHW)
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9675 Smoke-activated Fire Damper Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9678 Passive Stack Ventilator Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9681 DX Indoor Unit Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-M-9682 DX Outdoor Unit Schedule
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-Z-0001 Designers MEP Risk Assessment
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-L-Z-0004 Heat Loss Calculations
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-T-E-0001 Electrical Specification
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-T-E-0003 Electrical Maximum Demand
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-T-M-0001 Mechanical Specification
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-T-Z-0002 Plant Access Maintenance And Replacement Strategy
P02 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-T-Z-0006 NBS Project Description
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-XX-T-Z-0007 Thermal Modelling, Compliance & Sustainability Report
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-D-E-9001 Lightning Protection
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-D-Z-6115 Server and Hub Room
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-D-Z-9610 Typical D&T Classroom
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-D-Z-9611 Typical Food Room
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-D-Z-9612 Typical ICT Classroom
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-D-Z-9613 Typical Riser
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-D-Z-9614 Typical Science Room
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-E-6010 LV Schematic Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-E-6011 LV Schematic Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-E-6811 Fire Alarm Schematic
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-M-5010 Controls Schematic
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-M-5210 Above Ground Drainage Schematic Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-M-5211 Above Ground Drainage Schematic Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-M-5310 Domestic Water Services Schematic
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-M-5410 Gas Schematic
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-M-5610 Heating & Cooling Schematic Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-M-5611 Heating & Cooling Schematic Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-M-5612 Heating & Cooling Schematic Sheet 3
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-M-5613 Heating & Cooling Schematic Sheet 4
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-M-5710 Ventilation Schematic Sheet 1
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-M-5711 Ventilation Schematic Sheet 2
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-G-M-5812 Plantroom Schematic
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-M-Z-0001 MEP Model Revit
P15 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-M-Z-0002 MEP Model IFC
P15 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-AGL-ZZ-ZZ-M-Z-0003 MEP Model NWC
P15 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-XX-XX-L-A-0001 Schedule Of Accommodation
P06 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-XX-XX-T-A-0005 Teaching Block Finishes
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-XX-XX-T-A-0010 Outline Specification
P09 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-XX-XX-T-A-5001 Stage 4 Report
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-XX-XX-T-A-5002 Design Development Report
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-XX-XX-T-A-5003 Pre-Construction Information
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-XX-ZZ-L-A-0000 Building Model COBie Report
P25 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-2001 GA Proposed L00 Floor Plan
P17 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-2142 Ground Edge Details
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-2200 Wall And Partition Types L00
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-2900 Fire Strategy L00
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-3001 External Door Schedules Sheet 01
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-3050 Internal Doors Level 00 Sheet 01
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-3051 Internal Doors Level 00 Sheet 02
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-3052 Internal Doors Level 00 Sheet 03
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-3053 Internal Doors Level 00 Sheet 04
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-3054 Internal Doors Level 00 Sheet 05
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-3500 Reflected Ceiling L00
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-6807 Room Elevations Hygiene Room
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-6808 Room Elecations Pupil WC'S
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-6809 Room Elevations Pupils And Staff WC
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-6810 Room Elevations Accessible WC
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-6811 Room Elevations Changing Room
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-00-D-A-6812 Room Elevations Accessible Changing Room
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-01-D-A-2002 GA Proposed L01 Floor Plan
P16 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-01-D-A-2201 Wall And Partition Types L01
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-01-D-A-2250 Patressing Plan For Typical Classroom
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-01-D-A-2251 Patressing Plan For Art Room
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-01-D-A-2901 Fire Strategy L01
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-01-D-A-3501 Reflected Ceiling L01
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-01-D-A-6800 Room Elevations Classroom
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-02-D-A-2003 GA Proposed L02 Floor Plan
P17 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-02-D-A-2202 Wall And Partition Types L02
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-02-D-A-2902 Fire Strategy L02
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-02-D-A-3502 Reflected Ceiling L02
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-RF-D-A-2023 GA Proposed Roof Plan
P15 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-RF-D-A-2144 Roof Details Sheet 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-RF-D-A-2145 Roof Details Sheet 2
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-RF-D-A-2903 Fire Strategy Rf
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-RF-D-A-3100 Rooflight Elevations Sheet 1
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-RF-D-A-3101 Rooflights And Hatch Plan
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-XX-D-A-2146 3D Section
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-XX-D-A-2210 Partition Detail Plans
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-XX-L-A-0020 CDM Design Risk Assessment
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-0050 Circulation Strategy
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-0051 Zoning and Security Strategy
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-0052 Sanitary and Hygiene Strategy
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-0053 Access and Maintenance Strategy
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-0054 Cleaning and Maintenance Strategy
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-0060 Proposed Room Cluster Diagram
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2001 GA Proposed Section AA, BB, CC, DD
P08 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2002 GA Proposed Section EE
P06 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2010 GA Proposed Elevations Sheet 1
P08 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2011 GA Proposed Elevations Sheet 02
P06 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2012 GA Proposed Elevations Sheet 03
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2025 Hazard Identification Plan
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2031 Internal Views
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2032 External Views
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2040 Lock Suiting Strategy
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2140 Construction Building Sections Sheet 1
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2141 Construction Building Sections Sheet 2
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2143 External Wall Details Sheet 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2144 External Wall Details Sheet 2
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2401 Typical Staircase Sheet 01
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2402 Typical Staircase Sheet 02
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2403 Typical Staircase Sheet 03
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2404 Typical Staircase Sheet 04
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-2405 Typical Staircase Sheet 05
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-3002 External Door Schedues Sheet 02
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-3010 Curtain Wall Panelling Elevations Sheet 01
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-3011 Curtain Wall Panelling Elevations Sheet 02
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-3020 External Windows Elevation And Schedule
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-3021 Internal Glazed Panel Elevations And Schedule
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-3055 Internal Doors Level 00 Sheet 06
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-3062 Window Schedule
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-4001 GA Wall Finishes Strategy
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-4004 GA Floor Finishes Strategy
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-6601 Lift Pit Details
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-6801 Room Elevations Assembly Dining Sheet 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-6802 Room Elevations Assembly Dining Sheet 2
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-6803 Room Elevations Sports Hall Sheet 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-6804 Room Elevations Sports Hall Sheet 2
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-6805 Room Elevations Sports Hall Sheet 3
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-6806 Room Elevations Sports Hall Acoustic Panel Set Out
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-D-A-6813 Room Elevations Pupil WC'S L01 And L02
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-L-A-0001 Clash Report
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-L-A-3060 Internal Door Schedule
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-L-A-3061 External Door Schedule
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-M-A-0002 Federated Model
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-M-A-0003 Architectural Model NWC
P25 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-M-A-0004 Architectural Model IFC
P25 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-M-A-0005 Architectural Model Revit
P25 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-V-A-0001 External Flythrough Video
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-CPM-ZZ-ZZ-V-A-0002 Internal Flythrough Video
P01 | 2025-03-14 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-D-O-0001 Server Room Location
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-D-O-0002 ICT Plans
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-D-O-0003 Wireless Heat Maps
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-D-O-0004 Server Cabinet Layout
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-G-O-0001 ICT Network Diagrams
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-L-O-0001 ICT Equipment List
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-L-O-0002 ICT Cost Matrix
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-L-O-0003 ICT Small Power and Data Schedule
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-L-O-0004 ICT Construction Programme
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-T-O-0002 ICT Calculations
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-T-O-0004 ICT Contractor's Proposals
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-T-O-0005 Post Award ICT Meetings (PAM) Agendas
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-T-O-0006 User Acceptance Testing (UAT) Schedule
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-EVR-XX-XX-T-O-0007 Post Award ICT Meetings (PAM) Minutes
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-D-X-0001 Site Construction Plan
P01 | 2025-03-13 | DFE Review | C - Rejected | 2025-03-19 | 1. this drawing shows the phase 1 construction area but uses the phase 3 car park layout (final configuration). HB need to show 2 construction phases and the different car park layouts as presented in the logistics CEM.
| 2025-03-19 | Designer Response | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-D-X-0003 Site Set Up Plan Phase 1
P02 | 2025-03-13 | DFE Review | A - Accepted | 2025-03-19 | this document shows the correct car park layouts for this phase. therefore can FS1018-HBC-XX-XX-D-X-0001 be removed?
FS1018-HBC-XX-XX-D-X-0004 Site Set Up Plan Phase 2 Section 1
P02 | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. as this is summer works are the notes regarding pedestrian access to be maintained necessary? 2. re the note about a decision needs to eb made regadring use if link road - Can the link road be released for use from Sept 2026 to improve the bus and pedestrian and vehicle access? 3. what arrangements will be made for Teaching staff parking during this phase of works as the new building will be open. This was raised at CEM meeting
| 2025-03-19 | Designer Response | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-D-X-0005 Site Set Up Plan Phase 2 Section 2
P01 | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. more detailed proposals will be needed for phasing of access into staff car park as drawing indicates that this may be blocked. 2. Staff car parking will be needed in the interim period following portacabin decant and reinstatement of portakabin area to provide parking
| 2025-03-19 | Designer Response | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-D-X-0006 Site Set Up Plan Phase 3
P01 | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. should this drawing be named final layout post handover not site set up phase 3?
| 2025-03-19 | Designer Response | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-0001 MIDP
P15 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-0003 Design Programme
P02 | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. Line 47 Judicial review and line 49 Discharge of pre commencement conditions can these be run concurrently? 2. line 51 is this a duplicate of line 49 but does suggest condition discharge is running concurrently? 3. line 68 Delivery of CPS was only partial MEP 17th March and costs etc not received as of 19/3/2025 4. Should CP review evaluation line 69 should be 8 weeks from receipt of full CPS. 5. line 80 should also include a note .. Contract finalisation including any increased DFE budget submissions (CCF)
| 2025-03-19 | Designer Response | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-0004 Construction Programme
P02 | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. Line 56 - please clarify this task - is this place order or install the substation - NB noted line 224 Legal process for easements and S77 disposal of land has been planned into programme 2. Line 74 power and water on 2a. power on does the activity need more details see my comments re line 56? 2b, this is planned for early in school term - can the service interruptions be planned outside school term ie summer or half term or weekends? 3 ICT fit out needs to be planned with School ICT contractor, also will need the main hall AV as a planned activity as well as the drama rooms etc. 4. Lines 297 and line 310 phase 2 section and 1 and 2 handover are both after school term starts can these be planned for completion prior to school term starts to avoid disruption ie before 1st September 2026 and 2027?
| 2025-03-19 | Designer Response | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-0005 Master Programme
P02 | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. see comments regarding Design programme and construction programme. Master programme to eb updated to reflect these comments
| 2025-03-19 | Designer Response | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-0006 Works Package Procurement Programme
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-0007 Risk Register
P02 | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. line 3 - existing drainage culvert - need to update this risk following IDB planning objection 2. Line 11 Sport England response has been received removing objection - needs updating 3. Planning delay - needs updating / re evaluating due to delays in statutory consultee responses and risk of not making April committee
| 2025-03-19 | Designer Response | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-0013 DFE KPIs
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-0014 Supplier Directory CV
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-0016 Handover Training Plan
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-0018 HB Social Value KPIs
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-0019 Site Organisation Chart
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-0020 Commissioning Programme
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-1001 Quality Management Plan
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-1002 Sustainable Estate Strategy
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-1003 Lift Specification
P01 | 2025-03-13 | DFE Review | C - Rejected | 2025-03-21 | This is a lift companies sale literature (which is non compliant for a new lift going into a new build building) and is not a lift specification as WSP VT would expect. Front page of document says 29 pages and 12 are submitted. Please provide full lift specification for review. WSP VT can not offer comment as document is incomplete
| 2025-03-21 | Designer Response | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-1004 Project Execution Plan
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-3000 Derogations Schedule
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-L-X-4000 Planning Condition Tracker
P01 | 2025-03-13 | DFE Review | C - Rejected | 2025-03-21 | rejected Pending conclusion of the planning submission
| 2025-03-21 | Designer Response | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0001 Construction Phasing Plan
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0024 CEM7 Meeting Minutes
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0025 CEM8 Meeting Minutes
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0026 CEM8-9A Meeting Minutes
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0027 CEM09 Meeting Minutes
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0028 CEM10 Meeting Minutes
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0029 CEM10A Meeting Minutes
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0030 CEM11 Meeting Minutes
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0031 CEM12 Meeting Minutes
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0033 CEM07 Agenda
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0034 CEM08 Agenda
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0035 CEM09 Agenda
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0036 CEM08-9A Agenda
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0037 CEM10 Meeting Agenda
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0038 CEM10A Agenda
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0039 CEM11 Agenda
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0040 CEM12 Agenda
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0042 Employer Necessary Consents
P01 | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-21 | ENCs are unclear at present as the land transaction has yet to be completed with CCC and also the planning approval has yet to be concluded which may result in s278 or other legal agreements. As these processes are concluded ENCs may arise and this document will need to be updated
| 2025-03-21 | Designer Response | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0043 Construction Method Statement
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0044 Handover Strategy
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HBC-XX-XX-T-X-0045 Thermal Assessment
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-XX-XX-T-C-0004 CIVIL DESIGN PHILOSOPHY
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-XX-XX-T-C-0010 Risk Register
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-XX-XX-T-C-0011 Drainage Specification
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-XX-XX-T-C-0012 Earthworks Specification
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-XX-XX-T-H-0001 Transport Assessment
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-XX-XX-T-S-0003 Structural Design Philosophy
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-XX-XX-T-S-0004 Concrete Specification
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-XX-XX-T-S-0005 Steelwork Specification
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-XX-XX-T-S-0006 Piling Specification
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-00-D-S-0101 FOUNDATION LAYOUT
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-00-D-S-0102 Foundation Details
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-00-D-S-0200 GROUND FLOOR COLUMN PLAN
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-01-D-S-0201 FIRST FLOOR STEELWORK LAYOUT
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-02-D-S-0202 SECOND FLOOR STEELWORK LAYOUT
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-RF-D-S-0203 MAIN ROOF STEELWORK LAYOUT
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-RF-D-S-0204 HALL ROOF STEELWORK LAYOUTS
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-RF-D-S-0205 PARAPET STEELWORK LAYOUT
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-XX-D-S-0001 PROJECT NOTES
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-C-5200 SURFACE WATER DRAINAGE LAYOUT SHEET 1
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-C-5201 SURFACE WATER DRAINAGE LAYOUT SHEET 2
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-C-5205 FOUL WATER DRAINAGE LAYOUT
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-C-5210 DRAINAGE CONSTRUCTION DETAILS SHEET 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-C-5211 DRAINAGE CONSTRUCTION DETAILS SHEET 2
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-C-9000 Earthworks Analysis
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-C-9020 EXTERNAL WORKS LAYOUT SHEET 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-C-9021 EXTERNAL WORKS LAYOUT SHEET 2
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-C-9025 EXTERNAL WORKS CONSTRUCTION DETAILS
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-S-0501 BUILDING ELEVATIONS SHEET 01 OF 02
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-S-0502 BUILDING ELEVATIONS SHEET 02 OF 02
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-S-0503 BRACING ELEVATIONS
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-S-0601 BUILDING SECTIONS
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-S-0602 Structural Sections and Details
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-D-S-0801 3D Views
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-M-C-0001 Native Civil Model
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-M-C-0002 IFC SPF Civil Model
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-M-C-0003 Navisworks Civil Model
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-M-S-0001 Native Structural Model
P09 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-M-S-0002 IFC SPF Structural Model
P09 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-M-S-0003 Navis Structural Model
P09 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-HEX-ZZ-ZZ-T-C-0001 GENERAL NOTES
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-MAJ-XX-XX-L-X-0090 Detailed Responsibility Matrix
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-MAJ-XX-XX-L-X-8001 Asset Register
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-MAJ-XX-XX-L-X-8002 COBie QC Report
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-MAJ-XX-XX-T-X-0001 BIM Execution Plan
P06 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-MAJ-XX-XX-T-X-1001 Information Managers Report
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-MAJ-ZZ-ZZ-M-X-0001 Federated Information Model
P06 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-OFR-XX-ZZ-G-K-0001 Fire Strategy Report
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-XX-T-L-0001 Outline Specification
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-XX-T-L-0002 Design Development Schedule
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0001 Location Plan
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0002 Existing Site Plan
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0003 Whole Site Plan
P14 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0004 Site Landscaping Plan 1 of 5
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0005 Site Landscaping Plan 2 of 5
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0006 Site Landscaping Plan 3 of 5
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0007 Site Landscaping Plan 4 of 5
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0008 Site Landscaping Plan 5 of 5
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0009 Access and Security Strategy
P08 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0010 Circulation Strategy
P06 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0011 External Sports Provision
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0012 Green Infrastructure Plan
P08 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0013 BB103 Guidance
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0014 Hazard Identification Plan
P06 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0015 Refurbishment Remodelling Strategy
P09 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0017 Site Sections
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0021 Existing Site Plan 1 of 5
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0022 Existing Site Plan 2 of 5
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0023 Existing Site Plan 3 of 5
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0024 Existing Site Plan 4 of 5
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0025 Existing Site Plan 5 of 5
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0201 Detailed Planting Plan Sheet 1 of 5
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0202 Detailed Planting Plan Sheet 2 of 5
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0203 Detailed Planting Plan Sheet 3 of 5
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0204 Detailed Planting Plan Sheet 4 of 5
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0205 Detailed Planting Plan Sheet 5 of 5
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0401 Outline Levels Plan 1 of 5
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0402 Outline Levels Plan 2 of 5
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0403 Outline Levels Plan 3 of 5
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0404 Outline Levels Plan 4 of 5
P06 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0405 Outline Levels Plan 5 of 5
P06 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0601 Landscape Details Sheet 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0602 Landscape Details Sheet 2
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-XX-ZZ-D-L-0603 Landscape Details Sheet 3
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-ZZ-XX-T-L-0004 Security Statement
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-ZZ-ZZ-M-L-0001 Landscape Model
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-ZZ-ZZ-M-L-0002 Landscape Model
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-ONE-ZZ-ZZ-M-L-0003 Landscape Model
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-XX-XX-L-O-0003 Task Team Risk Register
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-0001 Ground Floor GA 1 Of 2
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-0002 Ground Floor GA 2 Of 2
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-0006 Lobby 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-0601 Food Prep Area, Kitchen Servery And Wash Up 1
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-1109 MUSIC ROOM
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-1110 DT WORKSHOP 1
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-1111 Food Room 1 Option 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-1112 DT Studio Graphic Products
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-1113 DT Studio Electronics And Control
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-1211 FOOD ROOM 1
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-2001 Assembly Hall, Dining Layout
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-2002 Sports Hall Exam Layout
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-2003 Assembly Hall, Assembly Layout
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-3002 Sports Hall Sport Layout
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-3004 LRC
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-4003 Enclosed Office, Admin Head 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-4004 Enclosed Office, Admin PA 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-4005 Reprographics Room 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-4006 Enclosed Office, With Recep Desk And Window 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-4008 Reception Area, Entrance 50% Circulation
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-4009 Confidential Meeting Room Interview 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-4015 Office With Meeting Area, 2 Person 4
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-4018 Staff Workroom Premises 1 And Equipment Store, Maintenance 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-5003 Confidential Meeting Room Interview 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-5007 Dt Prep Room 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-5008 Food Prep Room 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-5009 Teaching Resources Store Off DT Studio
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-5011 Teaching Resources Store Off DT Studio
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-5013 Teaching Resources Store Music 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-5018 Sports Equipment Store, Internal Sports Hall 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-5019 Sports Equipment Store, External 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-5103 Secure Storeroom 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-5109 Coats And Bag Store Lockers 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-5114 Cleaners Store
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-5117 Cleaners Store
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-6001 DINING AND CATERING
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-6002 Office, Kitchen 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-6003 Food Store, Kitchen Dry 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-6004 Cold Store, Kitchen 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-6005 Cold Store, Kitchen Freezer 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-6006 Toilet (With Changing Area) 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-6007 Changing Room, With Showers Pupils 1 And Toilets, Suite Pupils, Other 1
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-6008 Changing Room, With Showers Pupils 2 And Toilets, Suite Pupils, Other 2
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-6009 Music Practice Room 2
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-6011 Hygiene Room 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-6042 First Aid Post Sick Bay 1 And Stairway 7
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-6069 Circulation Space Horizontal On And Coats And Bag Store Lockers 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-7001 DINING AND CATERING 3D
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-7003 Dishwashing
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-7101 Food Prep Area, Kitchen Servery And Wash Up 1 Electrical Plan
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-7201 Food Prep Area, Kitchen Servery And Wash Up 1 Electrical Elevations
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-7301 Food Prep Area, Kitchen Servery And Wash Up 1 Mechanical Plan
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-7401 Food Prep Area, Kitchen Servery And Wash Up 1 Mechanical Elevations
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-7501 Dishwash Services Requirements
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-8001 Music Practice Room 1
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-8003 Music Practice Room Extensive 1
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-9001 Classroom Store, Room Off Sen Room 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-00-D-O-9003 Teaching Resources Store Music 2
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1000 First Floor GA 1 Of 2
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1001 First Floor GA 2 Of 2
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1002 Classroom General 2
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1003 Classroom General 3
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1004 Classroom General 4
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1005 Classroom General 5
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1006 Classroom General 6
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1007 Classroom General 7
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1008 Classroom General 8
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1009 Classroom General 9
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1021 Classroom General 1
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1101 ICT RICH CLASSROOM 1
P06 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1102 ICT RICH CLASSROOM 2
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-1108 Art Room General
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-3006 Medical Treatment Mi Room 1 And 3007 Sen Resource Space 1
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-3009 Small Group Room Large Sen Etc. 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-4002 Meeting Room Conference 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-4007 Office Pastoral 1 And 5002 Teaching Resources Store It Gt Off Corridor 2
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-4012 Office With Meeting Area, 2 Person 1
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-4013 Office With Meeting Area, 2 Person 2
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-4016 Office Senco, Learning Support 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-4017 Staff Workroom ICT Technicians 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-5006 Teaching Resources Store Off Art Room 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-5017 Classroom Store, Room Off Sen Room 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-5104 Secure Storeroom 2
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-5110 Coats And Bag Store Lockers 2
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-5111 Coats And Bag Store Lockers 3
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-5112 Coats And Bag Store Lockers 4
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-5113 Coats And Bag Store Lockers 5
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-01-D-O-5116 Cleaners' Store 3
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1010 Classroom General 10
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1011 Classroom General 11
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1012 Classroom General 12
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1013 Classroom General 13
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1014 Classroom General 14
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1015 Classroom General 15
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1016 Classroom General 16
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1042 6042P Stairway 7 And 5113A Coats And Bag Store Lockers 5
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1103 Science Laboratories Restrictive, Extg 1
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1104 Science Laboratories Restrictive, Extg 2
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1105 Science Laboratories Restrictive, Extg 3
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1106 Science Laboratories Restrictive, Extg 4
P04 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-1107 Science Laboratories Restrictive, Extg 5
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-2000 SECOND FLOOR GA
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-2042 6042O Stairway 7 And 5113B Coats And Bag Store Lockers 5
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-3008 Small Group Room Medium 1 And 6042T Stairway 7
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-3042 6042N Stairway 7, 5113C And 5113D Coats And Bag Store Lockers 5
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-4001 Staff Workroom Teaching Staff 1 And Teaching Resources Store It Gt Off Corridor 3
P05 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-4014 Office With Meeting Area, 2 Person 3
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-5004 Science Prep Option 1
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-5005 Chemical Store 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-5020 Science Prep
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-5102 General Storeroom Central Stock 1
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-5115 Cleaners' Store 2
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-6113 Coats And Bags Store Lockers 5
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-7113 Coats And Bags Store Lockers 5
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-8113 Coats And Bags Store Lockers 5
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-02-D-O-9113 Coats And Bags Store Lockers 5
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-ZZ-L-O-0005 FFE Gap Analysis and Occupancy Schedule
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-ZZ-L-O-0006 Catering Equipment Schedule
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-ZZ-L-O-0007 FFE Cost Plan
P01 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-ZZ-M-O-0001 FFE REVIT MODEL
P11 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-ZZ-M-O-0002 FFE IFC MODEL
P09 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-ZZ-M-O-0003 FFE NAVIS MODEL
P07 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-ZZ-M-O-0004 CATERING IFC MODEL
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-ZZ-M-O-0005 CATERING REVIT MODEL
P03 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)
FS1018-PIN-ZZ-ZZ-M-O-0006 CATERING NWC MODEL
P02 | 2025-03-13 | DFE Review | Pending | (blank) | (blank)

## RawData
Project Name | Date Generated
FS1018 DfE Wisbech Free School | 2025-03-23
Document Number | Title | Revision | Workflow Status | Date In | Step Name | Step Outcome | Date of Comments | Comments | Latest revision? | (Helper) Num + Title | (Helper) Hyperlink
FS1018-ADT-ZZ-00-D-J-0001 | Acoustic criteria - ground floor | P01 | Completed | 2023-09-06 | Architectural Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-ADT-ZZ-00-D-J-0001 Acoustic criteria - ground floor | FS1018-ADT-ZZ-00-D-J-0001
FS1018-ADT-ZZ-00-D-J-0001 | BB93 Acoustic Criteria Ground Floor | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ADT-ZZ-00-D-J-0001 BB93 Acoustic Criteria Ground Floor | FS1018-ADT-ZZ-00-D-J-0001
FS1018-ADT-ZZ-00-D-J-0004 | Acoustic wall types - ground floor | P01 | Completed | 2023-09-06 | Architectural Review | B3 - Partially Accepted with Comments | 2023-09-21 | Have the internal wall types been developed to take into account the minimum wall thicknesses to satisfy the acoustic requirements, which vary from 250 - 600mm studs? | FALSE | FS1018-ADT-ZZ-00-D-J-0004 Acoustic wall types - ground floor | FS1018-ADT-ZZ-00-D-J-0004
FS1018-ADT-ZZ-00-D-J-0004 | Acoustic Wall Types Ground Floor | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ADT-ZZ-00-D-J-0004 Acoustic Wall Types Ground Floor | FS1018-ADT-ZZ-00-D-J-0004
FS1018-ADT-ZZ-01-D-J-0002 | Acoustic criteria - first floor | P01 | Completed | 2023-09-06 | Architectural Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-ADT-ZZ-01-D-J-0002 Acoustic criteria - first floor | FS1018-ADT-ZZ-01-D-J-0002
FS1018-ADT-ZZ-01-D-J-0002 | BB93 Acoustic Criteria First Floor | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ADT-ZZ-01-D-J-0002 BB93 Acoustic Criteria First Floor | FS1018-ADT-ZZ-01-D-J-0002
FS1018-ADT-ZZ-01-D-J-0005 | Acoustic wall types - first floor | P01 | Completed | 2023-09-06 | Architectural Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on FS1018-ADT-ZZ-00-D-J-0004 | FALSE | FS1018-ADT-ZZ-01-D-J-0005 Acoustic wall types - first floor | FS1018-ADT-ZZ-01-D-J-0005
FS1018-ADT-ZZ-01-D-J-0005 | Acoustic Wall Types First Floor | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ADT-ZZ-01-D-J-0005 Acoustic Wall Types First Floor | FS1018-ADT-ZZ-01-D-J-0005
FS1018-ADT-ZZ-02-D-J-0003 | Acoustic criteria - second floor | P01 | Completed | 2023-09-06 | Architectural Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-ADT-ZZ-02-D-J-0003 Acoustic criteria - second floor | FS1018-ADT-ZZ-02-D-J-0003
FS1018-ADT-ZZ-02-D-J-0003 | BB93 Acoustic Criteria Second Floor | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ADT-ZZ-02-D-J-0003 BB93 Acoustic Criteria Second Floor | FS1018-ADT-ZZ-02-D-J-0003
FS1018-ADT-ZZ-02-D-J-0006 | Acoustic wall types - second floor | P01 | Completed | 2023-09-06 | Architectural Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on FS1018-ADT-ZZ-00-D-J-0004 | FALSE | FS1018-ADT-ZZ-02-D-J-0006 Acoustic wall types - second floor | FS1018-ADT-ZZ-02-D-J-0006
FS1018-ADT-ZZ-02-D-J-0006 | Acoustic Wall Types Second Floor | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ADT-ZZ-02-D-J-0006 Acoustic Wall Types Second Floor | FS1018-ADT-ZZ-02-D-J-0006
FS1018-ADT-ZZ-ZZ-T-J-0001 | Stage 3 acoustic strategy | P01 | Completed | 2023-09-06 | Architectural Review | B3 - Partially Accepted with Comments | 2023-09-21 | Refer to comment on document | FALSE | FS1018-ADT-ZZ-ZZ-T-J-0001 Stage 3 acoustic strategy | FS1018-ADT-ZZ-ZZ-T-J-0001
FS1018-ADT-ZZ-ZZ-T-J-0001 | Acoustic Strategy | P01 | Completed | 2024-08-28 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ADT-ZZ-ZZ-T-J-0001 Acoustic Strategy | FS1018-ADT-ZZ-ZZ-T-J-0001
FS1018-ADT-ZZ-ZZ-T-J-0001 | Acoustic Strategy | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ADT-ZZ-ZZ-T-J-0001 Acoustic Strategy | FS1018-ADT-ZZ-ZZ-T-J-0001
FS1018-ADT-ZZ-ZZ-T-Y-0002 | Environmental Noise Impact Assessment | P01 | Completed | 2024-08-08 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ADT-ZZ-ZZ-T-Y-0002 Environmental Noise Impact Assessment | FS1018-ADT-ZZ-ZZ-T-Y-0002
FS1018-ADT-ZZ-ZZ-T-Y-0002 | Environmental Noise Impact Assessment | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ADT-ZZ-ZZ-T-Y-0002 Environmental Noise Impact Assessment | FS1018-ADT-ZZ-ZZ-T-Y-0002
FS1018-AGL-XX-XX-L-X-0007 | Risk Register | P01 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-AGL-XX-XX-L-X-0007 Risk Register | FS1018-AGL-XX-XX-L-X-0007
FS1018-AGL-ZZ-00-D-E-6101 | Level 00 Distribution Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Cables or other electrical equipment shall not be installed in a protected escape route unless part of an essential fire safety or related safety system, general needs lighting, socket- outlets provided for cleaning or maintenance. please refer to the latest BS 7671 18th edition (regulation 422.2). Data containment shall be installed at 300mm away from LV submain tray inorder to migitate the electromagnetic interference issue. Fire alarm cables should have been installed independently of the other cables. Separate partition required in the services shaft to protect the fire alarm and data tray Confirm which DB supply serves the furniture store, plantroom (heat source and water heater) | FALSE | FS1018-AGL-ZZ-00-D-E-6101 Level 00 Distribution Strategy | FS1018-AGL-ZZ-00-D-E-6101
FS1018-AGL-ZZ-00-D-E-6110 | Level 00 Containment Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6110 Level 00 Containment Sheet 1 | FS1018-AGL-ZZ-00-D-E-6110
FS1018-AGL-ZZ-00-D-E-6111 | Level 00 Containment Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6111 Level 00 Containment Sheet 2 | FS1018-AGL-ZZ-00-D-E-6111
FS1018-AGL-ZZ-00-D-E-6112 | Level 00 Containment Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6112 Level 00 Containment Sheet 3 | FS1018-AGL-ZZ-00-D-E-6112
FS1018-AGL-ZZ-00-D-E-6114 | Building Electrical Switchroom Details | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6114 Building Electrical Switchroom Details | FS1018-AGL-ZZ-00-D-E-6114
FS1018-AGL-ZZ-00-D-E-6210 | Level 00 Small Power And Data Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6210 Level 00 Small Power And Data Sheet 1 | FS1018-AGL-ZZ-00-D-E-6210
FS1018-AGL-ZZ-00-D-E-6211 | Level 00 Small Power And Data Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6211 Level 00 Small Power And Data Sheet 2 | FS1018-AGL-ZZ-00-D-E-6211
FS1018-AGL-ZZ-00-D-E-6212 | Level 00 Small Power And Data Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6212 Level 00 Small Power And Data Sheet 3 | FS1018-AGL-ZZ-00-D-E-6212
FS1018-AGL-ZZ-00-D-E-6213 | Level 00 MSER Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6213 Level 00 MSER Sheet 1 | FS1018-AGL-ZZ-00-D-E-6213
FS1018-AGL-ZZ-00-D-E-6214 | Level 00 MSER Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6214 Level 00 MSER Sheet 2 | FS1018-AGL-ZZ-00-D-E-6214
FS1018-AGL-ZZ-00-D-E-6215 | Level 00 MSER Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6215 Level 00 MSER Sheet 3 | FS1018-AGL-ZZ-00-D-E-6215
FS1018-AGL-ZZ-00-D-E-6301 | Level 00 Lighting Lux Levels Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | 200lux level to be achived in front of lift. Confirm the lux level requirements of cold store, food store, kicthe office areas near to food prep area Confirm why two lux requirements for music practice rooms? It appears that in various areas, the same rooms have different lux requirements (Eg. Confidential Meeting rooms near entrance) | FALSE | FS1018-AGL-ZZ-00-D-E-6301 Level 00 Lighting Lux Levels Strategy | FS1018-AGL-ZZ-00-D-E-6301
FS1018-AGL-ZZ-00-D-E-6302 | Level 00 Lighting Controls Strategy | P01 | Completed | 2023-09-06 | Electrical Review | A3 - Accepted | 2023-10-02 |  | FALSE | FS1018-AGL-ZZ-00-D-E-6302 Level 00 Lighting Controls Strategy | FS1018-AGL-ZZ-00-D-E-6302
FS1018-AGL-ZZ-00-D-E-6310 | Level 00 Lighting Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6310 Level 00 Lighting Sheet 1 | FS1018-AGL-ZZ-00-D-E-6310
FS1018-AGL-ZZ-00-D-E-6311 | Level 00 Lighting Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6311 Level 00 Lighting Sheet 2 | FS1018-AGL-ZZ-00-D-E-6311
FS1018-AGL-ZZ-00-D-E-6312 | Level 00 Lighting Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6312 Level 00 Lighting Sheet 3 | FS1018-AGL-ZZ-00-D-E-6312
FS1018-AGL-ZZ-00-D-E-6801 | Level 00 Fire Alarm Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Confirm the location of fire alarm panel. Confirm the fire alarm detection location of triple height spaces such as assembly halls, sports halls. | FALSE | FS1018-AGL-ZZ-00-D-E-6801 Level 00 Fire Alarm Strategy | FS1018-AGL-ZZ-00-D-E-6801
FS1018-AGL-ZZ-00-D-E-6802 | Level 00 CCTV and Access Control Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Confirm that the door access control is linked to the fire alarm panel for fail-safe operation during emergency evacuation. | FALSE | FS1018-AGL-ZZ-00-D-E-6802 Level 00 CCTV and Access Control Strategy | FS1018-AGL-ZZ-00-D-E-6802
FS1018-AGL-ZZ-00-D-E-6803 | Level 00 PA Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | BS5839-1 says fire alarm sounder should not be used for purposes other than warning of fire, unless the response required is identical to that required in the event of fire (i.e immediate evacuation by use of all escape routes). However, as an established exception, the fire alarm signal may be used in schools to indicate start or finish of predetermined periods. The duration of such signal should not exceed 5s. Please confirm if the PA system and the class change system are independent of the fire alarm system. | FALSE | FS1018-AGL-ZZ-00-D-E-6803 Level 00 PA Strategy | FS1018-AGL-ZZ-00-D-E-6803
FS1018-AGL-ZZ-00-D-E-6810 | Level 00 Fire Alarm Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6810 Level 00 Fire Alarm Sheet 1 | FS1018-AGL-ZZ-00-D-E-6810
FS1018-AGL-ZZ-00-D-E-6811 | Level 00 Fire Alarm Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6811 Level 00 Fire Alarm Sheet 2 | FS1018-AGL-ZZ-00-D-E-6811
FS1018-AGL-ZZ-00-D-E-6812 | Level 00 Fire Alarm Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6812 Level 00 Fire Alarm Sheet 3 | FS1018-AGL-ZZ-00-D-E-6812
FS1018-AGL-ZZ-00-D-E-6820 | Level 00 Fire Alarm Zoning Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6820 Level 00 Fire Alarm Zoning Sheet 1 | FS1018-AGL-ZZ-00-D-E-6820
FS1018-AGL-ZZ-00-D-E-6821 | Level 00 Fire Alarm Zoning Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6821 Level 00 Fire Alarm Zoning Sheet 2 | FS1018-AGL-ZZ-00-D-E-6821
FS1018-AGL-ZZ-00-D-E-6822 | Level 00 Fire Alarm Zoning Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6822 Level 00 Fire Alarm Zoning Sheet 3 | FS1018-AGL-ZZ-00-D-E-6822
FS1018-AGL-ZZ-00-D-E-6840 | Level 00 Security Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6840 Level 00 Security Sheet 1 | FS1018-AGL-ZZ-00-D-E-6840
FS1018-AGL-ZZ-00-D-E-6841 | Level 00 Security Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6841 Level 00 Security Sheet 2 | FS1018-AGL-ZZ-00-D-E-6841
FS1018-AGL-ZZ-00-D-E-6842 | Level 00 Security Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-6842 Level 00 Security Sheet 3 | FS1018-AGL-ZZ-00-D-E-6842
FS1018-AGL-ZZ-00-D-E-9001 | Photovoltaic Canopies | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-E-9001 Photovoltaic Canopies | FS1018-AGL-ZZ-00-D-E-9001
FS1018-AGL-ZZ-00-D-M-5201 | Level 00 Above Ground Drainage Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-09-29 | Would have expected to see PH major routes/ proposed sizes and riser locations. Currently no pipework shown within drawings for review | FALSE | FS1018-AGL-ZZ-00-D-M-5201 Level 00 Above Ground Drainage Strategy | FS1018-AGL-ZZ-00-D-M-5201
FS1018-AGL-ZZ-00-D-M-5210 | Level 00 Above Ground Drainage Sheet 1 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-00-D-M-5210 Level 00 Above Ground Drainage Sheet 1 | FS1018-AGL-ZZ-00-D-M-5210
FS1018-AGL-ZZ-00-D-M-5211 | Level 00 Above Ground Drainage Sheet 2 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-00-D-M-5211 Level 00 Above Ground Drainage Sheet 2 | FS1018-AGL-ZZ-00-D-M-5211
FS1018-AGL-ZZ-00-D-M-5212 | Level 00 Above Ground Drainage Sheet 3 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-00-D-M-5212 Level 00 Above Ground Drainage Sheet 3 | FS1018-AGL-ZZ-00-D-M-5212
FS1018-AGL-ZZ-00-D-M-5301 | Level 00 Domestic Water Services Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-09-29 | Would have expected to see PH major routes/ proposed sizes and riser locations. Currently no pipework shown within drawings for review | FALSE | FS1018-AGL-ZZ-00-D-M-5301 Level 00 Domestic Water Services Strategy | FS1018-AGL-ZZ-00-D-M-5301
FS1018-AGL-ZZ-00-D-M-5310 | Level 00 Domestic Water Services Sheet 1 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-00-D-M-5310 Level 00 Domestic Water Services Sheet 1 | FS1018-AGL-ZZ-00-D-M-5310
FS1018-AGL-ZZ-00-D-M-5311 | Level 00 Domestic Water Services Sheet 2 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-00-D-M-5311 Level 00 Domestic Water Services Sheet 2 | FS1018-AGL-ZZ-00-D-M-5311
FS1018-AGL-ZZ-00-D-M-5312 | Level 00 Domestic Water Services Sheet 3 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-00-D-M-5312 Level 00 Domestic Water Services Sheet 3 | FS1018-AGL-ZZ-00-D-M-5312
FS1018-AGL-ZZ-00-D-M-5401 | Level 00 Gas Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Would have expected to see major gas routes/ proposed sizes and riser locations in stage 3 design. Currently no pipework shown within drawings for review. | FALSE | FS1018-AGL-ZZ-00-D-M-5401 Level 00 Gas Strategy | FS1018-AGL-ZZ-00-D-M-5401
FS1018-AGL-ZZ-00-D-M-5410 | Level 00 Gas | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-00-D-M-5410 Level 00 Gas | FS1018-AGL-ZZ-00-D-M-5410
FS1018-AGL-ZZ-00-D-M-5601 | Level 00 Heating and Cooling Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Would have expected to see major heating and cooling routes/ proposed sizes and riser locations in stage 3 design. Currently no pipework shown within drawings for review. | FALSE | FS1018-AGL-ZZ-00-D-M-5601 Level 00 Heating and Cooling Strategy | FS1018-AGL-ZZ-00-D-M-5601
FS1018-AGL-ZZ-00-D-M-5610 | Level 00 Heating and Cooling Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-M-5610 Level 00 Heating and Cooling Sheet 1 | FS1018-AGL-ZZ-00-D-M-5610
FS1018-AGL-ZZ-00-D-M-5611 | Level 00 Heating and Cooling Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-M-5611 Level 00 Heating and Cooling Sheet 2 | FS1018-AGL-ZZ-00-D-M-5611
FS1018-AGL-ZZ-00-D-M-5612 | Level 00 Heating and Cooling Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-M-5612 Level 00 Heating and Cooling Sheet 3 | FS1018-AGL-ZZ-00-D-M-5612
FS1018-AGL-ZZ-00-D-M-5701 | Level 00 Ventilation Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Would have expected to see major ventilation routes/ proposed sizes and riser locations in stage 3 design. Currently no pipework shown within drawings for review. | FALSE | FS1018-AGL-ZZ-00-D-M-5701 Level 00 Ventilation Strategy | FS1018-AGL-ZZ-00-D-M-5701
FS1018-AGL-ZZ-00-D-M-5710 | Level 00 Ventilation Sheet 1 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-00-D-M-5710 Level 00 Ventilation Sheet 1 | FS1018-AGL-ZZ-00-D-M-5710
FS1018-AGL-ZZ-00-D-M-5711 | Level 00 Ventilation Sheet 2 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-00-D-M-5711 Level 00 Ventilation Sheet 2 | FS1018-AGL-ZZ-00-D-M-5711
FS1018-AGL-ZZ-00-D-M-5712 | Level 00 Ventilation Sheet 3 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-00-D-M-5712 Level 00 Ventilation Sheet 3 | FS1018-AGL-ZZ-00-D-M-5712
FS1018-AGL-ZZ-00-D-M-5810 | Level 00 Plantroom Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-M-5810 Level 00 Plantroom Sheet 1 | FS1018-AGL-ZZ-00-D-M-5810
FS1018-AGL-ZZ-00-D-M-5811 | Level 00 Plantroom Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-M-5811 Level 00 Plantroom Sheet 2 | FS1018-AGL-ZZ-00-D-M-5811
FS1018-AGL-ZZ-00-D-Z-6010 | Level 00 Builderswork Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-Z-6010 Level 00 Builderswork Sheet 1 | FS1018-AGL-ZZ-00-D-Z-6010
FS1018-AGL-ZZ-00-D-Z-6011 | Level 00 Builderswork Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-Z-6011 Level 00 Builderswork Sheet 2 | FS1018-AGL-ZZ-00-D-Z-6011
FS1018-AGL-ZZ-00-D-Z-6012 | Level 00 Builderswork Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-Z-6012 Level 00 Builderswork Sheet 3 | FS1018-AGL-ZZ-00-D-Z-6012
FS1018-AGL-ZZ-00-D-Z-9501 | Level 00 Plant Access and Maintenance Strategy | P01 | Completed | 2023-09-06 | Multiple Discipline Review | B3 - Partially Accepted with Comments | 2023-10-06 | '- Would have expected to see critical maintenance information including maintenance space requirements, delivery path, etc. Currently only showing “access required” in the drawing. - Please confirm the access, maintenance, and replacement strategy for lighting and smoke detection systems in the assembly halls and sports hall. | FALSE | FS1018-AGL-ZZ-00-D-Z-9501 Level 00 Plant Access and Maintenance Strategy | FS1018-AGL-ZZ-00-D-Z-9501
FS1018-AGL-ZZ-00-D-Z-9610 | Level 00 Reflected Ceiling Plan Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-Z-9610 Level 00 Reflected Ceiling Plan Sheet 1 | FS1018-AGL-ZZ-00-D-Z-9610
FS1018-AGL-ZZ-00-D-Z-9611 | Level 00 Reflected Ceiling Plan Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-Z-9611 Level 00 Reflected Ceiling Plan Sheet 2 | FS1018-AGL-ZZ-00-D-Z-9611
FS1018-AGL-ZZ-00-D-Z-9612 | Level 00 Reflected Ceiling Plan Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-00-D-Z-9612 Level 00 Reflected Ceiling Plan Sheet 3 | FS1018-AGL-ZZ-00-D-Z-9612
FS1018-AGL-ZZ-01-D-E-6101 | Level 01 Distribution Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Data containment shall be installed at 300mm away from LV submain tray inorder to migitate the electromagnetic interference issue. Fire alarm cables should have been installed independently of the other cables. Separate partition required in the services shaft to protect the fire alarm and data tray | FALSE | FS1018-AGL-ZZ-01-D-E-6101 Level 01 Distribution Strategy | FS1018-AGL-ZZ-01-D-E-6101
FS1018-AGL-ZZ-01-D-E-6110 | Level 01 Containment Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6110 Level 01 Containment Sheet 1 | FS1018-AGL-ZZ-01-D-E-6110
FS1018-AGL-ZZ-01-D-E-6111 | Level 01 Containment Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6111 Level 01 Containment Sheet 2 | FS1018-AGL-ZZ-01-D-E-6111
FS1018-AGL-ZZ-01-D-E-6210 | Level 01 Small Power And Data Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6210 Level 01 Small Power And Data Sheet 1 | FS1018-AGL-ZZ-01-D-E-6210
FS1018-AGL-ZZ-01-D-E-6211 | Level 01 Small Power And Data Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6211 Level 01 Small Power And Data Sheet 2 | FS1018-AGL-ZZ-01-D-E-6211
FS1018-AGL-ZZ-01-D-E-6212 | Level 01 MSER Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6212 Level 01 MSER Sheet 1 | FS1018-AGL-ZZ-01-D-E-6212
FS1018-AGL-ZZ-01-D-E-6213 | Level 01 MSER Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6213 Level 01 MSER Sheet 2 | FS1018-AGL-ZZ-01-D-E-6213
FS1018-AGL-ZZ-01-D-E-6301 | Level 01 Lighting Lux Levels Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | 200lux level to be achived in front of lift. | FALSE | FS1018-AGL-ZZ-01-D-E-6301 Level 01 Lighting Lux Levels Strategy | FS1018-AGL-ZZ-01-D-E-6301
FS1018-AGL-ZZ-01-D-E-6302 | Level 01 Lighting Controls Strategy | P01 | Completed | 2023-09-06 | Electrical Review | A3 - Accepted | 2023-10-02 |  | FALSE | FS1018-AGL-ZZ-01-D-E-6302 Level 01 Lighting Controls Strategy | FS1018-AGL-ZZ-01-D-E-6302
FS1018-AGL-ZZ-01-D-E-6310 | Level 01 Lighting Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6310 Level 01 Lighting Sheet 1 | FS1018-AGL-ZZ-01-D-E-6310
FS1018-AGL-ZZ-01-D-E-6311 | Level 01 Lighting Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6311 Level 01 Lighting Sheet 2 | FS1018-AGL-ZZ-01-D-E-6311
FS1018-AGL-ZZ-01-D-E-6801 | Level 01 Fire Alarm Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Confirm the fire alarm detection location of triple height spaces such as assembly halls, sports halls. | FALSE | FS1018-AGL-ZZ-01-D-E-6801 Level 01 Fire Alarm Strategy | FS1018-AGL-ZZ-01-D-E-6801
FS1018-AGL-ZZ-01-D-E-6802 | Level 01 CCTV and Access Control Strategy | P01 | Completed | 2023-09-06 | Electrical Review | A3 - Accepted | 2023-10-02 |  | FALSE | FS1018-AGL-ZZ-01-D-E-6802 Level 01 CCTV and Access Control Strategy | FS1018-AGL-ZZ-01-D-E-6802
FS1018-AGL-ZZ-01-D-E-6803 | Level 01 PA Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | BS5839-1 says fire alarm sounder should not be used for purposes other than warning of fire, unless the response required is identical to that required in the event of fire (i.e immediate evacuation by use of all escape routes). However, as an established exception, the fire alarm signal may be used in schools to indicate start or finish of predetermined periods. The duration of such signal should not exceed 5s. Please confirm if the PA system and the class change system are independent of the fire alarm system. | FALSE | FS1018-AGL-ZZ-01-D-E-6803 Level 01 PA Strategy | FS1018-AGL-ZZ-01-D-E-6803
FS1018-AGL-ZZ-01-D-E-6810 | Level 01 Fire Alarm Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6810 Level 01 Fire Alarm Sheet 1 | FS1018-AGL-ZZ-01-D-E-6810
FS1018-AGL-ZZ-01-D-E-6811 | Level 01 Fire Alarm Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6811 Level 01 Fire Alarm Sheet 2 | FS1018-AGL-ZZ-01-D-E-6811
FS1018-AGL-ZZ-01-D-E-6820 | Level 01 Fire Alarm Zoning Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6820 Level 01 Fire Alarm Zoning Sheet 1 | FS1018-AGL-ZZ-01-D-E-6820
FS1018-AGL-ZZ-01-D-E-6821 | Level 01 Fire Alarm Zoning Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6821 Level 01 Fire Alarm Zoning Sheet 2 | FS1018-AGL-ZZ-01-D-E-6821
FS1018-AGL-ZZ-01-D-E-6840 | Level 01 Security Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6840 Level 01 Security Sheet 1 | FS1018-AGL-ZZ-01-D-E-6840
FS1018-AGL-ZZ-01-D-E-6841 | Level 01 Security Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-E-6841 Level 01 Security Sheet 2 | FS1018-AGL-ZZ-01-D-E-6841
FS1018-AGL-ZZ-01-D-M-5201 | Level 01 Above Ground Drainage Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-09-29 | Would have expected to see PH major routes/ proposed sizes and riser locations. Currently no pipework shown within drawings for review | FALSE | FS1018-AGL-ZZ-01-D-M-5201 Level 01 Above Ground Drainage Strategy | FS1018-AGL-ZZ-01-D-M-5201
FS1018-AGL-ZZ-01-D-M-5210 | Level 01 Above Ground Drainage Sheet 1 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-01-D-M-5210 Level 01 Above Ground Drainage Sheet 1 | FS1018-AGL-ZZ-01-D-M-5210
FS1018-AGL-ZZ-01-D-M-5211 | Level 01 Above Ground Drainage Sheet 2 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-01-D-M-5211 Level 01 Above Ground Drainage Sheet 2 | FS1018-AGL-ZZ-01-D-M-5211
FS1018-AGL-ZZ-01-D-M-5301 | Level 01 Domestic Water Services Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-09-29 | Would have expected to see PH major routes/ proposed sizes and riser locations. Currently no pipework shown within drawings for review | FALSE | FS1018-AGL-ZZ-01-D-M-5301 Level 01 Domestic Water Services Strategy | FS1018-AGL-ZZ-01-D-M-5301
FS1018-AGL-ZZ-01-D-M-5310 | Level 01 Domestic Water Services Sheet 1 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-01-D-M-5310 Level 01 Domestic Water Services Sheet 1 | FS1018-AGL-ZZ-01-D-M-5310
FS1018-AGL-ZZ-01-D-M-5311 | Level 01 Domestic Water Services Sheet 2 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-01-D-M-5311 Level 01 Domestic Water Services Sheet 2 | FS1018-AGL-ZZ-01-D-M-5311
FS1018-AGL-ZZ-01-D-M-5401 | Level 01 Gas Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Would have expected to see major gas routes/ proposed sizes and riser locations in stage 3 design. Currently no pipework shown within drawings for review. | FALSE | FS1018-AGL-ZZ-01-D-M-5401 Level 01 Gas Strategy | FS1018-AGL-ZZ-01-D-M-5401
FS1018-AGL-ZZ-01-D-M-5410 | Level 01 Gas | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-01-D-M-5410 Level 01 Gas | FS1018-AGL-ZZ-01-D-M-5410
FS1018-AGL-ZZ-01-D-M-5601 | Level 01 Heating and Cooling Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Would have expected to see major heating and cooling routes/ proposed sizes and riser locations in stage 3 design. Currently no pipework shown within drawings for review. | FALSE | FS1018-AGL-ZZ-01-D-M-5601 Level 01 Heating and Cooling Strategy | FS1018-AGL-ZZ-01-D-M-5601
FS1018-AGL-ZZ-01-D-M-5610 | Level 01 Heating and Cooling Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-M-5610 Level 01 Heating and Cooling Sheet 1 | FS1018-AGL-ZZ-01-D-M-5610
FS1018-AGL-ZZ-01-D-M-5611 | Level 01 Heating and Cooling Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-M-5611 Level 01 Heating and Cooling Sheet 2 | FS1018-AGL-ZZ-01-D-M-5611
FS1018-AGL-ZZ-01-D-M-5701 | Level 01 Ventilation Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Would have expected to see major ventilation routes/ proposed sizes and riser locations in stage 3 design. Currently no pipework shown within drawings for review. | FALSE | FS1018-AGL-ZZ-01-D-M-5701 Level 01 Ventilation Strategy | FS1018-AGL-ZZ-01-D-M-5701
FS1018-AGL-ZZ-01-D-M-5710 | Level 01 Ventilation Sheet 1 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-01-D-M-5710 Level 01 Ventilation Sheet 1 | FS1018-AGL-ZZ-01-D-M-5710
FS1018-AGL-ZZ-01-D-M-5711 | Level 01 Ventilation Sheet 2 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-01-D-M-5711 Level 01 Ventilation Sheet 2 | FS1018-AGL-ZZ-01-D-M-5711
FS1018-AGL-ZZ-01-D-Z-6010 | Level 01 Builderswork Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-Z-6010 Level 01 Builderswork Sheet 1 | FS1018-AGL-ZZ-01-D-Z-6010
FS1018-AGL-ZZ-01-D-Z-6011 | Level 01 Builderswork Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-Z-6011 Level 01 Builderswork Sheet 2 | FS1018-AGL-ZZ-01-D-Z-6011
FS1018-AGL-ZZ-01-D-Z-9501 | Level 01 Plant Access and Maintenance Strategy | P01 | Completed | 2023-09-06 | Multiple Discipline Review | B3 - Partially Accepted with Comments | 2023-10-06 | '- Would have expected to see critical maintenance information including maintenance space requirements, delivery path, etc. Currently only showing “access required” in the drawing. - Please confirm the access, maintenance, and replacement strategy for lighting and smoke detection systems in the assembly halls and sports hall. | FALSE | FS1018-AGL-ZZ-01-D-Z-9501 Level 01 Plant Access and Maintenance Strategy | FS1018-AGL-ZZ-01-D-Z-9501
FS1018-AGL-ZZ-01-D-Z-9610 | Level 01 Reflected Ceiling Plan Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-Z-9610 Level 01 Reflected Ceiling Plan Sheet 1 | FS1018-AGL-ZZ-01-D-Z-9610
FS1018-AGL-ZZ-01-D-Z-9611 | Level 01 Reflected Ceiling Plan Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-01-D-Z-9611 Level 01 Reflected Ceiling Plan Sheet 2 | FS1018-AGL-ZZ-01-D-Z-9611
FS1018-AGL-ZZ-02-D-E-6101 | Level 02 Distribution Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Data containment shall be installed at 300mm away from LV submain tray inorder to migitate the electromagnetic interference issue. Fire alarm cables should have been installed independently of the other cables. Separate partition required in the services shaft to protect the fire alarm and data tray | FALSE | FS1018-AGL-ZZ-02-D-E-6101 Level 02 Distribution Strategy | FS1018-AGL-ZZ-02-D-E-6101
FS1018-AGL-ZZ-02-D-E-6110 | Level 02 Containment Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6110 Level 02 Containment Sheet 1 | FS1018-AGL-ZZ-02-D-E-6110
FS1018-AGL-ZZ-02-D-E-6111 | Level 02 Containment Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6111 Level 02 Containment Sheet 2 | FS1018-AGL-ZZ-02-D-E-6111
FS1018-AGL-ZZ-02-D-E-6210 | Level 02 Small Power And Data Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6210 Level 02 Small Power And Data Sheet 1 | FS1018-AGL-ZZ-02-D-E-6210
FS1018-AGL-ZZ-02-D-E-6211 | Level 02 Small Power And Data Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6211 Level 02 Small Power And Data Sheet 2 | FS1018-AGL-ZZ-02-D-E-6211
FS1018-AGL-ZZ-02-D-E-6212 | Level 02 MSER Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6212 Level 02 MSER Sheet 1 | FS1018-AGL-ZZ-02-D-E-6212
FS1018-AGL-ZZ-02-D-E-6213 | Level 02 MSER Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6213 Level 02 MSER Sheet 2 | FS1018-AGL-ZZ-02-D-E-6213
FS1018-AGL-ZZ-02-D-E-6301 | Level 02 Lighting Lux Levels Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | 200lux level to be achived in front of lift. It is noted that the proposed lux level in the stairway is 100 lux, while lower levels have 150 lux. Lux levels should be the same throughout the stairways. | FALSE | FS1018-AGL-ZZ-02-D-E-6301 Level 02 Lighting Lux Levels Strategy | FS1018-AGL-ZZ-02-D-E-6301
FS1018-AGL-ZZ-02-D-E-6302 | Level 02 Lighting Controls Strategy | P01 | Completed | 2023-09-06 | Electrical Review | A3 - Accepted | 2023-10-02 |  | FALSE | FS1018-AGL-ZZ-02-D-E-6302 Level 02 Lighting Controls Strategy | FS1018-AGL-ZZ-02-D-E-6302
FS1018-AGL-ZZ-02-D-E-6310 | Level 02 Lighting Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6310 Level 02 Lighting Sheet 1 | FS1018-AGL-ZZ-02-D-E-6310
FS1018-AGL-ZZ-02-D-E-6311 | Level 02 Lighting Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6311 Level 02 Lighting Sheet 2 | FS1018-AGL-ZZ-02-D-E-6311
FS1018-AGL-ZZ-02-D-E-6801 | Level 02 Fire Alarm Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Confirm the fire alarm detection location of triple height spaces such as assembly halls, sports halls. | FALSE | FS1018-AGL-ZZ-02-D-E-6801 Level 02 Fire Alarm Strategy | FS1018-AGL-ZZ-02-D-E-6801
FS1018-AGL-ZZ-02-D-E-6802 | Level 02 CCTV and Access Control Strategy | P01 | Completed | 2023-09-06 | Electrical Review | A3 - Accepted | 2023-10-02 |  | FALSE | FS1018-AGL-ZZ-02-D-E-6802 Level 02 CCTV and Access Control Strategy | FS1018-AGL-ZZ-02-D-E-6802
FS1018-AGL-ZZ-02-D-E-6803 | Level 02 PA Strategy | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | BS5839-1 says fire alarm sounder should not be used for purposes other than warning of fire, unless the response required is identical to that required in the event of fire (i.e immediate evacuation by use of all escape routes). However, as an established exception, the fire alarm signal may be used in schools to indicate start or finish of predetermined periods. The duration of such signal should not exceed 5s. Please confirm if the PA system and the class change system are independent of the fire alarm system. | FALSE | FS1018-AGL-ZZ-02-D-E-6803 Level 02 PA Strategy | FS1018-AGL-ZZ-02-D-E-6803
FS1018-AGL-ZZ-02-D-E-6810 | Level 02 Fire Alarm Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6810 Level 02 Fire Alarm Sheet 1 | FS1018-AGL-ZZ-02-D-E-6810
FS1018-AGL-ZZ-02-D-E-6811 | Level 02 Fire Alarm Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6811 Level 02 Fire Alarm Sheet 2 | FS1018-AGL-ZZ-02-D-E-6811
FS1018-AGL-ZZ-02-D-E-6820 | Level 02 Fire Alarm Zoning Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6820 Level 02 Fire Alarm Zoning Sheet 1 | FS1018-AGL-ZZ-02-D-E-6820
FS1018-AGL-ZZ-02-D-E-6821 | Level 02 Fire Alarm Zoning Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6821 Level 02 Fire Alarm Zoning Sheet 2 | FS1018-AGL-ZZ-02-D-E-6821
FS1018-AGL-ZZ-02-D-E-6840 | Level 02 Security Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6840 Level 02 Security Sheet 1 | FS1018-AGL-ZZ-02-D-E-6840
FS1018-AGL-ZZ-02-D-E-6841 | Level 02 Security Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-E-6841 Level 02 Security Sheet 2 | FS1018-AGL-ZZ-02-D-E-6841
FS1018-AGL-ZZ-02-D-M-5201 | Level 02 Above Ground Drainage Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-09-29 | Would have expected to see PH major routes/ proposed sizes and riser locations. Currently no pipework shown within drawings for review | FALSE | FS1018-AGL-ZZ-02-D-M-5201 Level 02 Above Ground Drainage Strategy | FS1018-AGL-ZZ-02-D-M-5201
FS1018-AGL-ZZ-02-D-M-5210 | Level 02 Above Ground Drainage Sheet 1 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-02-D-M-5210 Level 02 Above Ground Drainage Sheet 1 | FS1018-AGL-ZZ-02-D-M-5210
FS1018-AGL-ZZ-02-D-M-5211 | Level 02 Above Ground Drainage Sheet 2 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-02-D-M-5211 Level 02 Above Ground Drainage Sheet 2 | FS1018-AGL-ZZ-02-D-M-5211
FS1018-AGL-ZZ-02-D-M-5301 | Level 02 Domestic Water Services Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-09-29 | Would have expected to see PH major routes/ proposed sizes and riser locations. Currently no pipework shown within drawings for review | FALSE | FS1018-AGL-ZZ-02-D-M-5301 Level 02 Domestic Water Services Strategy | FS1018-AGL-ZZ-02-D-M-5301
FS1018-AGL-ZZ-02-D-M-5310 | Level 02 Domestic Water Services Sheet 1 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-02-D-M-5310 Level 02 Domestic Water Services Sheet 1 | FS1018-AGL-ZZ-02-D-M-5310
FS1018-AGL-ZZ-02-D-M-5311 | Level 02 Domestic Water Services Sheet 2 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-02-D-M-5311 Level 02 Domestic Water Services Sheet 2 | FS1018-AGL-ZZ-02-D-M-5311
FS1018-AGL-ZZ-02-D-M-5401 | Level 02 Gas Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Would have expected to see major gas routes/ proposed sizes and riser locations in stage 3 design. Currently no pipework shown within drawings for review. | FALSE | FS1018-AGL-ZZ-02-D-M-5401 Level 02 Gas Strategy | FS1018-AGL-ZZ-02-D-M-5401
FS1018-AGL-ZZ-02-D-M-5410 | Level 02 Gas | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-02-D-M-5410 Level 02 Gas | FS1018-AGL-ZZ-02-D-M-5410
FS1018-AGL-ZZ-02-D-M-5601 | Level 02 Heating and Cooling Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Would have expected to see major heating and cooling routes/ proposed sizes and riser locations in stage 3 design. Currently no pipework shown within drawings for review. | FALSE | FS1018-AGL-ZZ-02-D-M-5601 Level 02 Heating and Cooling Strategy | FS1018-AGL-ZZ-02-D-M-5601
FS1018-AGL-ZZ-02-D-M-5610 | Level 02 Heating and Cooling Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-M-5610 Level 02 Heating and Cooling Sheet 1 | FS1018-AGL-ZZ-02-D-M-5610
FS1018-AGL-ZZ-02-D-M-5611 | Level 02 Heating and Cooling Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-M-5611 Level 02 Heating and Cooling Sheet 2 | FS1018-AGL-ZZ-02-D-M-5611
FS1018-AGL-ZZ-02-D-M-5701 | Level 02 Ventilation Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Would have expected to see major ventilation routes/ proposed sizes and riser locations in stage 3 design. Currently no pipework shown within drawings for review. | FALSE | FS1018-AGL-ZZ-02-D-M-5701 Level 02 Ventilation Strategy | FS1018-AGL-ZZ-02-D-M-5701
FS1018-AGL-ZZ-02-D-M-5710 | Level 02 Ventilation Sheet 1 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-02-D-M-5710 Level 02 Ventilation Sheet 1 | FS1018-AGL-ZZ-02-D-M-5710
FS1018-AGL-ZZ-02-D-M-5711 | Level 02 Ventilation Sheet 2 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-02-D-M-5711 Level 02 Ventilation Sheet 2 | FS1018-AGL-ZZ-02-D-M-5711
FS1018-AGL-ZZ-02-D-Z-6010 | Level 02 Builderswork Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-Z-6010 Level 02 Builderswork Sheet 1 | FS1018-AGL-ZZ-02-D-Z-6010
FS1018-AGL-ZZ-02-D-Z-6011 | Level 02 Builderswork Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-Z-6011 Level 02 Builderswork Sheet 2 | FS1018-AGL-ZZ-02-D-Z-6011
FS1018-AGL-ZZ-02-D-Z-9501 | Level 02 Plant Access and Maintenance Strategy | P01 | Completed | 2023-09-06 | Multiple Discipline Review | B3 - Partially Accepted with Comments | 2023-10-06 | '- Would have expected to see critical maintenance information including maintenance space requirements, delivery path, etc. Currently only showing “access required” in the drawing. - Please confirm the access, maintenance, and replacement strategy for lighting and smoke detection systems in the assembly halls and sports hall. | FALSE | FS1018-AGL-ZZ-02-D-Z-9501 Level 02 Plant Access and Maintenance Strategy | FS1018-AGL-ZZ-02-D-Z-9501
FS1018-AGL-ZZ-02-D-Z-9610 | Level 02 Reflected Ceiling Plan Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-Z-9610 Level 02 Reflected Ceiling Plan Sheet 1 | FS1018-AGL-ZZ-02-D-Z-9610
FS1018-AGL-ZZ-02-D-Z-9611 | Level 02 Reflected Ceiling Plan Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-02-D-Z-9611 Level 02 Reflected Ceiling Plan Sheet 2 | FS1018-AGL-ZZ-02-D-Z-9611
FS1018-AGL-ZZ-RF-D-E-6213 | Roof Level MSER | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-RF-D-E-6213 Roof Level MSER | FS1018-AGL-ZZ-RF-D-E-6213
FS1018-AGL-ZZ-RF-D-E-6810 | Roof Level Fire Alarm Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-RF-D-E-6810 Roof Level Fire Alarm Sheet 1 | FS1018-AGL-ZZ-RF-D-E-6810
FS1018-AGL-ZZ-RF-D-E-6811 | Roof Level Fire Alarm Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-RF-D-E-6811 Roof Level Fire Alarm Sheet 2 | FS1018-AGL-ZZ-RF-D-E-6811
FS1018-AGL-ZZ-RF-D-E-6840 | Roof Level Security Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-RF-D-E-6840 Roof Level Security Sheet 1 | FS1018-AGL-ZZ-RF-D-E-6840
FS1018-AGL-ZZ-RF-D-E-6841 | Roof Level Security Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-RF-D-E-6841 Roof Level Security Sheet 2 | FS1018-AGL-ZZ-RF-D-E-6841
FS1018-AGL-ZZ-RF-D-E-6842 | Roof Level Security Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-RF-D-E-6842 Roof Level Security Sheet 3 | FS1018-AGL-ZZ-RF-D-E-6842
FS1018-AGL-ZZ-RF-D-E-9001 | Photovoltaic | P01 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-AGL-ZZ-RF-D-E-9001 Photovoltaic | FS1018-AGL-ZZ-RF-D-E-9001
FS1018-AGL-ZZ-RF-D-E-9001 | Photovoltaic | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-RF-D-E-9001 Photovoltaic | FS1018-AGL-ZZ-RF-D-E-9001
FS1018-AGL-ZZ-RF-D-M-5210 | Roof Level Above Ground Drainage Sheet 1 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-RF-D-M-5210 Roof Level Above Ground Drainage Sheet 1 | FS1018-AGL-ZZ-RF-D-M-5210
FS1018-AGL-ZZ-RF-D-M-5211 | Roof Level Above Ground Drainage Sheet 2 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-RF-D-M-5211 Roof Level Above Ground Drainage Sheet 2 | FS1018-AGL-ZZ-RF-D-M-5211
FS1018-AGL-ZZ-RF-D-M-5212 | Roof Level Above Ground Drainage Sheet 3 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-RF-D-M-5212 Roof Level Above Ground Drainage Sheet 3 | FS1018-AGL-ZZ-RF-D-M-5212
FS1018-AGL-ZZ-RF-D-M-5301 | Roof Level Domestic Water Services Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-09-29 | Would have expected to see PH major routes/ proposed sizes and riser locations. Currently no pipework shown within drawings for review | FALSE | FS1018-AGL-ZZ-RF-D-M-5301 Roof Level Domestic Water Services Strategy | FS1018-AGL-ZZ-RF-D-M-5301
FS1018-AGL-ZZ-RF-D-M-5310 | Roof Level Domestic Water Services Sheet 1 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-RF-D-M-5310 Roof Level Domestic Water Services Sheet 1 | FS1018-AGL-ZZ-RF-D-M-5310
FS1018-AGL-ZZ-RF-D-M-5311 | Roof Level Domestic Water Services Sheet 2 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-RF-D-M-5311 Roof Level Domestic Water Services Sheet 2 | FS1018-AGL-ZZ-RF-D-M-5311
FS1018-AGL-ZZ-RF-D-M-5312 | Roof Level Domestic Water Services Sheet 3 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-RF-D-M-5312 Roof Level Domestic Water Services Sheet 3 | FS1018-AGL-ZZ-RF-D-M-5312
FS1018-AGL-ZZ-RF-D-M-5710 | Roof Level Ventilation Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-RF-D-M-5710 Roof Level Ventilation Sheet 1 | FS1018-AGL-ZZ-RF-D-M-5710
FS1018-AGL-ZZ-RF-D-M-5711 | Roof Level Ventilation Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-RF-D-M-5711 Roof Level Ventilation Sheet 2 | FS1018-AGL-ZZ-RF-D-M-5711
FS1018-AGL-ZZ-RF-D-M-5712 | Roof Level Ventilation Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-RF-D-M-5712 Roof Level Ventilation Sheet 3 | FS1018-AGL-ZZ-RF-D-M-5712
FS1018-AGL-ZZ-RF-D-M-5801 | Roof Level Plantroom Strategy | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Missing major airduct route and attenuator information for Kitchen AHU and extract fan. Any electrostatic precipitator for kitchen extract fan? | FALSE | FS1018-AGL-ZZ-RF-D-M-5801 Roof Level Plantroom Strategy | FS1018-AGL-ZZ-RF-D-M-5801
FS1018-AGL-ZZ-RF-D-Z-5810 | Roof Level Plantroom Sheet 1 | P01 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-AGL-ZZ-RF-D-Z-5810 Roof Level Plantroom Sheet 1 | FS1018-AGL-ZZ-RF-D-Z-5810
FS1018-AGL-ZZ-RF-D-Z-5810 | Roof Level Plantroom Sheet 1 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-RF-D-Z-5810 Roof Level Plantroom Sheet 1 | FS1018-AGL-ZZ-RF-D-Z-5810
FS1018-AGL-ZZ-RF-D-Z-5811 | Roof Level Plantroom Sheet 2 | P01 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-AGL-ZZ-RF-D-Z-5811 Roof Level Plantroom Sheet 2 | FS1018-AGL-ZZ-RF-D-Z-5811
FS1018-AGL-ZZ-RF-D-Z-5811 | Roof Level Plantroom Sheet 2 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-RF-D-Z-5811 Roof Level Plantroom Sheet 2 | FS1018-AGL-ZZ-RF-D-Z-5811
FS1018-AGL-ZZ-RF-D-Z-5812 | Roof Level Plantroom Sheet 3 | P01 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-AGL-ZZ-RF-D-Z-5812 Roof Level Plantroom Sheet 3 | FS1018-AGL-ZZ-RF-D-Z-5812
FS1018-AGL-ZZ-RF-D-Z-5812 | Roof Level Plantroom Sheet 3 | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-RF-D-Z-5812 Roof Level Plantroom Sheet 3 | FS1018-AGL-ZZ-RF-D-Z-5812
FS1018-AGL-ZZ-RF-D-Z-6010 | Roof Level Builderswork Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-RF-D-Z-6010 Roof Level Builderswork Sheet 1 | FS1018-AGL-ZZ-RF-D-Z-6010
FS1018-AGL-ZZ-RF-D-Z-6011 | Roof Level Builderswork Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-RF-D-Z-6011 Roof Level Builderswork Sheet 2 | FS1018-AGL-ZZ-RF-D-Z-6011
FS1018-AGL-ZZ-RF-D-Z-6012 | Roof Level Builderswork Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-RF-D-Z-6012 Roof Level Builderswork Sheet 3 | FS1018-AGL-ZZ-RF-D-Z-6012
FS1018-AGL-ZZ-RF-D-Z-6101 | Roof Level Mechanical and Electrical Strategy | P01 | Completed | 2023-09-06 | Multiple Discipline Review | B3 - Partially Accepted with Comments | 2023-10-06 | Label for PV is incorrect. Not clear what initial proposed solar PV array layout looks like. Needs further detail to show this and confirm how it is accommodated with green roof. | FALSE | FS1018-AGL-ZZ-RF-D-Z-6101 Roof Level Mechanical and Electrical Strategy | FS1018-AGL-ZZ-RF-D-Z-6101
FS1018-AGL-ZZ-XX-D-E-6802 | External Access Control Strategy | P01 | Completed | 2023-09-06 | Electrical Review | A3 - Accepted | 2023-10-02 |  | FALSE | FS1018-AGL-ZZ-XX-D-E-6802 External Access Control Strategy | FS1018-AGL-ZZ-XX-D-E-6802
FS1018-AGL-ZZ-XX-D-E-9001 | External Lighting | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Please confirm if external emergency lighting is in place along every exit route of the building in line with BS5266-2016 | FALSE | FS1018-AGL-ZZ-XX-D-E-9001 External Lighting | FS1018-AGL-ZZ-XX-D-E-9001
FS1018-AGL-ZZ-XX-D-E-9001 | External Lighting | P02 | Completed | 2024-08-29 | Mechanical Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-AGL-ZZ-XX-D-E-9001 External Lighting | FS1018-AGL-ZZ-XX-D-E-9001
FS1018-AGL-ZZ-XX-D-E-9001 | External Lighting | P04 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-D-E-9001 External Lighting | FS1018-AGL-ZZ-XX-D-E-9001
FS1018-AGL-ZZ-XX-D-E-9002 | External Lighting Lux Levels | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Please confirm if minimum 10 lux level has been achieved on car parks and pathways. Please confirm if external emergency lighting is in place along every exit route of the building in line with BS5266-2016 | FALSE | FS1018-AGL-ZZ-XX-D-E-9002 External Lighting Lux Levels | FS1018-AGL-ZZ-XX-D-E-9002
FS1018-AGL-ZZ-XX-D-E-9002 | External Lighting Lux Levels | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-XX-D-E-9002 External Lighting Lux Levels | FS1018-AGL-ZZ-XX-D-E-9002
FS1018-AGL-ZZ-XX-D-E-9511 | DNO Services Drawing and Proposal | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-D-E-9511 DNO Services Drawing and Proposal | FS1018-AGL-ZZ-XX-D-E-9511
FS1018-AGL-ZZ-XX-D-Z-5810 | External Compound | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-D-Z-5810 External Compound | FS1018-AGL-ZZ-XX-D-Z-5810
FS1018-AGL-ZZ-XX-D-Z-9510 | External Services | P02 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-AGL-ZZ-XX-D-Z-9510 External Services | FS1018-AGL-ZZ-XX-D-Z-9510
FS1018-AGL-ZZ-XX-D-Z-9510 | External Services | P03 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-D-Z-9510 External Services | FS1018-AGL-ZZ-XX-D-Z-9510
FS1018-AGL-ZZ-XX-L-E-0001 | Proposed Manufacturers Electrical Schedule | P01 | Completed | 2023-09-06 | Electrical Review | A3 - Accepted | 2023-10-02 |  | FALSE | FS1018-AGL-ZZ-XX-L-E-0001 Proposed Manufacturers Electrical Schedule | FS1018-AGL-ZZ-XX-L-E-0001
FS1018-AGL-ZZ-XX-L-E-0001 | Proposed Manufacturers Electrical Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-E-0001 Proposed Manufacturers Electrical Schedule | FS1018-AGL-ZZ-XX-L-E-0001
FS1018-AGL-ZZ-XX-L-E-0002 | Cable Calculation & Schedule Report | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-E-0002 Cable Calculation & Schedule Report | FS1018-AGL-ZZ-XX-L-E-0002
FS1018-AGL-ZZ-XX-L-E-0003 | Containment Calculations | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-E-0003 Containment Calculations | FS1018-AGL-ZZ-XX-L-E-0003
FS1018-AGL-ZZ-XX-L-E-0004 | Lighting Calculations | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-E-0004 Lighting Calculations | FS1018-AGL-ZZ-XX-L-E-0004
FS1018-AGL-ZZ-XX-L-E-0005 | Exit Signage Calculation | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-E-0005 Exit Signage Calculation | FS1018-AGL-ZZ-XX-L-E-0005
FS1018-AGL-ZZ-XX-L-E-9602 | Luminaire Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-E-9602 Luminaire Schedule | FS1018-AGL-ZZ-XX-L-E-9602
FS1018-AGL-ZZ-XX-L-M-0001 | Proposed Manufacturers Mechanical Schedule | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Any electrostatic precipitator for kitchen extract fan? | FALSE | FS1018-AGL-ZZ-XX-L-M-0001 Proposed Manufacturers Mechanical Schedule | FS1018-AGL-ZZ-XX-L-M-0001
FS1018-AGL-ZZ-XX-L-M-0002 | Peak Water Demand BS EN 806 | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Peak water demand to be reviewed upon final layouts and finalisation of fixtures and fittings. (i.e showers area) | FALSE | FS1018-AGL-ZZ-XX-L-M-0002 Peak Water Demand BS EN 806 | FS1018-AGL-ZZ-XX-L-M-0002
FS1018-AGL-ZZ-XX-L-M-0003 | Domestic Water Services Calculations | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-0003 Domestic Water Services Calculations | FS1018-AGL-ZZ-XX-L-M-0003
FS1018-AGL-ZZ-XX-L-M-0004 | Ventilation Calculations | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-0004 Ventilation Calculations | FS1018-AGL-ZZ-XX-L-M-0004
FS1018-AGL-ZZ-XX-L-M-0005 | Gas Calculations | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-0005 Gas Calculations | FS1018-AGL-ZZ-XX-L-M-0005
FS1018-AGL-ZZ-XX-L-M-0006 | Above Ground Drainage Calculations | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-0006 Above Ground Drainage Calculations | FS1018-AGL-ZZ-XX-L-M-0006
FS1018-AGL-ZZ-XX-L-M-0007 | Heating Calculations | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-0007 Heating Calculations | FS1018-AGL-ZZ-XX-L-M-0007
FS1018-AGL-ZZ-XX-L-M-0008 | Heat Source Calculations | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-0008 Heat Source Calculations | FS1018-AGL-ZZ-XX-L-M-0008
FS1018-AGL-ZZ-XX-L-M-9604 | Heat Pump Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9604 Heat Pump Schedule | FS1018-AGL-ZZ-XX-L-M-9604
FS1018-AGL-ZZ-XX-L-M-9605 | Buffer Vessel Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9605 Buffer Vessel Schedule | FS1018-AGL-ZZ-XX-L-M-9605
FS1018-AGL-ZZ-XX-L-M-9607 | Plate Heat Exchanger Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9607 Plate Heat Exchanger Schedule | FS1018-AGL-ZZ-XX-L-M-9607
FS1018-AGL-ZZ-XX-L-M-9608 | Water Heater Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9608 Water Heater Schedule | FS1018-AGL-ZZ-XX-L-M-9608
FS1018-AGL-ZZ-XX-L-M-9609 | Air & Dirt Separator Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9609 Air & Dirt Separator Schedule | FS1018-AGL-ZZ-XX-L-M-9609
FS1018-AGL-ZZ-XX-L-M-9610 | Dosing Pot Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9610 Dosing Pot Schedule | FS1018-AGL-ZZ-XX-L-M-9610
FS1018-AGL-ZZ-XX-L-M-9613 | Water Filter Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9613 Water Filter Schedule | FS1018-AGL-ZZ-XX-L-M-9613
FS1018-AGL-ZZ-XX-L-M-9614 | Water Softener Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9614 Water Softener Schedule | FS1018-AGL-ZZ-XX-L-M-9614
FS1018-AGL-ZZ-XX-L-M-9617 | Leak Detection Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9617 Leak Detection Schedule | FS1018-AGL-ZZ-XX-L-M-9617
FS1018-AGL-ZZ-XX-L-M-9619 | Gas Meter Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9619 Gas Meter Schedule | FS1018-AGL-ZZ-XX-L-M-9619
FS1018-AGL-ZZ-XX-L-M-9620 | Water Meter Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9620 Water Meter Schedule | FS1018-AGL-ZZ-XX-L-M-9620
FS1018-AGL-ZZ-XX-L-M-9621 | Heat Meter Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9621 Heat Meter Schedule | FS1018-AGL-ZZ-XX-L-M-9621
FS1018-AGL-ZZ-XX-L-M-9623 | Gas Solenoid Valve Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9623 Gas Solenoid Valve Schedule | FS1018-AGL-ZZ-XX-L-M-9623
FS1018-AGL-ZZ-XX-L-M-9624 | Gas Detection & Proving Panel Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9624 Gas Detection & Proving Panel Schedule | FS1018-AGL-ZZ-XX-L-M-9624
FS1018-AGL-ZZ-XX-L-M-9625 | Pressurisation Unit Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9625 Pressurisation Unit Schedule | FS1018-AGL-ZZ-XX-L-M-9625
FS1018-AGL-ZZ-XX-L-M-9627 | Storage Tank Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9627 Storage Tank Schedule | FS1018-AGL-ZZ-XX-L-M-9627
FS1018-AGL-ZZ-XX-L-M-9628 | Booster Set Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9628 Booster Set Schedule | FS1018-AGL-ZZ-XX-L-M-9628
FS1018-AGL-ZZ-XX-L-M-9630 | Pump Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9630 Pump Schedule | FS1018-AGL-ZZ-XX-L-M-9630
FS1018-AGL-ZZ-XX-L-M-9634 | Local Water Heater Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9634 Local Water Heater Schedule | FS1018-AGL-ZZ-XX-L-M-9634
FS1018-AGL-ZZ-XX-L-M-9637 | Radiator Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9637 Radiator Schedule | FS1018-AGL-ZZ-XX-L-M-9637
FS1018-AGL-ZZ-XX-L-M-9641 | Underfloor Heating Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9641 Underfloor Heating Schedule | FS1018-AGL-ZZ-XX-L-M-9641
FS1018-AGL-ZZ-XX-L-M-9642 | Underfloor Heating Manifold Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9642 Underfloor Heating Manifold Schedule | FS1018-AGL-ZZ-XX-L-M-9642
FS1018-AGL-ZZ-XX-L-M-9644 | Overdoor Heater Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9644 Overdoor Heater Schedule | FS1018-AGL-ZZ-XX-L-M-9644
FS1018-AGL-ZZ-XX-L-M-9647 | Electric Heater Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9647 Electric Heater Schedule | FS1018-AGL-ZZ-XX-L-M-9647
FS1018-AGL-ZZ-XX-L-M-9649 | Fan Convector Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9649 Fan Convector Schedule | FS1018-AGL-ZZ-XX-L-M-9649
FS1018-AGL-ZZ-XX-L-M-9652 | Air Handling Unit Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9652 Air Handling Unit Schedule | FS1018-AGL-ZZ-XX-L-M-9652
FS1018-AGL-ZZ-XX-L-M-9653 | Heat Recovery Unit Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9653 Heat Recovery Unit Schedule | FS1018-AGL-ZZ-XX-L-M-9653
FS1018-AGL-ZZ-XX-L-M-9654 | Hybrid Ventilation Unit Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9654 Hybrid Ventilation Unit Schedule | FS1018-AGL-ZZ-XX-L-M-9654
FS1018-AGL-ZZ-XX-L-M-9655 | Fan Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9655 Fan Schedule | FS1018-AGL-ZZ-XX-L-M-9655
FS1018-AGL-ZZ-XX-L-M-9658 | Louvre Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9658 Louvre Schedule | FS1018-AGL-ZZ-XX-L-M-9658
FS1018-AGL-ZZ-XX-L-M-9659 | Supply Diffuser Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9659 Supply Diffuser Schedule | FS1018-AGL-ZZ-XX-L-M-9659
FS1018-AGL-ZZ-XX-L-M-9660 | Extract Grille Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9660 Extract Grille Schedule | FS1018-AGL-ZZ-XX-L-M-9660
FS1018-AGL-ZZ-XX-L-M-9661 | Attenuator Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9661 Attenuator Schedule | FS1018-AGL-ZZ-XX-L-M-9661
FS1018-AGL-ZZ-XX-L-M-9662 | Transfer Grille Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9662 Transfer Grille Schedule | FS1018-AGL-ZZ-XX-L-M-9662
FS1018-AGL-ZZ-XX-L-M-9671 | Heating Coil Schedule (LTHW) | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9671 Heating Coil Schedule (LTHW) | FS1018-AGL-ZZ-XX-L-M-9671
FS1018-AGL-ZZ-XX-L-M-9675 | Smoke-activated Fire Damper Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9675 Smoke-activated Fire Damper Schedule | FS1018-AGL-ZZ-XX-L-M-9675
FS1018-AGL-ZZ-XX-L-M-9678 | Passive Stack Ventilator Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9678 Passive Stack Ventilator Schedule | FS1018-AGL-ZZ-XX-L-M-9678
FS1018-AGL-ZZ-XX-L-M-9681 | DX Indoor Unit Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9681 DX Indoor Unit Schedule | FS1018-AGL-ZZ-XX-L-M-9681
FS1018-AGL-ZZ-XX-L-M-9682 | DX Outdoor Unit Schedule | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-M-9682 DX Outdoor Unit Schedule | FS1018-AGL-ZZ-XX-L-M-9682
FS1018-AGL-ZZ-XX-L-Z-0001 | Designers MEP Risk Assessment | P01 | Completed | 2023-09-06 | CDM Review | C - Rejected | 2023-09-25 | KB Comments:  have these been provided to the Principal Designer for comment?  Have the Designers been provided with Pre-Construction Information to inform their Design and DRA’s?  Is the Principal Designer satisfied that the Designers have used the general principles of prevention to eliminate/reduce risk in their design?  Confusing as comments in the “Action already taken during design process” seem to apply to future actions required by others e.g contractor.  How has risk been eliminated/reduced through Stage 3 design?  Confirm/Identify appropriate information from the design that the Principal Designer will need to include in the H&S file for completion. | FALSE | FS1018-AGL-ZZ-XX-L-Z-0001 Designers MEP Risk Assessment | FS1018-AGL-ZZ-XX-L-Z-0001
FS1018-AGL-ZZ-XX-L-Z-0001 | Designers MEP Risk Assessment | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-XX-L-Z-0001 Designers MEP Risk Assessment | FS1018-AGL-ZZ-XX-L-Z-0001
FS1018-AGL-ZZ-XX-L-Z-0002 | Derogation Schedule | P01 | Completed | 2023-09-06 | Multiple Discipline Review | C - Rejected | 2023-09-25 | We need one derogation schedule to pick up all derogations across the project. Could this please be resubmitted as a Henry Brothers document, incorporating other disciplines? | FALSE | FS1018-AGL-ZZ-XX-L-Z-0002 Derogation Schedule | FS1018-AGL-ZZ-XX-L-Z-0002
FS1018-AGL-ZZ-XX-L-Z-0003 | M and E Design Development Report | P01 | Completed | 2023-09-08 | Multiple Discipline Review | B3 - Partially Accepted with Comments | 2023-10-06 | Mechanical: Any design development on kitchen ventilation requirement and control strategy? | FALSE | FS1018-AGL-ZZ-XX-L-Z-0003 M and E Design Development Report | FS1018-AGL-ZZ-XX-L-Z-0003
FS1018-AGL-ZZ-XX-L-Z-0004 | Heat Loss Calculations | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-L-Z-0004 Heat Loss Calculations | FS1018-AGL-ZZ-XX-L-Z-0004
FS1018-AGL-ZZ-XX-T-E-0001 | Electrical Specification | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-T-E-0001 Electrical Specification | FS1018-AGL-ZZ-XX-T-E-0001
FS1018-AGL-ZZ-XX-T-E-0003 | Electrical Maximum Demand | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Please confirm that the total power requirement for electric vehicle charging corresponds to the number of parking bays available on site. Check SoA for GIFA. | FALSE | FS1018-AGL-ZZ-XX-T-E-0003 Electrical Maximum Demand | FS1018-AGL-ZZ-XX-T-E-0003
FS1018-AGL-ZZ-XX-T-E-0003 | Electrical Maximum Demand | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-XX-T-E-0003 Electrical Maximum Demand | FS1018-AGL-ZZ-XX-T-E-0003
FS1018-AGL-ZZ-XX-T-M-0001 | Mechanical Specification | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-T-M-0001 Mechanical Specification | FS1018-AGL-ZZ-XX-T-M-0001
FS1018-AGL-ZZ-XX-T-Z-0001 | Gateway M and E Proposal Report | P01 | Completed | 2023-09-06 | Multiple Discipline Review | B3 - Partially Accepted with Comments | 2023-10-06 | Gas strategy includes both LPG tank and mains gas as options to supply for science teaching. This is inconsistent with FS1018-AGL-ZZ-00-D-M-5401-Level 00 Gas Strategy-S5-P01 and stated requirement for LPG tank. It is consistent with FS1018-AGL-ZZ-ZZ-G-M-5401-Gas Strategy Schematic-S5-P01. Should have agreed position on this by this stage of design. | FALSE | FS1018-AGL-ZZ-XX-T-Z-0001 Gateway M and E Proposal Report | FS1018-AGL-ZZ-XX-T-Z-0001
FS1018-AGL-ZZ-XX-T-Z-0002 | M and E Plant Access Maintenance and Replacement Strategy | P01 | Completed | 2023-09-06 | Multiple Discipline Review | B3 - Partially Accepted with Comments | 2023-10-06 | '- delivery path for large equipment replacement like ASHP and AHU should be provide. - Please confirm the access, maintenance, and replacement strategy for lighting and smoke detection systems in the assembly halls and sports hall. | FALSE | FS1018-AGL-ZZ-XX-T-Z-0002 M and E Plant Access Maintenance and Replacement Strategy | FS1018-AGL-ZZ-XX-T-Z-0002
FS1018-AGL-ZZ-XX-T-Z-0002 | Plant Access Maintenance And Replacement Strategy | P02 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | TRUE | FS1018-AGL-ZZ-XX-T-Z-0002 Plant Access Maintenance And Replacement Strategy | FS1018-AGL-ZZ-XX-T-Z-0002
FS1018-AGL-ZZ-XX-T-Z-0003 | Thermal Modelling and Compliance Report | P01 | Completed | 2023-09-06 | Multiple Discipline Review | B3 - Partially Accepted with Comments | 2023-10-06 | Need to remove reference to Newcastle City Council in Section 6. This is not the relevant planning authority. Check any additional planning guidance as issued by the relevant authority. | FALSE | FS1018-AGL-ZZ-XX-T-Z-0003 Thermal Modelling and Compliance Report | FS1018-AGL-ZZ-XX-T-Z-0003
FS1018-AGL-ZZ-XX-T-Z-0003 | Thermal Modelling and Compliance Report | P02 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-AGL-ZZ-XX-T-Z-0003 Thermal Modelling and Compliance Report | FS1018-AGL-ZZ-XX-T-Z-0003
FS1018-AGL-ZZ-XX-T-Z-0006 | NBS Project Description | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-T-Z-0006 NBS Project Description | FS1018-AGL-ZZ-XX-T-Z-0006
FS1018-AGL-ZZ-XX-T-Z-0007 | Thermal Modelling, Compliance & Sustainability Report | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-XX-T-Z-0007 Thermal Modelling, Compliance & Sustainability Report | FS1018-AGL-ZZ-XX-T-Z-0007
FS1018-AGL-ZZ-ZZ-D-E-7205 | Typical Teachers Wall Detail | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Please confirm if there will be any light switch controls in the teaching wall area. | FALSE | FS1018-AGL-ZZ-ZZ-D-E-7205 Typical Teachers Wall Detail | FS1018-AGL-ZZ-ZZ-D-E-7205
FS1018-AGL-ZZ-ZZ-D-E-9001 | Lightning Protection | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-D-E-9001 Lightning Protection | FS1018-AGL-ZZ-ZZ-D-E-9001
FS1018-AGL-ZZ-ZZ-D-Z-5002 | Typical Riser and Corridor Details | P01 | Completed | 2023-09-08 | Multiple Discipline Review | B3 - Partially Accepted with Comments | 2023-10-06 | All control valve is missing. | FALSE | FS1018-AGL-ZZ-ZZ-D-Z-5002 Typical Riser and Corridor Details | FS1018-AGL-ZZ-ZZ-D-Z-5002
FS1018-AGL-ZZ-ZZ-D-Z-5801 | Level 00 Plantroom and Server Room Strategy | P01 | Completed | 2023-09-06 | Multiple Discipline Review | A3 - Accepted | 2023-10-06 |  | FALSE | FS1018-AGL-ZZ-ZZ-D-Z-5801 Level 00 Plantroom and Server Room Strategy | FS1018-AGL-ZZ-ZZ-D-Z-5801
FS1018-AGL-ZZ-ZZ-D-Z-6115 | Server and Hub Room | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-D-Z-6115 Server and Hub Room | FS1018-AGL-ZZ-ZZ-D-Z-6115
FS1018-AGL-ZZ-ZZ-D-Z-7201 | Typical Classroom Strategy | P01 | Completed | 2023-09-08 | Multiple Discipline Review | A3 - Accepted | 2023-10-06 |  | FALSE | FS1018-AGL-ZZ-ZZ-D-Z-7201 Typical Classroom Strategy | FS1018-AGL-ZZ-ZZ-D-Z-7201
FS1018-AGL-ZZ-ZZ-D-Z-7202 | Typical Science Room Strategy | P01 | Completed | 2023-09-08 | Multiple Discipline Review | A3 - Accepted | 2023-10-06 |  | FALSE | FS1018-AGL-ZZ-ZZ-D-Z-7202 Typical Science Room Strategy | FS1018-AGL-ZZ-ZZ-D-Z-7202
FS1018-AGL-ZZ-ZZ-D-Z-7203 | Typical ICT Classroom Strategy | P01 | Completed | 2023-09-08 | Multiple Discipline Review | A3 - Accepted | 2023-10-06 |  | FALSE | FS1018-AGL-ZZ-ZZ-D-Z-7203 Typical ICT Classroom Strategy | FS1018-AGL-ZZ-ZZ-D-Z-7203
FS1018-AGL-ZZ-ZZ-D-Z-7204 | Typical DT Classroom Strategy | P01 | Completed | 2023-09-08 | Multiple Discipline Review | A3 - Accepted | 2023-10-06 |  | FALSE | FS1018-AGL-ZZ-ZZ-D-Z-7204 Typical DT Classroom Strategy | FS1018-AGL-ZZ-ZZ-D-Z-7204
FS1018-AGL-ZZ-ZZ-D-Z-9610 | Typical D&T Classroom | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-D-Z-9610 Typical D&T Classroom | FS1018-AGL-ZZ-ZZ-D-Z-9610
FS1018-AGL-ZZ-ZZ-D-Z-9611 | Typical Food Room | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-D-Z-9611 Typical Food Room | FS1018-AGL-ZZ-ZZ-D-Z-9611
FS1018-AGL-ZZ-ZZ-D-Z-9612 | Typical ICT Classroom | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-D-Z-9612 Typical ICT Classroom | FS1018-AGL-ZZ-ZZ-D-Z-9612
FS1018-AGL-ZZ-ZZ-D-Z-9613 | Typical Riser | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-D-Z-9613 Typical Riser | FS1018-AGL-ZZ-ZZ-D-Z-9613
FS1018-AGL-ZZ-ZZ-D-Z-9614 | Typical Science Room | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-D-Z-9614 Typical Science Room | FS1018-AGL-ZZ-ZZ-D-Z-9614
FS1018-AGL-ZZ-ZZ-G-E-6001 | LV Schematic | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Confirm emergency fire man PV isolation switch location. Lift supply is not shown in the LV schematic. Please confirm. | FALSE | FS1018-AGL-ZZ-ZZ-G-E-6001 LV Schematic | FS1018-AGL-ZZ-ZZ-G-E-6001
FS1018-AGL-ZZ-ZZ-G-E-6010 | LV Schematic Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-E-6010 LV Schematic Sheet 1 | FS1018-AGL-ZZ-ZZ-G-E-6010
FS1018-AGL-ZZ-ZZ-G-E-6011 | LV Schematic Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-E-6011 LV Schematic Sheet 2 | FS1018-AGL-ZZ-ZZ-G-E-6011
FS1018-AGL-ZZ-ZZ-G-E-6801 | Fire Alarm Strategy Schematic | P01 | Completed | 2023-09-06 | Electrical Review | B3 - Partially Accepted with Comments | 2023-10-02 | Confirm if PV isolation is controlled through the main fire alarm panel. Confirm the location of fire man's PV isolation switches Define and segregate the areas with Smoke/heat/sounder/detector/beacon locations. | FALSE | FS1018-AGL-ZZ-ZZ-G-E-6801 Fire Alarm Strategy Schematic | FS1018-AGL-ZZ-ZZ-G-E-6801
FS1018-AGL-ZZ-ZZ-G-E-6811 | Fire Alarm Schematic | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-E-6811 Fire Alarm Schematic | FS1018-AGL-ZZ-ZZ-G-E-6811
FS1018-AGL-ZZ-ZZ-G-M-5001 | Controls Strategy Schematic | P01 | Completed | 2023-09-06 | Mechanical Review | A3 - Accepted | 2023-10-06 |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5001 Controls Strategy Schematic | FS1018-AGL-ZZ-ZZ-G-M-5001
FS1018-AGL-ZZ-ZZ-G-M-5010 | Controls Schematic | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5010 Controls Schematic | FS1018-AGL-ZZ-ZZ-G-M-5010
FS1018-AGL-ZZ-ZZ-G-M-5210 | Above Ground Drainage Schematic Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5210 Above Ground Drainage Schematic Sheet 1 | FS1018-AGL-ZZ-ZZ-G-M-5210
FS1018-AGL-ZZ-ZZ-G-M-5211 | Above Ground Drainage Schematic Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5211 Above Ground Drainage Schematic Sheet 2 | FS1018-AGL-ZZ-ZZ-G-M-5211
FS1018-AGL-ZZ-ZZ-G-M-5310 | Domestic Water Services Schematic | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5310 Domestic Water Services Schematic | FS1018-AGL-ZZ-ZZ-G-M-5310
FS1018-AGL-ZZ-ZZ-G-M-5401 | Gas Strategy Schematic | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | See comments against Gateway M and E Proposal Report | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5401 Gas Strategy Schematic | FS1018-AGL-ZZ-ZZ-G-M-5401
FS1018-AGL-ZZ-ZZ-G-M-5410 | Gas Schematic | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5410 Gas Schematic | FS1018-AGL-ZZ-ZZ-G-M-5410
FS1018-AGL-ZZ-ZZ-G-M-5610 | Heating & Cooling Schematic Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5610 Heating & Cooling Schematic Sheet 1 | FS1018-AGL-ZZ-ZZ-G-M-5610
FS1018-AGL-ZZ-ZZ-G-M-5611 | Heating & Cooling Schematic Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5611 Heating & Cooling Schematic Sheet 2 | FS1018-AGL-ZZ-ZZ-G-M-5611
FS1018-AGL-ZZ-ZZ-G-M-5612 | Heating & Cooling Schematic Sheet 3 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5612 Heating & Cooling Schematic Sheet 3 | FS1018-AGL-ZZ-ZZ-G-M-5612
FS1018-AGL-ZZ-ZZ-G-M-5613 | Heating & Cooling Schematic Sheet 4 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5613 Heating & Cooling Schematic Sheet 4 | FS1018-AGL-ZZ-ZZ-G-M-5613
FS1018-AGL-ZZ-ZZ-G-M-5701 | Ventilation Strategy Schematic | P01 | Completed | 2023-09-06 | Mechanical Review | A3 - Accepted | 2023-10-06 |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5701 Ventilation Strategy Schematic | FS1018-AGL-ZZ-ZZ-G-M-5701
FS1018-AGL-ZZ-ZZ-G-M-5710 | Ventilation Schematic Sheet 1 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5710 Ventilation Schematic Sheet 1 | FS1018-AGL-ZZ-ZZ-G-M-5710
FS1018-AGL-ZZ-ZZ-G-M-5711 | Ventilation Schematic Sheet 2 | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5711 Ventilation Schematic Sheet 2 | FS1018-AGL-ZZ-ZZ-G-M-5711
FS1018-AGL-ZZ-ZZ-G-M-5801 | Heating and Domestic Water Plant Strategy Schematic | P01 | Completed | 2023-09-06 | Mechanical Review | B3 - Partially Accepted with Comments | 2023-10-06 | Please update with relevant main sizing of plant (cold water storage tank / hot water heaters / CAT 5 / Boosted water pump) | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5801 Heating and Domestic Water Plant Strategy Schematic | FS1018-AGL-ZZ-ZZ-G-M-5801
FS1018-AGL-ZZ-ZZ-G-M-5812 | Plantroom Schematic | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-G-M-5812 Plantroom Schematic | FS1018-AGL-ZZ-ZZ-G-M-5812
FS1018-AGL-ZZ-ZZ-G-M-9600 | PV Proposal | P01 | Completed | 2023-10-18 | Multiple Discipline Review | C - Rejected | 2023-10-18 | Please confirm the split between roof mounted and canopy mounted panels. The canopies proposed do not appear to comply with the DfE specification. | FALSE | FS1018-AGL-ZZ-ZZ-G-M-9600 PV Proposal | FS1018-AGL-ZZ-ZZ-G-M-9600
FS1018-AGL-ZZ-ZZ-M-Z-0001 | MEPModel Revit | P01 | Completed | 2023-09-06 | Multiple Discipline Review | C - Rejected | 2023-09-25 | Lack of model geometry. Would have expected to see ME and PH major routes, Plumbing fixtures, Electrical fixtures. Only cable tray primary routes and plant room equipment present in model. Empty levels present in the model and incorrect level assignments. | FALSE | FS1018-AGL-ZZ-ZZ-M-Z-0001 MEPModel Revit | FS1018-AGL-ZZ-ZZ-M-Z-0001
FS1018-AGL-ZZ-ZZ-M-Z-0001 | MEPModel Revit | P02 | Completed | 2024-08-29 | Mechanical Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-AGL-ZZ-ZZ-M-Z-0001 MEPModel Revit | FS1018-AGL-ZZ-ZZ-M-Z-0001
FS1018-AGL-ZZ-ZZ-M-Z-0001 | MEP Model Revit | P15 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-M-Z-0001 MEP Model Revit | FS1018-AGL-ZZ-ZZ-M-Z-0001
FS1018-AGL-ZZ-ZZ-M-Z-0002 | MEPModel IFC | P01 | Completed | 2023-09-06 | Multiple Discipline Review | C - Rejected | 2023-09-25 | Mechanical equipment should be assigned appropriate IFC Type and not remain generic Building Element Proxy type. 133 elements have USERDEFINED or NOTDEFINED predefined type. Empty levels present in the model and incorrect level assignments. | FALSE | FS1018-AGL-ZZ-ZZ-M-Z-0002 MEPModel IFC | FS1018-AGL-ZZ-ZZ-M-Z-0002
FS1018-AGL-ZZ-ZZ-M-Z-0002 | MEP Model IFC | P03 | Completed | 2024-08-28 | Mechanical Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-AGL-ZZ-ZZ-M-Z-0002 MEP Model IFC | FS1018-AGL-ZZ-ZZ-M-Z-0002
FS1018-AGL-ZZ-ZZ-M-Z-0002 | MEP Model IFC | P15 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-M-Z-0002 MEP Model IFC | FS1018-AGL-ZZ-ZZ-M-Z-0002
FS1018-AGL-ZZ-ZZ-M-Z-0003 | MEPModel NWC | P01 | Completed | 2023-09-06 | Multiple Discipline Review | C - Rejected | 2023-09-25 | Lack of model geometry. Would have expected to see ME and PH major routes, Plumbing fixtures, Electrical fixtures. Only cable tray primary routes and plant room equipment present in model. Empty levels present in the model and incorrect level assignments. | FALSE | FS1018-AGL-ZZ-ZZ-M-Z-0003 MEPModel NWC | FS1018-AGL-ZZ-ZZ-M-Z-0003
FS1018-AGL-ZZ-ZZ-M-Z-0003 | MEP Model NWC | P03 | Completed | 2024-08-28 | Mechanical Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-AGL-ZZ-ZZ-M-Z-0003 MEP Model NWC | FS1018-AGL-ZZ-ZZ-M-Z-0003
FS1018-AGL-ZZ-ZZ-M-Z-0003 | MEP Model NWC | P15 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-AGL-ZZ-ZZ-M-Z-0003 MEP Model NWC | FS1018-AGL-ZZ-ZZ-M-Z-0003
FS1018-AMT-XX-XX-L-O-0001 | Preliminary Ecological Appraisal | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-25 |  | FALSE | FS1018-AMT-XX-XX-L-O-0001 Preliminary Ecological Appraisal | FS1018-AMT-XX-XX-L-O-0001
FS1018-AMT-XX-XX-L-O-0002 | Tree Survey and Constraints Report | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-25 |  | FALSE | FS1018-AMT-XX-XX-L-O-0002 Tree Survey and Constraints Report | FS1018-AMT-XX-XX-L-O-0002
FS1018-CPM-01-XX-T-A-0005 | Teaching Block Finishes | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | Superseded by P02 | FALSE | FS1018-CPM-01-XX-T-A-0005 Teaching Block Finishes | FS1018-CPM-01-XX-T-A-0005
FS1018-CPM-01-XX-T-A-0010 | Outline Specification | P02 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | Superceded by P03 | TRUE | FS1018-CPM-01-XX-T-A-0010 Outline Specification | FS1018-CPM-01-XX-T-A-0010
FS1018-CPM-01-ZZ-L-A-0000 | Building Model COBie | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-26 | This information should be incorporated into the Asset Register, in this case this was not done because the IFC was not provided to Majenta. COBie sheet populated with Sheets required for Stage 3 . Majority of Facility COBie fields are not compliant with Standardised Values set out in the Project Information Standards. Nor Space name field. External spaces missing from COBie. Zone Sheet not compliant to COBie standard, Name field must be unique and grouped according to the Zones in the PIS. Contact sheet has supplier that is not referenced in other sheets. | FALSE | FS1018-CPM-01-ZZ-L-A-0000 Building Model COBie | FS1018-CPM-01-ZZ-L-A-0000
FS1018-CPM-XX-XX-L-A-0001 | Schedule Of Accommodation | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | Refer to comments in TA notes section on SoA. Note that proposed GIFA is 5009 sq m ie 179 sqm more than the SoA at ITT of 4830 sqm. Note Thermal modelling currently based on GIFA of 4973 sq m | FALSE | FS1018-CPM-XX-XX-L-A-0001 Schedule Of Accommodation | FS1018-CPM-XX-XX-L-A-0001
FS1018-CPM-XX-XX-L-A-0001 | Schedule Of Accommodation | P04 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-XX-XX-L-A-0001 Schedule Of Accommodation | FS1018-CPM-XX-XX-L-A-0001
FS1018-CPM-XX-XX-L-A-0001 | Schedule Of Accommodation | P06 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-XX-XX-L-A-0001 Schedule Of Accommodation | FS1018-CPM-XX-XX-L-A-0001
FS1018-CPM-XX-XX-T-A-0005 | Teaching Block Finishes | P01 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-XX-XX-T-A-0005 Teaching Block Finishes | FS1018-CPM-XX-XX-T-A-0005
FS1018-CPM-XX-XX-T-A-0005 | Teaching Block Finishes | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-XX-XX-T-A-0005 Teaching Block Finishes | FS1018-CPM-XX-XX-T-A-0005
FS1018-CPM-XX-XX-T-A-0010 | OutlineSpecification | P03 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | 1.0 Please state at the top how proposals satisfy the overall ER's with respect to Minimum Life Expectancy, U-value requirements etc; 1.1 Please also describe recessed and hit & miss condition. Do these also achieve stated required u-values? ; 1.2 Fibre cement rainscreen described as 'Mechanical fixing with colour-matched screw heads; ' yet drawing describes secret fix' - which is it?; 1.3 does not mentioned top hung opening lights in hall and whether they are automated ; 3.1 BIO-SOLAR ROOF ARRANGEMENT ON HOT MELT ROOFING SYSTEM - ensure proposed roof buildup satisifies ER's TA 2C: 3.2.13 The system shall incorporate, as a minimum, the following (for a flat roof green roof build up): a lightweight growing material tested to BS8616, a filtration layer, drainage board for water storage, a protection layer to the top surface of the underlying waterproofing membrane comprising a bituminous/Hot Melt/Single Ply or Cold Applied liquid waterproofing layer to top of insulation. [Ss_45_40_47_28]; 3.5 MAINTENANCE ACCESS EQUIPMENT: - galvanised stairs described - see comments elsewhere, galvanised finishes not acceptable, see TA 2C 3.5.2 g) Galvanised mild steel balustrades are permitted in non-visually obvious situations [PM_80_60_50] ; 3.6 SYPHONIC RAINWATER DRAINAGE SYSTEM: see comments elsewhere, please draw this for our review; 4.1 FAIR-FACED BLOCKWORK WALLS: identified 'to plant rooms, lift shaft and risers' - Is Blockwork in lift shafts typical? Also, how does it satisfy fire rating requirements?; 4.0 INTERNAL PARTITION WALLS AND FINISHES - please include additional wall linings required to meet acoustic requiements; 7.1 ENCLOSED STAIRCASES: and 7.3 BALUSTRADING TO STACK VENTILATION VOIDS - how does structural glass balustrading satisfy BWT's requirements for privacy?; What are the internal finishes on the lanterns? ; 10.3 Furniture: Do proposals satisfy requirements of ER's?; 10.4 Fencing: Discrepancies between what is proposed here and proposed on FS1018-ONE-XX-ZZ-D-L-0009-Access Security Strategy-S5-P04; 10.5 Soft Landscaping: How do these satisfy BNG requirements? | FALSE | FS1018-CPM-XX-XX-T-A-0010 OutlineSpecification | FS1018-CPM-XX-XX-T-A-0010
FS1018-CPM-XX-XX-T-A-0010 | OutlineSpecification | P04 | Completed | 2023-09-22 | Architectural Review | B3 - Partially Accepted with Comments | 2023-10-09 | 1.4 - blinds - confirm blinds comply with dim out and black out in relevant locations in accordance with Annex 3 and Annex 2D. 1.5 Confirm doors external doors are PAS 24 compliant in accordance with Annex 2C 5.1.3. 7.3 Confirm balustrade height is acceptable to Trust based on risk assessment in accordance with Annex 2D 6.1.1c. 10.4 is 4.5m high fence for sprinkler tank achievable/practical? are the gates to be 4.5m high too? how easy will these be to open for the users? | FALSE | FS1018-CPM-XX-XX-T-A-0010 OutlineSpecification | FS1018-CPM-XX-XX-T-A-0010
FS1018-CPM-XX-XX-T-A-0010 | Outline Specification | P08 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-XX-XX-T-A-0010 Outline Specification | FS1018-CPM-XX-XX-T-A-0010
FS1018-CPM-XX-XX-T-A-0010 | Outline Specification | P09 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-XX-XX-T-A-0010 Outline Specification | FS1018-CPM-XX-XX-T-A-0010
FS1018-CPM-XX-XX-T-A-0020 | Design and Access Statement | P02 | Completed | 2024-08-28 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-CPM-XX-XX-T-A-0020 Design and Access Statement | FS1018-CPM-XX-XX-T-A-0020
FS1018-CPM-XX-XX-T-A-5001 | Stage 3 Report | P01 | Completed | 2023-09-06 | Architectural Review | B3 - Partially Accepted with Comments | 2023-09-21 | Would like to have seen more of a narrative on how the SSB has evolved through the CEMs, how this has been captured and how it has been addressed; Would also like to see Next Steps and timescale itemised | FALSE | FS1018-CPM-XX-XX-T-A-5001 Stage 3 Report | FS1018-CPM-XX-XX-T-A-5001
FS1018-CPM-XX-XX-T-A-5001 | Stage 4 Report | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-XX-XX-T-A-5001 Stage 4 Report | FS1018-CPM-XX-XX-T-A-5001
FS1018-CPM-XX-XX-T-A-5002 | Design Development Report | P01 | Completed | 2023-09-06 | Architectural Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on document, and, Schedule does not totalise the Brief / Proposed area though I count the proposed design to be +35 sqm on the brief area. Please compare and contrast with FS1018-CPM-XX-XX-L-A-0001-ScheduleOfAccommodation-S5-P01 as well as GIFA as contained in Revit model and clarify. | FALSE | FS1018-CPM-XX-XX-T-A-5002 Design Development Report | FS1018-CPM-XX-XX-T-A-5002
FS1018-CPM-XX-XX-T-A-5002 | Design Development Report | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-XX-XX-T-A-5002 Design Development Report | FS1018-CPM-XX-XX-T-A-5002
FS1018-CPM-XX-XX-T-A-5003 | Pre-Construction Information | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-XX-XX-T-A-5003 Pre-Construction Information | FS1018-CPM-XX-XX-T-A-5003
FS1018-CPM-XX-ZZ-L-A-0000 | Building Model COBie | P12 | Completed | 2024-08-28 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-XX-ZZ-L-A-0000 Building Model COBie | FS1018-CPM-XX-ZZ-L-A-0000
FS1018-CPM-XX-ZZ-L-A-0000 | Building Model COBie Report | P25 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-XX-ZZ-L-A-0000 Building Model COBie Report | FS1018-CPM-XX-ZZ-L-A-0000
FS1018-CPM-ZZ-00-D-A-0001 | Reflected Ceiling Plan L00 | P01 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-00-D-A-0001 Reflected Ceiling Plan L00 | FS1018-CPM-ZZ-00-D-A-0001
FS1018-CPM-ZZ-00-D-A-2001 | GA Proposed Floor Plan L00 | P04 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | Refer to comments on attached drawings and the below. **--General notes for all GA plans deliverables: I really appreciate Room tag showing both SOA area and Proposed area - note however that some room tags are not legible eg DT Studio (electronics / control), please review; Have all rooms been allocated? What is total GIFA from Revit model? See comments on SoA discrepancies between FS1018-CPM-XX-XX-L-A-0001-ScheduleOfAccommodation-S5-P01 and FS1018-CPM-XX-XX-T-A-5002-DesignDevelopmentReport-S5-P01 ; No dimensions shown to gridlines, rooms, corridors, lifts, or stairs--**External staircase from L00 service yard to L01 roof not permissible under ER's - needs to ascend for internal secured space. See GDB: 2.6.5.2 External staircases are not permitted except when refurbishing Existing Buildings, if there is no alternative, and between changes in roof level for maintenance. [PM_10_20_82]; Ensure all externally opening doors have door guards inline with ER's and Statutory Requirements - ref TA 2C: 5.1.3 External door hardware, ironmongery or control mechanism provided shall be robust and heavy duty and the following requirements shall be met: i) Door guards shall be installed to opening outward doors. [Ss_25_30_20_25] and Building Regs Part K Diagram 10.2; Noting provision of 'Coat and bag store (lockers)' yet Trust previously advised they did not want these - please clarify your understanding that these are being shown for futureproofing? ; Confirm purpose of cupboard adjacent to Dining Hall doors? Note clash of outward opening doors. ; Please indicate access hatch between 00-2003 ¦ DIN11 and 00-6001 ¦ KIT01; Review appropriateness of proposed kitchen layout and 4 spaces within. Locating them all to the north reduces the usable wall area for the kitchen layout. Also consider environmental health requirements for access to toilets an clean/dirty workstreams. Is it worth trying to cluster these uses either side of the external door?; Confirm use of room located between 00-6041 ¦ TOC12 and 00-4003 ¦ ADM11?; Confirm reason for angled walls between 00-6001c ¦ RES12 and 00-6001d ¦ RES12. Not mentioned in FS1018-ADT-ZZ-ZZ-T-J-0001-AcousticStrategy-S5-P01; Confirm all proposed pupil toilet numbers satisfy ER's. Comment applies to all levels; Confirm all proposed staff toilet numbers satisfy ER's. Comment applies to all levels. ; Confirm dimensions to all toilets meet the ER's and Statutory requirements. Are they consistently sized? Comment applies to all levels.; Please show toilet layouts for 00-6012 ¦ TOC14 and 00-6013 ¦ TOC14 ; Please show shower and changing layouts for 00-6007 ¦ TOC01 and 00-6008 ¦ TOC01; Confirm how separate pupil and staff toilet use will be maintained when they are located alongside one another? ; Delineate clear zone in front of lift; Confirm proposed Lift dimensions satisfy ER's? See GDB 2.14.3.11: In mainstream schools the provision shall be related to the number of pupils and storeys served: [PM_80_50_30] b) for larger school | FALSE | FS1018-CPM-ZZ-00-D-A-2001 GA Proposed Floor Plan L00 | FS1018-CPM-ZZ-00-D-A-2001
FS1018-CPM-ZZ-00-D-A-2001 | GA Proposed L00 Floor Plan | P12 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-00-D-A-2001 GA Proposed L00 Floor Plan | FS1018-CPM-ZZ-00-D-A-2001
FS1018-CPM-ZZ-00-D-A-2001 | GA Proposed L00 Floor Plan | P17 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-00-D-A-2001 GA Proposed L00 Floor Plan | FS1018-CPM-ZZ-00-D-A-2001
FS1018-CPM-ZZ-00-D-A-2142 | Ground Edge Details | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-00-D-A-2142 Ground Edge Details | FS1018-CPM-ZZ-00-D-A-2142
FS1018-CPM-ZZ-00-D-A-2200 | Wall And Partition Types L00 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-00-D-A-2200 Wall And Partition Types L00 | FS1018-CPM-ZZ-00-D-A-2200
FS1018-CPM-ZZ-00-D-A-2900 | Fire Strategy L00 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-00-D-A-2900 Fire Strategy L00 | FS1018-CPM-ZZ-00-D-A-2900
FS1018-CPM-ZZ-00-D-A-3001 | External Door Schedules Sheet 01 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-00-D-A-3001 External Door Schedules Sheet 01 | FS1018-CPM-ZZ-00-D-A-3001
FS1018-CPM-ZZ-00-D-A-3050 | Internal Doors Level 00 Sheet 01 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-00-D-A-3050 Internal Doors Level 00 Sheet 01 | FS1018-CPM-ZZ-00-D-A-3050
FS1018-CPM-ZZ-00-D-A-3051 | Internal Doors Level 00 Sheet 02 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-00-D-A-3051 Internal Doors Level 00 Sheet 02 | FS1018-CPM-ZZ-00-D-A-3051
FS1018-CPM-ZZ-00-D-A-3052 | Internal Doors Level 00 Sheet 03 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-00-D-A-3052 Internal Doors Level 00 Sheet 03 | FS1018-CPM-ZZ-00-D-A-3052
FS1018-CPM-ZZ-00-D-A-3053 | Internal Doors Level 00 Sheet 04 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-00-D-A-3053 Internal Doors Level 00 Sheet 04 | FS1018-CPM-ZZ-00-D-A-3053
FS1018-CPM-ZZ-00-D-A-3054 | Internal Doors Level 00 Sheet 05 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-00-D-A-3054 Internal Doors Level 00 Sheet 05 | FS1018-CPM-ZZ-00-D-A-3054
FS1018-CPM-ZZ-00-D-A-3500 | Reflected Ceiling L00 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-00-D-A-3500 Reflected Ceiling L00 | FS1018-CPM-ZZ-00-D-A-3500
FS1018-CPM-ZZ-00-D-A-6807 | Room Elevations Hygiene Room | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-00-D-A-6807 Room Elevations Hygiene Room | FS1018-CPM-ZZ-00-D-A-6807
FS1018-CPM-ZZ-00-D-A-6808 | Room Elecations Pupil WC'S | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-00-D-A-6808 Room Elecations Pupil WC'S | FS1018-CPM-ZZ-00-D-A-6808
FS1018-CPM-ZZ-00-D-A-6809 | Room Elevations Pupils And Staff WC | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-00-D-A-6809 Room Elevations Pupils And Staff WC | FS1018-CPM-ZZ-00-D-A-6809
FS1018-CPM-ZZ-00-D-A-6810 | Room Elevations Accessible WC | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-00-D-A-6810 Room Elevations Accessible WC | FS1018-CPM-ZZ-00-D-A-6810
FS1018-CPM-ZZ-00-D-A-6811 | Room Elevations Changing Room | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-00-D-A-6811 Room Elevations Changing Room | FS1018-CPM-ZZ-00-D-A-6811
FS1018-CPM-ZZ-00-D-A-6812 | Room Elevations Accessible Changing Room | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-00-D-A-6812 Room Elevations Accessible Changing Room | FS1018-CPM-ZZ-00-D-A-6812
FS1018-CPM-ZZ-01-D-A-0001 | Reflected CeilingPlan L01 | P01 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-01-D-A-0001 Reflected CeilingPlan L01 | FS1018-CPM-ZZ-01-D-A-0001
FS1018-CPM-ZZ-01-D-A-2002 | GA Proposed Floor Plan L01 | P04 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | Refer to comments on the drawings and the below. Lightwells showing inconsistently - sometimes as void (white) sometimes as circulation (grey) - please clarify as will impact SoA; Are Lightwells coordinated between L00 and L01? Lightwell 1 at G-H/5 seems to offer a view into a riser cupboard below, while Lightwell 3 at N-P1/ 5 offers a view into 00-6010 ¦ TOC02; Please show a coordinated L01 Roof layout, with access routes, actual quantum of PV's indicated, along with syphonic drainage inlets (which need to be located away from access routes to prevent damage), proposed finishes codes to the Roof/Canopies to classrooms annotated, all roof levels, parapet levels ; How does 01-3006 ¦ SEN02 MI Medical treatment room provide hygienic setting as required of GDB 2.3.18.5 d) a medical treatment (nurse’s room) which provides a hygienic environment and provides secure and appropriate storage for medicines if it is used to access 01-4016 ¦ OFF23?; How does access to Services riser shaft from 01-4013 ¦ OFF12 satisfy GDB 2.3.3.2 Access to service risers within small rooms such as offices or stores shall not limit the required occupancy or furniture layout. [PM_10_80] ; Is it appropriate for 01-6062 ¦ PLA13 Server room to be located on the façade line with a window when Server Rooms need to be kept cool and other spaces could benefit from having this window? Is it worth considering swapping with 01-4013 ¦ OFF12 ? | FALSE | FS1018-CPM-ZZ-01-D-A-2002 GA Proposed Floor Plan L01 | FS1018-CPM-ZZ-01-D-A-2002
FS1018-CPM-ZZ-01-D-A-2002 | GA Proposed L01 Floor Plan | P11 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-01-D-A-2002 GA Proposed L01 Floor Plan | FS1018-CPM-ZZ-01-D-A-2002
FS1018-CPM-ZZ-01-D-A-2002 | GA Proposed L01 Floor Plan | P16 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-01-D-A-2002 GA Proposed L01 Floor Plan | FS1018-CPM-ZZ-01-D-A-2002
FS1018-CPM-ZZ-01-D-A-2201 | Wall And Partition Types L01 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-01-D-A-2201 Wall And Partition Types L01 | FS1018-CPM-ZZ-01-D-A-2201
FS1018-CPM-ZZ-01-D-A-2250 | Patressing Plan For Typical Classroom | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-01-D-A-2250 Patressing Plan For Typical Classroom | FS1018-CPM-ZZ-01-D-A-2250
FS1018-CPM-ZZ-01-D-A-2251 | Patressing Plan For Art Room | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-01-D-A-2251 Patressing Plan For Art Room | FS1018-CPM-ZZ-01-D-A-2251
FS1018-CPM-ZZ-01-D-A-2901 | Fire Strategy L01 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-01-D-A-2901 Fire Strategy L01 | FS1018-CPM-ZZ-01-D-A-2901
FS1018-CPM-ZZ-01-D-A-3501 | Reflected Ceiling L01 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-01-D-A-3501 Reflected Ceiling L01 | FS1018-CPM-ZZ-01-D-A-3501
FS1018-CPM-ZZ-01-D-A-6800 | Room Elevations Classroom | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-01-D-A-6800 Room Elevations Classroom | FS1018-CPM-ZZ-01-D-A-6800
FS1018-CPM-ZZ-02-D-A-0001 | Reflected Ceiling Plan L02 | P01 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-02-D-A-0001 Reflected Ceiling Plan L02 | FS1018-CPM-ZZ-02-D-A-0001
FS1018-CPM-ZZ-02-D-A-2003 | GA Proposed Floor Plan L02 | P04 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | Refer to comments on drawings and the below. Please show a coordinated L02 Roof layout, with access routes, actual quantum of PV's indicated, along with syphonic drainage inlets (which need to be located away from access routes to prevent damage), proposed finishes codes to the Roof/Canopies to classrooms annotated, all roof levels, parapet levels ; Check that all area showing in 02-3008 ¦ RES03 is attributed to the room and not circulation; Represent two halls at this level consistently - the Dining Hall is shown as a void, the Sports hall is shown as green fill with rooflights.; How is access from L02 up to Roof level via Stairway 2 restricted? Should route of Northern Stair be flipped and a door added? ; Omit shadows cast by Revit model on GA's | FALSE | FS1018-CPM-ZZ-02-D-A-2003 GA Proposed Floor Plan L02 | FS1018-CPM-ZZ-02-D-A-2003
FS1018-CPM-ZZ-02-D-A-2003 | GA Proposed L02 Floor Plan | P12 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-02-D-A-2003 GA Proposed L02 Floor Plan | FS1018-CPM-ZZ-02-D-A-2003
FS1018-CPM-ZZ-02-D-A-2003 | GA Proposed L02 Floor Plan | P17 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-02-D-A-2003 GA Proposed L02 Floor Plan | FS1018-CPM-ZZ-02-D-A-2003
FS1018-CPM-ZZ-02-D-A-2202 | Wall And Partition Types L02 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-02-D-A-2202 Wall And Partition Types L02 | FS1018-CPM-ZZ-02-D-A-2202
FS1018-CPM-ZZ-02-D-A-2902 | Fire Strategy L02 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-02-D-A-2902 Fire Strategy L02 | FS1018-CPM-ZZ-02-D-A-2902
FS1018-CPM-ZZ-02-D-A-3502 | Reflected Ceiling L02 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-02-D-A-3502 Reflected Ceiling L02 | FS1018-CPM-ZZ-02-D-A-3502
FS1018-CPM-ZZ-RF-D-A-2023 | GA Proposed Roof Plan | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | Refer to comments on the drawing and the below. Review clash of gridlines; Please show a coordinated Main Roof layout, with access routes, actual quantum of PV's indicated, along with syphonic drainage inlets (which need to be located away from access routes to prevent damage), proposed finishes codes to the Roof/Canopies to classrooms annotated, all roof levels, parapet levels, etc; Is proposed quantum of PV's sufficient? As commented elsewhere, this needs to be shown to justify provision of canopies elsewhere.; Is this a BioSolar Green roof in accordance with ER's? ; Are all rooflights required? See comments elsewhere about appropriate placement of rooms needing/not needing daylight.; Clarify discrepancy between Access Hatch at gridlines E/5 which is shown rectangular at Roof level, but serves a square-shaped space at L02. Is this coordinated?; Need more detail on railing to Secondary Means of Escape Hatch - does it comply with ER's? Note TA 2C: 3.5.4 Non-permanent or collapsible type barriers shall not be acceptable. The provision of free-standing systems which rely on their dead weight only and are not physically fixed to the building structure for stability and strength, shall be acceptable only where there are limitations forming connections through the roof deck to the structure e.g., in modular construction. [PM_10_20_82] | FALSE | FS1018-CPM-ZZ-RF-D-A-2023 GA Proposed Roof Plan | FS1018-CPM-ZZ-RF-D-A-2023
FS1018-CPM-ZZ-RF-D-A-2023 | GA Proposed Roof Plan | P07 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-RF-D-A-2023 GA Proposed Roof Plan | FS1018-CPM-ZZ-RF-D-A-2023
FS1018-CPM-ZZ-RF-D-A-2023 | GA Proposed Roof Plan | P15 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-RF-D-A-2023 GA Proposed Roof Plan | FS1018-CPM-ZZ-RF-D-A-2023
FS1018-CPM-ZZ-RF-D-A-2144 | Roof Details Sheet 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-RF-D-A-2144 Roof Details Sheet 1 | FS1018-CPM-ZZ-RF-D-A-2144
FS1018-CPM-ZZ-RF-D-A-2145 | Roof Details Sheet 2 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-RF-D-A-2145 Roof Details Sheet 2 | FS1018-CPM-ZZ-RF-D-A-2145
FS1018-CPM-ZZ-RF-D-A-2903 | Fire Strategy Rf | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-RF-D-A-2903 Fire Strategy Rf | FS1018-CPM-ZZ-RF-D-A-2903
FS1018-CPM-ZZ-RF-D-A-3100 | Rooflight Elevations Sheet 1 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-RF-D-A-3100 Rooflight Elevations Sheet 1 | FS1018-CPM-ZZ-RF-D-A-3100
FS1018-CPM-ZZ-RF-D-A-3101 | Rooflights And Hatch Plan | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-RF-D-A-3101 Rooflights And Hatch Plan | FS1018-CPM-ZZ-RF-D-A-3101
FS1018-CPM-ZZ-XX-D-A-2146 | 3D Section | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-XX-D-A-2146 3D Section | FS1018-CPM-ZZ-XX-D-A-2146
FS1018-CPM-ZZ-XX-D-A-2210 | Partition Detail Plans | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-XX-D-A-2210 Partition Detail Plans | FS1018-CPM-ZZ-XX-D-A-2210
FS1018-CPM-ZZ-XX-L-A-0020 | CDM Design Risk Assessment | P01 | Completed | 2023-09-06 | CDM Review | B3 - Partially Accepted with Comments | 2023-09-25 | KB Comments:  Would comment that its more of a RAG list status more than a risk assessment that identifies hazards and the actions taken at design stage to eliminate or reduce and at what stage it applies i.e. construction, operation/maintenance, demolition.  would be expecting to see the Principal Designer accumulate project designers’ significant risks into a single CDM Risk Register;  Confirm/Identify appropriate information at design that the Principal Designer will need to include in the H&S file for completion | FALSE | FS1018-CPM-ZZ-XX-L-A-0020 CDM Design Risk Assessment | FS1018-CPM-ZZ-XX-L-A-0020
FS1018-CPM-ZZ-XX-L-A-0020 | CDM Design Risk Assessment | P02 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-CPM-ZZ-XX-L-A-0020 CDM Design Risk Assessment | FS1018-CPM-ZZ-XX-L-A-0020
FS1018-CPM-ZZ-XX-L-A-0020 | CDM Design Risk Assessment | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-XX-L-A-0020 CDM Design Risk Assessment | FS1018-CPM-ZZ-XX-L-A-0020
FS1018-CPM-ZZ-ZZ-D-A-0050 | Circulation Strategy | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on the drawing. Circulation widths to wc's is not consistent between L00 (1.5m) and upper floors (1.8m) - all need to be in accordance with ER's ; Clarify annotations of 'principal entrance' and 'pupil entrance' - is this pupil entrance just from the Hard/Soft play or is this their entrance upon arrival to school? Please see comments on Landscape drawing FS1018-ONE-XX-ZZ-D-L-0009-Access Security Strategy-S5-P04 Please indicate Entrances for Staff / Pupils / Public / Community | FALSE | FS1018-CPM-ZZ-ZZ-D-A-0050 Circulation Strategy | FS1018-CPM-ZZ-ZZ-D-A-0050
FS1018-CPM-ZZ-ZZ-D-A-0050 | Circulation Strategy | P02 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-CPM-ZZ-ZZ-D-A-0050 Circulation Strategy | FS1018-CPM-ZZ-ZZ-D-A-0050
FS1018-CPM-ZZ-ZZ-D-A-0050 | Circulation Strategy | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-0050 Circulation Strategy | FS1018-CPM-ZZ-ZZ-D-A-0050
FS1018-CPM-ZZ-ZZ-D-A-0051 | Zoning & Security Strategy | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on the drawing and, Are 00-6009 ¦ TOC02 and 00-6010 ¦ TOC02 intended for community use also? Otherwise, where can accessible changing and changing places activities take place?; Are all aspects of ER's satisfied with regards to Passive Supervision? GDB 1.8.4.1 d) toilets that are positioned for easy access and to facilitate passive supervision. [Ac_25_90_60]). | FALSE | FS1018-CPM-ZZ-ZZ-D-A-0051 Zoning & Security Strategy | FS1018-CPM-ZZ-ZZ-D-A-0051
FS1018-CPM-ZZ-ZZ-D-A-0051 | Zoning and Security Strategy | P02 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-CPM-ZZ-ZZ-D-A-0051 Zoning and Security Strategy | FS1018-CPM-ZZ-ZZ-D-A-0051
FS1018-CPM-ZZ-ZZ-D-A-0051 | Zoning And Security Strategy | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-0051 Zoning And Security Strategy | FS1018-CPM-ZZ-ZZ-D-A-0051
FS1018-CPM-ZZ-ZZ-D-A-0052 | Sanitary & Hygiene Strategy | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawing and, 7 toilets denoted at eastern cluster - contrast with GA's which show 8.; 5M & 5F showers denoted - does this satisfy ER's? Ref BB103: Normally in secondary schools it is sufficient to provide changing facilities for half a year group with equal and separate facilities for boys and girls in co-educational schools. Showers should generally be in the form of separate cubicles, with about one for every seven pupils changing. At least one accessible changing area (with a sanitary fitting, wash basin and shower) should be provided, although this may be also be used by staff. See point made elsewhere - please show layout | FALSE | FS1018-CPM-ZZ-ZZ-D-A-0052 Sanitary & Hygiene Strategy | FS1018-CPM-ZZ-ZZ-D-A-0052
FS1018-CPM-ZZ-ZZ-D-A-0052 | Sanitary and Hygiene Strategy | P02 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-CPM-ZZ-ZZ-D-A-0052 Sanitary and Hygiene Strategy | FS1018-CPM-ZZ-ZZ-D-A-0052
FS1018-CPM-ZZ-ZZ-D-A-0052 | Sanitary And Hygiene Strategy | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-0052 Sanitary And Hygiene Strategy | FS1018-CPM-ZZ-ZZ-D-A-0052
FS1018-CPM-ZZ-ZZ-D-A-0053 | Access & Maintenance Strategy | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawing and, "Access & Maintenance Strategy Legend lists Building Fabric elements - but Access and Maintenance Strategy ought to also highlight the major risks represented and steps taken to design out / reduce / mitigate said risks. Some immediate specific risks that stand out: 1/ access from L00 up to L01 roof (covered elsewhere here) 2/ area under stairs posing collision risk 3/ open voids to L01 / L02 with respect to falling, fire, throwing things down to L00 etc" | FALSE | FS1018-CPM-ZZ-ZZ-D-A-0053 Access & Maintenance Strategy | FS1018-CPM-ZZ-ZZ-D-A-0053
FS1018-CPM-ZZ-ZZ-D-A-0053 | Access and Maintenance Strategy | P04 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-D-A-0053 Access and Maintenance Strategy | FS1018-CPM-ZZ-ZZ-D-A-0053
FS1018-CPM-ZZ-ZZ-D-A-0053 | Access And Maintenance Strategy | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-0053 Access And Maintenance Strategy | FS1018-CPM-ZZ-ZZ-D-A-0053
FS1018-CPM-ZZ-ZZ-D-A-0054 | Cleaning & Maintenance Strategy | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawings and, How are smaller areas of roof proposed to be accessed, cleaned and maintained? Roofs to: LRC, Sports stores, entrance canopy; Zone for polewashing for windows indicated but how are areas at L01 and above accessed for maintenance? Can you get a MEWP along the entire perimeter of the façade?; Show how MEWPS gain access to large internal hall spaces?; Need to indicate access and clearances around roof plant / PV's, as well as travel distances | FALSE | FS1018-CPM-ZZ-ZZ-D-A-0054 Cleaning & Maintenance Strategy | FS1018-CPM-ZZ-ZZ-D-A-0054
FS1018-CPM-ZZ-ZZ-D-A-0054 | Cleaning and Maintenance Strategy | P02 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-CPM-ZZ-ZZ-D-A-0054 Cleaning and Maintenance Strategy | FS1018-CPM-ZZ-ZZ-D-A-0054
FS1018-CPM-ZZ-ZZ-D-A-0054 | Cleaning And Maintenance Strategy | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-0054 Cleaning And Maintenance Strategy | FS1018-CPM-ZZ-ZZ-D-A-0054
FS1018-CPM-ZZ-ZZ-D-A-0060 | Proposed Room Cluster Diagram | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-0060 Proposed Room Cluster Diagram | FS1018-CPM-ZZ-ZZ-D-A-0060
FS1018-CPM-ZZ-ZZ-D-A-2001 | GA Proposed Sections AABBCCDD | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawing and, Key plan denotes Sections AA-EE, yet only sections AA-DD shown. Section EE missing and rather important. Also section through LRC and entrance is key. Please provide.; Please show floor levels to AOD, not AFFL (on the basis that your NGL may vary) - and then dim between floors; Please show proposed parapet levels to AOD; Section BB: What are the internal finishes on the lanterns? They look dark - could be oppressive at the top of a building.; Section CC: Please show stair tread numbers, rise/going, levels at half landings, clear heights; Section CC: How is area under stair at L00 to be dealt with, noting it is unusable and a hazard if left open?; Section CC: Consider relationship of openings/glazing/louvres to stair flights in both stair cores in relation to user experience, guarding as outlined in B Regs AD Part K Diagram 3.1 and elevation composition.; Sections CC and DD: Confirm all parapet heights are 1100mm for safe access | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2001 GA Proposed Sections AABBCCDD | FS1018-CPM-ZZ-ZZ-D-A-2001
FS1018-CPM-ZZ-ZZ-D-A-2001 | GA Proposed Section AA, BB, CC, DD | P05 | Completed | 2024-09-10 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2001 GA Proposed Section AA, BB, CC, DD | FS1018-CPM-ZZ-ZZ-D-A-2001
FS1018-CPM-ZZ-ZZ-D-A-2001 | GA Proposed Section Aa, Bb, Cc, Dd | P08 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2001 GA Proposed Section Aa, Bb, Cc, Dd | FS1018-CPM-ZZ-ZZ-D-A-2001
FS1018-CPM-ZZ-ZZ-D-A-2002 | GA Proposed Section EE 1 To 125 | P05 | Completed | 2024-09-10 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2002 GA Proposed Section EE 1 To 125 | FS1018-CPM-ZZ-ZZ-D-A-2002
FS1018-CPM-ZZ-ZZ-D-A-2002 | GA Proposed Section EE | P06 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2002 GA Proposed Section EE | FS1018-CPM-ZZ-ZZ-D-A-2002
FS1018-CPM-ZZ-ZZ-D-A-2005 | GA Proposed Section EE | P02 | Completed | 2024-09-10 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-CPM-ZZ-ZZ-D-A-2005 GA Proposed Section EE | FS1018-CPM-ZZ-ZZ-D-A-2005
FS1018-CPM-ZZ-ZZ-D-A-2010 | GA Proposed Elevations Sheet 01 | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawing and, "**---General notes for all GA elevation deliverables: Please omit shadows/rendered trees/bins/other fencing in front etc, we would like to see the full building elevations rather than a rendered Revit model cut line; Legend note 1 - 5: Please provide further information on selection of Buff and Dark Grey brickwork; Legend note 1 - 5: Please further detail on proposed wall depths/build ups to show head/jamb/cill details of recessed and hit & miss scenarios ; Legend note 6: Please provide further detail on proposed rainscreen system; Legend note 12: Galvanised - see ER's TA 2C 3.5.2 g) Galvanised mild steel balustrades are permitted in non-visually obvious situations [PM_80_60_50] - the proposed locations would be considered visually obvious; Please provide Sample board showing all proposed finishes; See previous comments about fencing heights - look low on these elevations--**; Please show External doors accurately - Doors to L00 Kitchen and Roof Plant shown as glazed (Note does say 'PPC Aluminium Doors (Louvred/Solid/Glazed)' but it should be drawn accurately)" | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2010 GA Proposed Elevations Sheet 01 | FS1018-CPM-ZZ-ZZ-D-A-2010
FS1018-CPM-ZZ-ZZ-D-A-2010 | GA Proposed Elevations Sheet 1 | P06 | Completed | 2024-09-10 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2010 GA Proposed Elevations Sheet 1 | FS1018-CPM-ZZ-ZZ-D-A-2010
FS1018-CPM-ZZ-ZZ-D-A-2010 | GA Proposed Elevations Sheet 1 | P08 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2010 GA Proposed Elevations Sheet 1 | FS1018-CPM-ZZ-ZZ-D-A-2010
FS1018-CPM-ZZ-ZZ-D-A-2011 | GA Proposed Elevations Sheet 02 | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawing and, At stair cores: consider relationship of openings/glazing/louvres to stair flights in elevation and in section; What are the various finishes to curtain walling at stair cores? Legend says 'PPC Aluminium Curtain Walling System (Dark Grey)' but elevation indicates light glazing and spandrel at L001, and dark glazing and spandrel at L01 and L02 - can you provide more detail? ; Consider terminating curtain walling at half landing instead of running down to L00 level if this area under stair will be out of sight and inaccessible? Not best use of £ also consider robustness requirements of ER's (GDB and TA 2C); Consider terminating Curtain walling at underside of Roof slab level? Currently shown running up past the Roof FFL to form part of the parapet? Improbable and not best use of £. Please review composition of elevations if maintaining a common datum between both stair cores is important to you. | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2011 GA Proposed Elevations Sheet 02 | FS1018-CPM-ZZ-ZZ-D-A-2011
FS1018-CPM-ZZ-ZZ-D-A-2011 | GA Proposed Elevations Sheet 2 | P04 | Completed | 2024-09-10 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2011 GA Proposed Elevations Sheet 2 | FS1018-CPM-ZZ-ZZ-D-A-2011
FS1018-CPM-ZZ-ZZ-D-A-2011 | GA Proposed Elevations Sheet 02 | P06 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2011 GA Proposed Elevations Sheet 02 | FS1018-CPM-ZZ-ZZ-D-A-2011
FS1018-CPM-ZZ-ZZ-D-A-2012 | GA Proposed Elevations Sheet 03 | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawing and, Please confirm what the main entrance doors will be made from? Proposal looks like internal double doors, but presume this is a function of Revit modelling view range.; Is signage on canopy sufficiently sized and contrasting for the person on the ground looking upwards? | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2012 GA Proposed Elevations Sheet 03 | FS1018-CPM-ZZ-ZZ-D-A-2012
FS1018-CPM-ZZ-ZZ-D-A-2012 | GA Proposed Elevations Sheet 03 | P04 | Completed | 2024-09-10 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2012 GA Proposed Elevations Sheet 03 | FS1018-CPM-ZZ-ZZ-D-A-2012
FS1018-CPM-ZZ-ZZ-D-A-2012 | GA Proposed Elevations Sheet 03 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2012 GA Proposed Elevations Sheet 03 | FS1018-CPM-ZZ-ZZ-D-A-2012
FS1018-CPM-ZZ-ZZ-D-A-2013 | GA Proposed Elevations SE 1 To 125 | P06 | Completed | 2024-09-10 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2013 GA Proposed Elevations SE 1 To 125 | FS1018-CPM-ZZ-ZZ-D-A-2013
FS1018-CPM-ZZ-ZZ-D-A-2014 | GA Proposed Elevations NW 1 to 125 | P06 | Completed | 2024-09-10 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2014 GA Proposed Elevations NW 1 to 125 | FS1018-CPM-ZZ-ZZ-D-A-2014
FS1018-CPM-ZZ-ZZ-D-A-2025 | Hazard Identification Plan | P01 | Completed | 2023-09-06 | Architectural Review | B3 - Partially Accepted with Comments | 2023-09-21 | Can you tabulate the risks to show: Risk rating (based on Probability x Impact) and proposed steps to eliminate, reduce, mitigate. | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2025 Hazard Identification Plan | FS1018-CPM-ZZ-ZZ-D-A-2025
FS1018-CPM-ZZ-ZZ-D-A-2025 | Hazard Identification Plan | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-ZZ-D-A-2025 Hazard Identification Plan | FS1018-CPM-ZZ-ZZ-D-A-2025
FS1018-CPM-ZZ-ZZ-D-A-2031 | Visuals Sheet 01 External | P01 | Completed | 2023-09-06 | Architectural Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2031 Visuals Sheet 01 External | FS1018-CPM-ZZ-ZZ-D-A-2031
FS1018-CPM-ZZ-ZZ-D-A-2031 | Internal Views | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2031 Internal Views | FS1018-CPM-ZZ-ZZ-D-A-2031
FS1018-CPM-ZZ-ZZ-D-A-2032 | Visuals Sheet 02 Internal | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawing and Ceilings in LRC look low - are they? GA Sections do not cover this area. | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2032 Visuals Sheet 02 Internal | FS1018-CPM-ZZ-ZZ-D-A-2032
FS1018-CPM-ZZ-ZZ-D-A-2032 | External Views | P02 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-CPM-ZZ-ZZ-D-A-2032 External Views | FS1018-CPM-ZZ-ZZ-D-A-2032
FS1018-CPM-ZZ-ZZ-D-A-2032 | External Views | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2032 External Views | FS1018-CPM-ZZ-ZZ-D-A-2032
FS1018-CPM-ZZ-ZZ-D-A-2040 | Lock Suiting Strategy | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2040 Lock Suiting Strategy | FS1018-CPM-ZZ-ZZ-D-A-2040
FS1018-CPM-ZZ-ZZ-D-A-2140 | Construction Building Sections Sheet 1 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2140 Construction Building Sections Sheet 1 | FS1018-CPM-ZZ-ZZ-D-A-2140
FS1018-CPM-ZZ-ZZ-D-A-2141 | Construction Building Sections | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawing and, Is proposed roof a Bio Solar Green Roof in line with DfE ER's? TA 2C 3.2.1 All roofs shall comprise a bio-solar green roofing system, maximised with photovoltaics (PVs) to meet the requirements in Technical Annex 2G, Technical Annex 2H and Technical Annex 2J. [PM_10_20_90]; Parapet detail annotates a 'Recessed feature brickwork' - yet the elevation shows hit and miss brickwork. Is it recessed or is it hit and miss? ; Detail 2: Is there barrier matting here? ; Are 2 x Top hung opening light's automated? ; Please provide more details of fibre cement rainscreen cladding; Confirm Thermal / Fire / Acoustic requirements have been achieved - provide all systems testing and certification | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2141 Construction Building Sections | FS1018-CPM-ZZ-ZZ-D-A-2141
FS1018-CPM-ZZ-ZZ-D-A-2141 | Construction Building Sections | P02 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-CPM-ZZ-ZZ-D-A-2141 Construction Building Sections | FS1018-CPM-ZZ-ZZ-D-A-2141
FS1018-CPM-ZZ-ZZ-D-A-2141 | Construction Building Sections Sheet 2 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-ZZ-D-A-2141 Construction Building Sections Sheet 2 | FS1018-CPM-ZZ-ZZ-D-A-2141
FS1018-CPM-ZZ-ZZ-D-A-2143 | External Wall Details Sheet 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2143 External Wall Details Sheet 1 | FS1018-CPM-ZZ-ZZ-D-A-2143
FS1018-CPM-ZZ-ZZ-D-A-2144 | External Wall Details Sheet 2 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-ZZ-D-A-2144 External Wall Details Sheet 2 | FS1018-CPM-ZZ-ZZ-D-A-2144
FS1018-CPM-ZZ-ZZ-D-A-2401 | Typical Staircase Sheet 01 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2401 Typical Staircase Sheet 01 | FS1018-CPM-ZZ-ZZ-D-A-2401
FS1018-CPM-ZZ-ZZ-D-A-2402 | Typical Staircase Sheet 02 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2402 Typical Staircase Sheet 02 | FS1018-CPM-ZZ-ZZ-D-A-2402
FS1018-CPM-ZZ-ZZ-D-A-2403 | Typical Staircase Sheet 03 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2403 Typical Staircase Sheet 03 | FS1018-CPM-ZZ-ZZ-D-A-2403
FS1018-CPM-ZZ-ZZ-D-A-2404 | Typical Staircase Sheet 04 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2404 Typical Staircase Sheet 04 | FS1018-CPM-ZZ-ZZ-D-A-2404
FS1018-CPM-ZZ-ZZ-D-A-2405 | Typical Staircase Sheet 05 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-2405 Typical Staircase Sheet 05 | FS1018-CPM-ZZ-ZZ-D-A-2405
FS1018-CPM-ZZ-ZZ-D-A-3002 | External Door Schedues Sheet 02 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-3002 External Door Schedues Sheet 02 | FS1018-CPM-ZZ-ZZ-D-A-3002
FS1018-CPM-ZZ-ZZ-D-A-3010 | Curtain Wall Panelling Elevations Sheet 01 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-3010 Curtain Wall Panelling Elevations Sheet 01 | FS1018-CPM-ZZ-ZZ-D-A-3010
FS1018-CPM-ZZ-ZZ-D-A-3011 | Curtain Wall Panelling Elevations Sheet 02 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-3011 Curtain Wall Panelling Elevations Sheet 02 | FS1018-CPM-ZZ-ZZ-D-A-3011
FS1018-CPM-ZZ-ZZ-D-A-3020 | External Windows Elevation And Schedule | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-3020 External Windows Elevation And Schedule | FS1018-CPM-ZZ-ZZ-D-A-3020
FS1018-CPM-ZZ-ZZ-D-A-3021 | Internal Glazed Panel Elevations And Schedule | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-3021 Internal Glazed Panel Elevations And Schedule | FS1018-CPM-ZZ-ZZ-D-A-3021
FS1018-CPM-ZZ-ZZ-D-A-3055 | Internal Doors Level 00 Sheet 06 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-3055 Internal Doors Level 00 Sheet 06 | FS1018-CPM-ZZ-ZZ-D-A-3055
FS1018-CPM-ZZ-ZZ-D-A-3062 | Window Schedule | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-3062 Window Schedule | FS1018-CPM-ZZ-ZZ-D-A-3062
FS1018-CPM-ZZ-ZZ-D-A-4001 | GA Wall Finishes Strategy | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawings and, Can I ask for these strategy drawings to show L00 at the bottom of the page and go up the page L01 L02, as your other strategy drawings? Mix of methods is inconsistent. Comment applies also to FS1018-CPM-ZZ-ZZ-D-A-4004-GAFloorFinishesStrategy-S5-P01 and FS1018-CPM-ZZ-ZZ-D-A-4007-GACeilingFinishesStrategy-S5-P01; Note that room fills denoting wall finishes missing from L00, please show.; How does your code W2.2 map to Internal Wall Finishes Table 2 in TA 2D? Do you mean 2.2h? ; Showers are shown as W2.2 but shouldn't they be W3.3 as per Table 2 in TA 2D? Ie Wet areas not humid areas? ; Please provide further detail on W6.1h proposed finish to Sports Hall. ; How are acoustic requirements outlined in FS1018-ADT-ZZ-ZZ-T-J-0001-AcousticStrategy-S5-P01 satisfied in proposals for both Main Hall and Sports Hall? Eg in Sports Hall acoustic strategy says 'The current proposal is to have plywood wall finishes including perforated panels at low level, on a sub frame with mineral wool backing.' | FALSE | FS1018-CPM-ZZ-ZZ-D-A-4001 GA Wall Finishes Strategy | FS1018-CPM-ZZ-ZZ-D-A-4001
FS1018-CPM-ZZ-ZZ-D-A-4001 | GA Wall Finishes Strategy | P03 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-D-A-4001 GA Wall Finishes Strategy | FS1018-CPM-ZZ-ZZ-D-A-4001
FS1018-CPM-ZZ-ZZ-D-A-4001 | GA Wall Finishes Strategy | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-4001 GA Wall Finishes Strategy | FS1018-CPM-ZZ-ZZ-D-A-4001
FS1018-CPM-ZZ-ZZ-D-A-4004 | GA Floor Finishes Strategy | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawing and, Note that room fills denoting floor finishes missing from L00, please show.; F1.1 Carpet is proposed for Stairs - is this correct?; F2.1 Vinyl to Server room - is this correct; Are F3.2i and F3.4 the same floor finish, with the only difference being in the skirting?; F3.4 for 'Light practical' in Art and Science? Wouldn't these be Heavy practical as outlined in TA 2D Table 5a?; Is there any F5 for Heavy practical? Not on legend besides F5.4 in Plantrooms; Do codes F6.1 (activity studio) and F6.2h (multi purpose hall) match the plans? ; No finish to cupboard from secondary access; Acoustic underlay denoted on legend but not shown on plans. | FALSE | FS1018-CPM-ZZ-ZZ-D-A-4004 GA Floor Finishes Strategy | FS1018-CPM-ZZ-ZZ-D-A-4004
FS1018-CPM-ZZ-ZZ-D-A-4004 | GA Floor Finishes Strategy | P03 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-D-A-4004 GA Floor Finishes Strategy | FS1018-CPM-ZZ-ZZ-D-A-4004
FS1018-CPM-ZZ-ZZ-D-A-4004 | GA Floor Finishes Strategy | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-4004 GA Floor Finishes Strategy | FS1018-CPM-ZZ-ZZ-D-A-4004
FS1018-CPM-ZZ-ZZ-D-A-4007 | GA Ceiling Finishes Strategy | P01 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawings and, Need to see proposed FCL's for each room; Do External Stores require a ceiling C1.1? ; Please clarify note in Ceiling 1.1 (600x600 grid ceiling) and Ceiling 1.2 (600x600 hygienic grid ceiling) 'in classrooms ceiling C3.2 provided to area outside of raft' - what does this mean, given that C3.2 is described as an emulsion painted concrete soffit to humid areas. Are you saying that the substrate is emulsion painted concrete soffit with raft ceilings? ; Ceiling type C1.1e described as 'PPC perforated profiled structural metal deck' - how does this satisfy acoustic requirements contained in Acoustic Strategy FS1018-ADT-ZZ-ZZ-T-J-0001-AcousticStrategy-S5-P01 'In the sports hall there will be a perforated liner tray to the roof, overlaid with mineral wool insulation and with insulation to the troughs, to achieve minimum absorption Class C.'; You have multiple ceiling codes for 2.2, 2.2/2.3, 2.3. Is Ceiling code 2.2/2.3 confusing things? ER's clear on what is needed where. This is why you need to draw your shower layouts - typically these are classed as wet areas (C2.3), with the changing space classed as a humid area (C2.2) | FALSE | FS1018-CPM-ZZ-ZZ-D-A-4007 GA Ceiling Finishes Strategy | FS1018-CPM-ZZ-ZZ-D-A-4007
FS1018-CPM-ZZ-ZZ-D-A-4007 | GA Ceiling Finishes Strategy | P03 | Completed | 2024-08-01 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-D-A-4007 GA Ceiling Finishes Strategy | FS1018-CPM-ZZ-ZZ-D-A-4007
FS1018-CPM-ZZ-ZZ-D-A-6601 | Lift Pit Details | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-6601 Lift Pit Details | FS1018-CPM-ZZ-ZZ-D-A-6601
FS1018-CPM-ZZ-ZZ-D-A-6801 | Room Elevations Assembly Dining Sheet 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-ZZ-D-A-6801 Room Elevations Assembly Dining Sheet 1 | FS1018-CPM-ZZ-ZZ-D-A-6801
FS1018-CPM-ZZ-ZZ-D-A-6802 | Room Elevations Assembly Dining Sheet 2 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-6802 Room Elevations Assembly Dining Sheet 2 | FS1018-CPM-ZZ-ZZ-D-A-6802
FS1018-CPM-ZZ-ZZ-D-A-6803 | Room Elevations Sports Hall Sheet 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-CPM-ZZ-ZZ-D-A-6803 Room Elevations Sports Hall Sheet 1 | FS1018-CPM-ZZ-ZZ-D-A-6803
FS1018-CPM-ZZ-ZZ-D-A-6804 | Room Elevations Sports Hall Sheet 2 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-6804 Room Elevations Sports Hall Sheet 2 | FS1018-CPM-ZZ-ZZ-D-A-6804
FS1018-CPM-ZZ-ZZ-D-A-6805 | Room Elevations Sports Hall Sheet 3 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-6805 Room Elevations Sports Hall Sheet 3 | FS1018-CPM-ZZ-ZZ-D-A-6805
FS1018-CPM-ZZ-ZZ-D-A-6806 | Room Elevations Sports Hall Acoustic Panel Set Out | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-6806 Room Elevations Sports Hall Acoustic Panel Set Out | FS1018-CPM-ZZ-ZZ-D-A-6806
FS1018-CPM-ZZ-ZZ-D-A-6813 | Room Elevations Pupil WC'S L01 And L02 | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-D-A-6813 Room Elevations Pupil WC'S L01 And L02 | FS1018-CPM-ZZ-ZZ-D-A-6813
FS1018-CPM-ZZ-ZZ-L-A-0001 | Clash Report | P02 | Completed | 2023-09-06 | Client / Contractor / BIM Review | C - Rejected | 2023-09-25 | Report identifies 2400 clashes. Report does not evidence sufficient issue/clash resolution progress during the stage. Report should be presented in a more actionable format. All images are corrupt in the report. | TRUE | FS1018-CPM-ZZ-ZZ-L-A-0001 Clash Report | FS1018-CPM-ZZ-ZZ-L-A-0001
FS1018-CPM-ZZ-ZZ-L-A-0001 | Clash Report | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-L-A-0001 Clash Report | FS1018-CPM-ZZ-ZZ-L-A-0001
FS1018-CPM-ZZ-ZZ-L-A-3060 | Internal Door Schedule | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-L-A-3060 Internal Door Schedule | FS1018-CPM-ZZ-ZZ-L-A-3060
FS1018-CPM-ZZ-ZZ-L-A-3061 | External Door Schedule | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-L-A-3061 External Door Schedule | FS1018-CPM-ZZ-ZZ-L-A-3061
FS1018-CPM-ZZ-ZZ-M-A-0002 | Federated Model | P02 | Completed | 2023-09-06 | Client / Contractor / BIM Review | C - Rejected | 2023-09-25 | Better spatial coordination would be expected by Stage 3, 2,400 clashes is impracticle and not acceptable. Structural elements not well coordinated with architecture (especially doors and structural elements. Internal walls not aligned with column and bracing positions. Instances of furniture interfering with architectural doorways and structural elements. Library entrance, threshold between outside and inside missing geometry. | TRUE | FS1018-CPM-ZZ-ZZ-M-A-0002 Federated Model | FS1018-CPM-ZZ-ZZ-M-A-0002
FS1018-CPM-ZZ-ZZ-M-A-0002 | Federated Model | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-M-A-0002 Federated Model | FS1018-CPM-ZZ-ZZ-M-A-0002
FS1018-CPM-ZZ-ZZ-M-A-0003 | Building Model Navisworks | P05 | Completed | 2023-09-06 | Architectural Review | B3 - Partially Accepted with Comments | 2023-09-26 | Object assignment to correct levels requires review as a it appears there are objects which should be on different levels. | FALSE | FS1018-CPM-ZZ-ZZ-M-A-0003 Building Model Navisworks | FS1018-CPM-ZZ-ZZ-M-A-0003
FS1018-CPM-ZZ-ZZ-M-A-0003 | Building Model Navisworks | P12 | Completed | 2024-08-28 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-M-A-0003 Building Model Navisworks | FS1018-CPM-ZZ-ZZ-M-A-0003
FS1018-CPM-ZZ-ZZ-M-A-0003 | Architectural Model NWC | P25 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-M-A-0003 Architectural Model NWC | FS1018-CPM-ZZ-ZZ-M-A-0003
FS1018-CPM-ZZ-ZZ-M-A-0004 | Building Model IFC | P05 | Completed | 2023-09-06 | Architectural Review | B3 - Partially Accepted with Comments | 2023-09-26 | modelling erros apparent (ie. ceiling passing through wall, gaps in external walls). 92 elements have USERDEFINED or NOTDEFINED predefined type and 341 with empty field. Object assignment to correct levels requires review. COBie Facility information not consistently available in the IFC properties, COBie Zones missing from architectural IFC. | FALSE | FS1018-CPM-ZZ-ZZ-M-A-0004 Building Model IFC | FS1018-CPM-ZZ-ZZ-M-A-0004
FS1018-CPM-ZZ-ZZ-M-A-0004 | Building Model IFC | P12 | Completed | 2024-08-28 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-M-A-0004 Building Model IFC | FS1018-CPM-ZZ-ZZ-M-A-0004
FS1018-CPM-ZZ-ZZ-M-A-0004 | Architectural Model IFC | P25 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-M-A-0004 Architectural Model IFC | FS1018-CPM-ZZ-ZZ-M-A-0004
FS1018-CPM-ZZ-ZZ-M-A-0005 | Building Model Revit | P05 | Completed | 2023-09-06 | Architectural Review | C - Rejected | 2023-09-26 | Model not detatched from central. Status on Flysheet is at S1. | FALSE | FS1018-CPM-ZZ-ZZ-M-A-0005 Building Model Revit | FS1018-CPM-ZZ-ZZ-M-A-0005
FS1018-CPM-ZZ-ZZ-M-A-0005 | Building Model Revit | P12 | Completed | 2024-08-28 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-CPM-ZZ-ZZ-M-A-0005 Building Model Revit | FS1018-CPM-ZZ-ZZ-M-A-0005
FS1018-CPM-ZZ-ZZ-M-A-0005 | Architectural Model Revit | P25 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-M-A-0005 Architectural Model Revit | FS1018-CPM-ZZ-ZZ-M-A-0005
FS1018-CPM-ZZ-ZZ-V-A-0001 | Flythrough Video | P01 | Completed | 2023-09-12 | Architectural Review | C - Rejected | 2023-09-21 | Video does not play. | FALSE | FS1018-CPM-ZZ-ZZ-V-A-0001 Flythrough Video | FS1018-CPM-ZZ-ZZ-V-A-0001
FS1018-CPM-ZZ-ZZ-V-A-0001 | Flythrough Video | P02 | Completed | 2024-08-28 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-CPM-ZZ-ZZ-V-A-0001 Flythrough Video | FS1018-CPM-ZZ-ZZ-V-A-0001
FS1018-CPM-ZZ-ZZ-V-A-0001 | External Flythrough Video | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-V-A-0001 External Flythrough Video | FS1018-CPM-ZZ-ZZ-V-A-0001
FS1018-CPM-ZZ-ZZ-V-A-0002 | Internal Flythrough Video | P01 | In Progress | 2025-03-14 | DFE Review | Pending |  |  | FALSE | FS1018-CPM-ZZ-ZZ-V-A-0002 Internal Flythrough Video | FS1018-CPM-ZZ-ZZ-V-A-0002
FS1018-DSI-XX-XX-T-G-0001 | GI Geo Environmental Assesment | P01 | Completed | 2024-08-28 | Civil Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-DSI-XX-XX-T-G-0001 GI Geo Environmental Assesment | FS1018-DSI-XX-XX-T-G-0001
FS1018-EVR-XX-XX-D-O-0001 | Server Room Location | P01 | Completed | 2023-09-06 | ICT Review | C - Rejected | 2023-09-26 | TR Comments:- Need to revisit proposed server and hub room location taking into account comments in lines 8, 9, 11, 12 - Is there a window in the server room | FALSE | FS1018-EVR-XX-XX-D-O-0001 Server Room Location | FS1018-EVR-XX-XX-D-O-0001
FS1018-EVR-XX-XX-D-O-0001 | Server Room Location | P02 | Completed | 2024-08-28 | ICT Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-EVR-XX-XX-D-O-0001 Server Room Location | FS1018-EVR-XX-XX-D-O-0001
FS1018-EVR-XX-XX-D-O-0001 | Server Room Location | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-EVR-XX-XX-D-O-0001 Server Room Location | FS1018-EVR-XX-XX-D-O-0001
FS1018-EVR-XX-XX-D-O-0002 | ICT Plans | P01 | Completed | 2023-09-06 | ICT Review | C - Rejected | 2023-09-26 | TR Comments:- Need to revisit proposed server and hub room location taking into account comments in lines 8, 9, 11, 12 | FALSE | FS1018-EVR-XX-XX-D-O-0002 ICT Plans | FS1018-EVR-XX-XX-D-O-0002
FS1018-EVR-XX-XX-D-O-0002 | ICT Plans | P02 | Completed | 2024-08-28 | ICT Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-EVR-XX-XX-D-O-0002 ICT Plans | FS1018-EVR-XX-XX-D-O-0002
FS1018-EVR-XX-XX-D-O-0002 | ICT Plans | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-EVR-XX-XX-D-O-0002 ICT Plans | FS1018-EVR-XX-XX-D-O-0002
FS1018-EVR-XX-XX-D-O-0003 | Wireless Heat Maps | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-EVR-XX-XX-D-O-0003 Wireless Heat Maps | FS1018-EVR-XX-XX-D-O-0003
FS1018-EVR-XX-XX-D-O-0004 | Server Cabinet Layout | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-EVR-XX-XX-D-O-0004 Server Cabinet Layout | FS1018-EVR-XX-XX-D-O-0004
FS1018-EVR-XX-XX-G-O-0001 | ICT Network Diagrams | P01 | Completed | 2023-09-06 | ICT Review | A3 - Accepted | 2023-09-26 |  | FALSE | FS1018-EVR-XX-XX-G-O-0001 ICT Network Diagrams | FS1018-EVR-XX-XX-G-O-0001
FS1018-EVR-XX-XX-G-O-0001 | ICT Network Diagrams | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-EVR-XX-XX-G-O-0001 ICT Network Diagrams | FS1018-EVR-XX-XX-G-O-0001
FS1018-EVR-XX-XX-L-O-0001 | ICT Equipment List | P01 | Completed | 2023-09-06 | ICT Review | C - Rejected | 2023-09-26 | TR Comments:- Need to revisit in line with changes that need to be made | FALSE | FS1018-EVR-XX-XX-L-O-0001 ICT Equipment List | FS1018-EVR-XX-XX-L-O-0001
FS1018-EVR-XX-XX-L-O-0001 | ICT Equipment List | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-EVR-XX-XX-L-O-0001 ICT Equipment List | FS1018-EVR-XX-XX-L-O-0001
FS1018-EVR-XX-XX-L-O-0002 | ICT Cost Matrix | P01 | Completed | 2023-09-06 | ICT Review | C - Rejected | 2023-09-26 | TR Comments:- Need to revisit in line with changes that need to be made | FALSE | FS1018-EVR-XX-XX-L-O-0002 ICT Cost Matrix | FS1018-EVR-XX-XX-L-O-0002
FS1018-EVR-XX-XX-L-O-0002 | ICT Cost Matrix | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-EVR-XX-XX-L-O-0002 ICT Cost Matrix | FS1018-EVR-XX-XX-L-O-0002
FS1018-EVR-XX-XX-L-O-0003 | ICT Small Power and Data Schedule | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-EVR-XX-XX-L-O-0003 ICT Small Power and Data Schedule | FS1018-EVR-XX-XX-L-O-0003
FS1018-EVR-XX-XX-L-O-0004 | ICT Construction Programme | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-EVR-XX-XX-L-O-0004 ICT Construction Programme | FS1018-EVR-XX-XX-L-O-0004
FS1018-EVR-XX-XX-T-O-0001 | ICT Decant Plan | P01 | Completed | 2024-08-28 | ICT Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-EVR-XX-XX-T-O-0001 ICT Decant Plan | FS1018-EVR-XX-XX-T-O-0001
FS1018-EVR-XX-XX-T-O-0002 | ICT Calculations | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-EVR-XX-XX-T-O-0002 ICT Calculations | FS1018-EVR-XX-XX-T-O-0002
FS1018-EVR-XX-XX-T-O-0003 | Draft ICT CPs | P01 | Completed | 2023-09-06 | ICT Review | C - Rejected | 2023-09-26 | See attached Comment sheet from Tony Roman - DfE ICT Advisor. Comments are logged against specific sections of the report which together ghave generated a Rejected vote. | FALSE | FS1018-EVR-XX-XX-T-O-0003 Draft ICT CPs | FS1018-EVR-XX-XX-T-O-0003
FS1018-EVR-XX-XX-T-O-0004 | ICT Contractor's Proposals | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-EVR-XX-XX-T-O-0004 ICT Contractor's Proposals | FS1018-EVR-XX-XX-T-O-0004
FS1018-EVR-XX-XX-T-O-0005 | Post Award ICT Meetings (PAM) Agendas | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-EVR-XX-XX-T-O-0005 Post Award ICT Meetings (PAM) Agendas | FS1018-EVR-XX-XX-T-O-0005
FS1018-EVR-XX-XX-T-O-0006 | User Acceptance Testing (UAT) Schedule | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-EVR-XX-XX-T-O-0006 User Acceptance Testing (UAT) Schedule | FS1018-EVR-XX-XX-T-O-0006
FS1018-EVR-XX-XX-T-O-0007 | Post Award ICT Meetings (PAM) Minutes | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-EVR-XX-XX-T-O-0007 Post Award ICT Meetings (PAM) Minutes | FS1018-EVR-XX-XX-T-O-0007
FS1018-GLE-XX-XX-T-Z-0001 | PV System Calculation | P03 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-GLE-XX-XX-T-Z-0001 PV System Calculation | FS1018-GLE-XX-XX-T-Z-0001
FS1018-HBC-XX-XX-D-R-9999 | DfE Wisbech - Blank TEST Document | P01 | Completed | 2023-08-29 | TEST Review | A - Approved | 2023-08-30 | Test Approval | FALSE | FS1018-HBC-XX-XX-D-R-9999 DfE Wisbech - Blank TEST Document | FS1018-HBC-XX-XX-D-R-9999
FS1018-HBC-XX-XX-D-R-9999 | DfE Wisbech - Blank TEST Document | P02 | Completed | 2023-08-30 | TEST Review | B - Approved with Comments | 2023-09-25 | Test | TRUE | FS1018-HBC-XX-XX-D-R-9999 DfE Wisbech - Blank TEST Document | FS1018-HBC-XX-XX-D-R-9999
FS1018-HBC-XX-XX-D-X-0001 | Site Set Up Plan | P01 | Completed | 2023-09-22 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2023-09-25 | Please provide a plan showing the site set-up during Phase 2 of the project. | FALSE | FS1018-HBC-XX-XX-D-X-0001 Site Set Up Plan | FS1018-HBC-XX-XX-D-X-0001
FS1018-HBC-XX-XX-D-X-0001 | Site Construction Plan | P01 | In Progress | 2025-03-19 | Designer Response | Pending |  |  | FALSE | FS1018-HBC-XX-XX-D-X-0001 Site Construction Plan | FS1018-HBC-XX-XX-D-X-0001
FS1018-HBC-XX-XX-D-X-0001 | Site Construction Plan | P01 | In Progress | 2025-03-13 | DFE Review | C - Rejected | 2025-03-19 | 1. this drawing shows the phase 1 construction area but uses the phase 3 car park layout (final configuration). HB need to show 2 construction phases and the different car park layouts as presented in the logistics CEM. | FALSE | FS1018-HBC-XX-XX-D-X-0001 Site Construction Plan | FS1018-HBC-XX-XX-D-X-0001
FS1018-HBC-XX-XX-D-X-0002 | Site Phasing Plan | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | C - Rejected | 2023-09-21 | Wtihin the phasing plan, we would expect to see the following: Details of the logistics for the different phases (compound, materials storage, hoarding, traffic management, etc.) Access points for staff, pupils, visitors, emergency services, contractors and deliveries. Generally, there are three different phases of the project: 1: Phase 1 only, pre-Phase 2 2: Phase 1 and 2 taking place in tandem 3: Phase 1 only, post-Phase 2 | FALSE | FS1018-HBC-XX-XX-D-X-0002 Site Phasing Plan | FS1018-HBC-XX-XX-D-X-0002
FS1018-HBC-XX-XX-D-X-0002 | Site Phasing Plan | P01 | Completed | 2023-10-02 | Client / Contractor / BIM Review | A3 - Accepted | 2023-10-09 |  | FALSE | FS1018-HBC-XX-XX-D-X-0002 Site Phasing Plan | FS1018-HBC-XX-XX-D-X-0002
FS1018-HBC-XX-XX-D-X-0002 | Site Phasing Plan | P02 | Completed | 2024-08-01 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-HBC-XX-XX-D-X-0002 Site Phasing Plan | FS1018-HBC-XX-XX-D-X-0002
FS1018-HBC-XX-XX-D-X-0003 | Site Set Up Plan Phase 1 | P01 | Completed | 2023-10-02 | Client / Contractor / BIM Review | A3 - Accepted | 2023-10-09 |  | FALSE | FS1018-HBC-XX-XX-D-X-0003 Site Set Up Plan Phase 1 | FS1018-HBC-XX-XX-D-X-0003
FS1018-HBC-XX-XX-D-X-0003 | Phase1 | P02 | Completed | 2024-08-01 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-HBC-XX-XX-D-X-0003 Phase1 | FS1018-HBC-XX-XX-D-X-0003
FS1018-HBC-XX-XX-D-X-0003 | Site Set Up Plan Phase 1 | P02 | Completed | 2025-03-13 | DFE Review | A - Accepted | 2025-03-19 | this document shows the correct car park layouts for this phase. therefore can FS1018-HBC-XX-XX-D-X-0001 be removed? | TRUE | FS1018-HBC-XX-XX-D-X-0003 Site Set Up Plan Phase 1 | FS1018-HBC-XX-XX-D-X-0003
FS1018-HBC-XX-XX-D-X-0004 | Site Set Up Plan Phase 2 | P01 | Completed | 2023-10-02 | Client / Contractor / BIM Review | A3 - Accepted | 2023-10-09 |  | FALSE | FS1018-HBC-XX-XX-D-X-0004 Site Set Up Plan Phase 2 | FS1018-HBC-XX-XX-D-X-0004
FS1018-HBC-XX-XX-D-X-0004 | Phase2 | P02 | Completed | 2024-08-01 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-HBC-XX-XX-D-X-0004 Phase2 | FS1018-HBC-XX-XX-D-X-0004
FS1018-HBC-XX-XX-D-X-0004 | Site Set Up Plan Phase 2 Section 1 | P02 | In Progress | 2025-03-19 | Designer Response | Pending |  |  | TRUE | FS1018-HBC-XX-XX-D-X-0004 Site Set Up Plan Phase 2 Section 1 | FS1018-HBC-XX-XX-D-X-0004
FS1018-HBC-XX-XX-D-X-0004 | Site Set Up Plan Phase 2 Section 1 | P02 | In Progress | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. as this is summer works are the notes regarding pedestrian access to be maintained necessary? 2. re the note about a decision needs to eb made regadring use if link road - Can the link road be released for use from Sept 2026 to improve the bus and pedestrian and vehicle access? 3. what arrangements will be made for Teaching staff parking during this phase of works as the new building will be open. This was raised at CEM meeting | TRUE | FS1018-HBC-XX-XX-D-X-0004 Site Set Up Plan Phase 2 Section 1 | FS1018-HBC-XX-XX-D-X-0004
FS1018-HBC-XX-XX-D-X-0005 | Roof Plan PV Annotations Mark up | P01 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-HBC-XX-XX-D-X-0005 Roof Plan PV Annotations Mark up | FS1018-HBC-XX-XX-D-X-0005
FS1018-HBC-XX-XX-D-X-0005 | Site Set Up Plan Phase 2 Section 2 | P01 | In Progress | 2025-03-19 | Designer Response | Pending |  |  | FALSE | FS1018-HBC-XX-XX-D-X-0005 Site Set Up Plan Phase 2 Section 2 | FS1018-HBC-XX-XX-D-X-0005
FS1018-HBC-XX-XX-D-X-0005 | Site Set Up Plan Phase 2 Section 2 | P01 | In Progress | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. more detailed proposals will be needed for phasing of access into staff car park as drawing indicates that this may be blocked. 2. Staff car parking will be needed in the interim period following portacabin decant and reinstatement of portakabin area to provide parking | FALSE | FS1018-HBC-XX-XX-D-X-0005 Site Set Up Plan Phase 2 Section 2 | FS1018-HBC-XX-XX-D-X-0005
FS1018-HBC-XX-XX-D-X-0006 | Site Set Up Plan Phase 3 | P01 | In Progress | 2025-03-19 | Designer Response | Pending |  |  | FALSE | FS1018-HBC-XX-XX-D-X-0006 Site Set Up Plan Phase 3 | FS1018-HBC-XX-XX-D-X-0006
FS1018-HBC-XX-XX-D-X-0006 | Site Set Up Plan Phase 3 | P01 | In Progress | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. should this drawing be named final layout post handover not site set up phase 3? | FALSE | FS1018-HBC-XX-XX-D-X-0006 Site Set Up Plan Phase 3 | FS1018-HBC-XX-XX-D-X-0006
FS1018-HBC-XX-XX-L-X-0001 | MIDP | P05 | Completed | 2023-10-03 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2023-10-20 | See email sent 20/10/23 - files in MIDP not matching CDE - 2 DEIR Items missing - 103 & 180. | FALSE | FS1018-HBC-XX-XX-L-X-0001 MIDP | FS1018-HBC-XX-XX-L-X-0001
FS1018-HBC-XX-XX-L-X-0001 | MIDP | P10 | Completed | 2024-08-30 | Client Review | C - Rejected | 2024-09-09 | the following items are either not matching CDE or not submitted - see email sent FS1018-AGL-ZZ-XX-T-Z-0003 FS1018-AGL-ZZ-XX-T-Z-0003 FS1018-AGL-ZZ-XX-T-Z-0003 FS1018-AGL-ZZ-ZZ-D-Z-5801 FS1018-CPM-ZZ-ZZ-D-A-2141 FS1018-CPM-XX-XX-T-A-5002 FS1018-DSI-XX-XX-T-G-0001 FS1018-EVR-XX-XX-D-O-0001 FS1018-EVR-XX-XX-T-O-0003 FS1018-HEX-ZZ-ZZ-M-C-0003 FS1018-HEX-ZZ-ZZ-D-C-5200 FS1018-HEX-ZZ-ZZ-D-C-5201 FS1018-HEX-ZZ-ZZ-D-C-5205 FS1018-HEX-ZZ-ZZ-D-C-5210 FS1018-HEX-ZZ-ZZ-D-C-5211 FS1018-ONE-ZZ-ZZ-M-L-0001 FS1018-PIN-ZZ-00-D-O-5021 | FALSE | FS1018-HBC-XX-XX-L-X-0001 MIDP | FS1018-HBC-XX-XX-L-X-0001
FS1018-HBC-XX-XX-L-X-0001 | MIDP | P12 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-HBC-XX-XX-L-X-0001 MIDP | FS1018-HBC-XX-XX-L-X-0001
FS1018-HBC-XX-XX-L-X-0001 | MIDP | P15 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-L-X-0001 MIDP | FS1018-HBC-XX-XX-L-X-0001
FS1018-HBC-XX-XX-L-X-0003 | Design Programme | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2023-09-21 | Programme needs updating following late issue of Stage 3 information to DfE. Additional comments on mark-up. | FALSE | FS1018-HBC-XX-XX-L-X-0003 Design Programme | FS1018-HBC-XX-XX-L-X-0003
FS1018-HBC-XX-XX-L-X-0003 | Design Programme | P02 | Completed | 2024-08-01 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-HBC-XX-XX-L-X-0003 Design Programme | FS1018-HBC-XX-XX-L-X-0003
FS1018-HBC-XX-XX-L-X-0003 | Design Programme | P02 | In Progress | 2025-03-19 | Designer Response | Pending |  |  | TRUE | FS1018-HBC-XX-XX-L-X-0003 Design Programme | FS1018-HBC-XX-XX-L-X-0003
FS1018-HBC-XX-XX-L-X-0003 | Design Programme | P02 | In Progress | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. Line 47 Judicial review and line 49 Discharge of pre commencement conditions can these be run concurrently? 2. line 51 is this a duplicate of line 49 but does suggest condition discharge is running concurrently? 3. line 68 Delivery of CPS was only partial MEP 17th March and costs etc not received as of 19/3/2025 4. Should CP review evaluation line 69 should be 8 weeks from receipt of full CPS. 5. line 80 should also include a note .. Contract finalisation including any increased DFE budget submissions (CCF) | TRUE | FS1018-HBC-XX-XX-L-X-0003 Design Programme | FS1018-HBC-XX-XX-L-X-0003
FS1018-HBC-XX-XX-L-X-0004 | Construction Programme | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2023-09-21 | Review required following late issue of Stage 3 information and to assess potential routes to allow the school to open in September 2025. | FALSE | FS1018-HBC-XX-XX-L-X-0004 Construction Programme | FS1018-HBC-XX-XX-L-X-0004
FS1018-HBC-XX-XX-L-X-0004 | Construction Programme | P02 | Completed | 2024-08-01 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-HBC-XX-XX-L-X-0004 Construction Programme | FS1018-HBC-XX-XX-L-X-0004
FS1018-HBC-XX-XX-L-X-0004 | Construction Programme | P02 | In Progress | 2025-03-19 | Designer Response | Pending |  |  | TRUE | FS1018-HBC-XX-XX-L-X-0004 Construction Programme | FS1018-HBC-XX-XX-L-X-0004
FS1018-HBC-XX-XX-L-X-0004 | Construction Programme | P02 | In Progress | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. Line 56 - please clarify this task - is this place order or install the substation - NB noted line 224 Legal process for easements and S77 disposal of land has been planned into programme 2. Line 74 power and water on 2a. power on does the activity need more details see my comments re line 56? 2b, this is planned for early in school term - can the service interruptions be planned outside school term ie summer or half term or weekends? 3 ICT fit out needs to be planned with School ICT contractor, also will need the main hall AV as a planned activity as well as the drama rooms etc. 4. Lines 297 and line 310 phase 2 section and 1 and 2 handover are both after school term starts can these be planned for completion prior to school term starts to avoid disruption ie before 1st September 2026 and 2027? | TRUE | FS1018-HBC-XX-XX-L-X-0004 Construction Programme | FS1018-HBC-XX-XX-L-X-0004
FS1018-HBC-XX-XX-L-X-0005 | Master Programme | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2023-09-21 | As comments on design and construction programmes. Additional comments on mark-up. | FALSE | FS1018-HBC-XX-XX-L-X-0005 Master Programme | FS1018-HBC-XX-XX-L-X-0005
FS1018-HBC-XX-XX-L-X-0005 | Master Programme | P02 | Completed | 2024-08-01 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-HBC-XX-XX-L-X-0005 Master Programme | FS1018-HBC-XX-XX-L-X-0005
FS1018-HBC-XX-XX-L-X-0005 | Master Programme | P02 | In Progress | 2025-03-19 | Designer Response | Pending |  |  | TRUE | FS1018-HBC-XX-XX-L-X-0005 Master Programme | FS1018-HBC-XX-XX-L-X-0005
FS1018-HBC-XX-XX-L-X-0005 | Master Programme | P02 | In Progress | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. see comments regarding Design programme and construction programme. Master programme to eb updated to reflect these comments | TRUE | FS1018-HBC-XX-XX-L-X-0005 Master Programme | FS1018-HBC-XX-XX-L-X-0005
FS1018-HBC-XX-XX-L-X-0006 | Work Package Procurement Plan | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-L-X-0006 Work Package Procurement Plan | FS1018-HBC-XX-XX-L-X-0006
FS1018-HBC-XX-XX-L-X-0006 | Work Package Procurement Plan | P02 | Completed | 2023-10-11 | Client / Contractor / BIM Review | A3 - Accepted | 2023-10-17 |  | TRUE | FS1018-HBC-XX-XX-L-X-0006 Work Package Procurement Plan | FS1018-HBC-XX-XX-L-X-0006
FS1018-HBC-XX-XX-L-X-0006 | Works Package Procurement Programme | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HBC-XX-XX-L-X-0006 Works Package Procurement Programme | FS1018-HBC-XX-XX-L-X-0006
FS1018-HBC-XX-XX-L-X-0007 | Risk Register | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2023-09-21 | We would expect to see risks for: Local incinerator and how this could impact on the design Objections to the planning application from locals or Cambridgeshire, or others Delay to securing the land from the existing PFI agreement | FALSE | FS1018-HBC-XX-XX-L-X-0007 Risk Register | FS1018-HBC-XX-XX-L-X-0007
FS1018-HBC-XX-XX-L-X-0007 | Risk Register | P02 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-HBC-XX-XX-L-X-0007 Risk Register | FS1018-HBC-XX-XX-L-X-0007
FS1018-HBC-XX-XX-L-X-0007 | Risk Register | P02 | In Progress | 2025-03-19 | Designer Response | Pending |  |  | TRUE | FS1018-HBC-XX-XX-L-X-0007 Risk Register | FS1018-HBC-XX-XX-L-X-0007
FS1018-HBC-XX-XX-L-X-0007 | Risk Register | P02 | In Progress | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-19 | 1. line 3 - existing drainage culvert - need to update this risk following IDB planning objection 2. Line 11 Sport England response has been received removing objection - needs updating 3. Planning delay - needs updating / re evaluating due to delays in statutory consultee responses and risk of not making April committee | TRUE | FS1018-HBC-XX-XX-L-X-0007 Risk Register | FS1018-HBC-XX-XX-L-X-0007
FS1018-HBC-XX-XX-L-X-0008 | PCSA | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-L-X-0008 PCSA | FS1018-HBC-XX-XX-L-X-0008
FS1018-HBC-XX-XX-L-X-0009 | PCSA Milestone Schedule | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-L-X-0009 PCSA Milestone Schedule | FS1018-HBC-XX-XX-L-X-0009
FS1018-HBC-XX-XX-L-X-0010 | PCSA Certificate Of Completion | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-L-X-0010 PCSA Certificate Of Completion | FS1018-HBC-XX-XX-L-X-0010
FS1018-HBC-XX-XX-L-X-0011 | Cashflow Forecast | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-L-X-0011 Cashflow Forecast | FS1018-HBC-XX-XX-L-X-0011
FS1018-HBC-XX-XX-L-X-0012 | Framewok Pricing Schedule | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | C - Rejected | 2023-09-21 | Separate review meetings ongoing. | FALSE | FS1018-HBC-XX-XX-L-X-0012 Framewok Pricing Schedule | FS1018-HBC-XX-XX-L-X-0012
FS1018-HBC-XX-XX-L-X-0013 | KPI Key Performance Indicator | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-L-X-0013 KPI Key Performance Indicator | FS1018-HBC-XX-XX-L-X-0013
FS1018-HBC-XX-XX-L-X-0013 | DFE KPIs | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HBC-XX-XX-L-X-0013 DFE KPIs | FS1018-HBC-XX-XX-L-X-0013
FS1018-HBC-XX-XX-L-X-0014 | Supplier Directory CV | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | C - Rejected | 2023-09-21 | This document needs to provide proposed sub-contractors for each package of work, typically three per package. | FALSE | FS1018-HBC-XX-XX-L-X-0014 Supplier Directory CV | FS1018-HBC-XX-XX-L-X-0014
FS1018-HBC-XX-XX-L-X-0014 | Supplier Directory CV | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-L-X-0014 Supplier Directory CV | FS1018-HBC-XX-XX-L-X-0014
FS1018-HBC-XX-XX-L-X-0015 | Supplier Directory Organisation Chart | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | C - Rejected | 2023-09-21 | This needs to focus more on the management of the different sub-contractors, not so much the design and DfE teams. | FALSE | FS1018-HBC-XX-XX-L-X-0015 Supplier Directory Organisation Chart | FS1018-HBC-XX-XX-L-X-0015
FS1018-HBC-XX-XX-L-X-0016 | Handover Training Plan | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-L-X-0016 Handover Training Plan | FS1018-HBC-XX-XX-L-X-0016
FS1018-HBC-XX-XX-L-X-0016 | Handover Training Plan | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HBC-XX-XX-L-X-0016 Handover Training Plan | FS1018-HBC-XX-XX-L-X-0016
FS1018-HBC-XX-XX-L-X-0017 | Supplier Chain Directory | P01 | Completed | 2023-10-11 | Client / Contractor / BIM Review | A3 - Accepted | 2023-10-17 |  | FALSE | FS1018-HBC-XX-XX-L-X-0017 Supplier Chain Directory | FS1018-HBC-XX-XX-L-X-0017
FS1018-HBC-XX-XX-L-X-0018 | HB Social Value KPIs | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HBC-XX-XX-L-X-0018 HB Social Value KPIs | FS1018-HBC-XX-XX-L-X-0018
FS1018-HBC-XX-XX-L-X-0019 | Site Organisation Chart | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-L-X-0019 Site Organisation Chart | FS1018-HBC-XX-XX-L-X-0019
FS1018-HBC-XX-XX-L-X-0020 | Commissioning Programme | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-L-X-0020 Commissioning Programme | FS1018-HBC-XX-XX-L-X-0020
FS1018-HBC-XX-XX-L-X-1001 | Quality Management Plan | P01 | Completed | 2023-09-06 | Sustainability Review | A3 - Accepted | 2023-09-25 |  | FALSE | FS1018-HBC-XX-XX-L-X-1001 Quality Management Plan | FS1018-HBC-XX-XX-L-X-1001
FS1018-HBC-XX-XX-L-X-1001 | Quality Management Plan | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HBC-XX-XX-L-X-1001 Quality Management Plan | FS1018-HBC-XX-XX-L-X-1001
FS1018-HBC-XX-XX-L-X-1002 | Sustainable Estate Strategy | P02 | Completed | 2023-09-06 | Sustainability Review | A3 - Accepted | 2023-10-02 |  | TRUE | FS1018-HBC-XX-XX-L-X-1002 Sustainable Estate Strategy | FS1018-HBC-XX-XX-L-X-1002
FS1018-HBC-XX-XX-L-X-1002 | Sustainable Estate Strategy | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-L-X-1002 Sustainable Estate Strategy | FS1018-HBC-XX-XX-L-X-1002
FS1018-HBC-XX-XX-L-X-1003 | Lift Specification | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-10-02 |  | FALSE | FS1018-HBC-XX-XX-L-X-1003 Lift Specification | FS1018-HBC-XX-XX-L-X-1003
FS1018-HBC-XX-XX-L-X-1003 | Lift Specification | P01 | In Progress | 2025-03-13 | DFE Review | C - Rejected | 2025-03-21 | This is a lift companies sale literature (which is non compliant for a new lift going into a new build building) and is not a lift specification as WSP VT would expect. Front page of document says 29 pages and 12 are submitted. Please provide full lift specification for review. WSP VT can not offer comment as document is incomplete | FALSE | FS1018-HBC-XX-XX-L-X-1003 Lift Specification | FS1018-HBC-XX-XX-L-X-1003
FS1018-HBC-XX-XX-L-X-1003 | Lift Specification | P01 | In Progress | 2025-03-21 | Designer Response | Pending |  |  | FALSE | FS1018-HBC-XX-XX-L-X-1003 Lift Specification | FS1018-HBC-XX-XX-L-X-1003
FS1018-HBC-XX-XX-L-X-1004 | Project Execution Plan | P01 | Completed | 2023-09-21 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-25 |  | FALSE | FS1018-HBC-XX-XX-L-X-1004 Project Execution Plan | FS1018-HBC-XX-XX-L-X-1004
FS1018-HBC-XX-XX-L-X-1004 | Project Execution Plan | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HBC-XX-XX-L-X-1004 Project Execution Plan | FS1018-HBC-XX-XX-L-X-1004
FS1018-HBC-XX-XX-L-X-2003 | HB Workflow Comment Tracker | P01 | Completed | 2023-10-11 | Client / Contractor / BIM Review | A3 - Accepted | 2023-10-17 |  | FALSE | FS1018-HBC-XX-XX-L-X-2003 HB Workflow Comment Tracker | FS1018-HBC-XX-XX-L-X-2003
FS1018-HBC-XX-XX-L-X-3000 | Derogations Schedule | P04 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-HBC-XX-XX-L-X-3000 Derogations Schedule | FS1018-HBC-XX-XX-L-X-3000
FS1018-HBC-XX-XX-L-X-3000 | Derogations Schedule | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-L-X-3000 Derogations Schedule | FS1018-HBC-XX-XX-L-X-3000
FS1018-HBC-XX-XX-L-X-4000 | Planning Condition Tracker | P01 | In Progress | 2025-03-13 | DFE Review | C - Rejected | 2025-03-21 | rejected Pending conclusion of the planning submission | FALSE | FS1018-HBC-XX-XX-L-X-4000 Planning Condition Tracker | FS1018-HBC-XX-XX-L-X-4000
FS1018-HBC-XX-XX-L-X-4000 | Planning Condition Tracker | P01 | In Progress | 2025-03-21 | Designer Response | Pending |  |  | FALSE | FS1018-HBC-XX-XX-L-X-4000 Planning Condition Tracker | FS1018-HBC-XX-XX-L-X-4000
FS1018-HBC-XX-XX-T-R-0001 | CDE Guide - Aconex | P01 | Completed | 2023-08-30 | TEST Review | A - Approved | 2023-09-25 | Test | FALSE | FS1018-HBC-XX-XX-T-R-0001 CDE Guide - Aconex | FS1018-HBC-XX-XX-T-R-0001
FS1018-HBC-XX-XX-T-X-0001 | Construction Phasing Plan | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2023-09-21 | Refer to mark-up. | FALSE | FS1018-HBC-XX-XX-T-X-0001 Construction Phasing Plan | FS1018-HBC-XX-XX-T-X-0001
FS1018-HBC-XX-XX-T-X-0001 | Construction Phasing Plan | P02 | Completed | 2023-10-11 | Client / Contractor / BIM Review | A3 - Accepted | 2023-10-17 |  | TRUE | FS1018-HBC-XX-XX-T-X-0001 Construction Phasing Plan | FS1018-HBC-XX-XX-T-X-0001
FS1018-HBC-XX-XX-T-X-0001 | Construction Phasing Plan | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0001 Construction Phasing Plan | FS1018-HBC-XX-XX-T-X-0001
FS1018-HBC-XX-XX-T-X-0017 | CEM1 Meeting Minutes | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-T-X-0017 CEM1 Meeting Minutes | FS1018-HBC-XX-XX-T-X-0017
FS1018-HBC-XX-XX-T-X-0018 | CEM2 Meeting Minutes | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-T-X-0018 CEM2 Meeting Minutes | FS1018-HBC-XX-XX-T-X-0018
FS1018-HBC-XX-XX-T-X-0019 | CEM3 Meeting Minutes | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-T-X-0019 CEM3 Meeting Minutes | FS1018-HBC-XX-XX-T-X-0019
FS1018-HBC-XX-XX-T-X-0020 | CEM4 Meeting Minutes | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-T-X-0020 CEM4 Meeting Minutes | FS1018-HBC-XX-XX-T-X-0020
FS1018-HBC-XX-XX-T-X-0021 | CEM5 Meeting Minutes | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-T-X-0021 CEM5 Meeting Minutes | FS1018-HBC-XX-XX-T-X-0021
FS1018-HBC-XX-XX-T-X-0022 | CEM6 Meeting Minutes | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-T-X-0022 CEM6 Meeting Minutes | FS1018-HBC-XX-XX-T-X-0022
FS1018-HBC-XX-XX-T-X-0023 | ICT Meeting Minutes | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-HBC-XX-XX-T-X-0023 ICT Meeting Minutes | FS1018-HBC-XX-XX-T-X-0023
FS1018-HBC-XX-XX-T-X-0024 | CEM7 Meeting Minutes | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0024 CEM7 Meeting Minutes | FS1018-HBC-XX-XX-T-X-0024
FS1018-HBC-XX-XX-T-X-0025 | CEM8 Meeting Minutes | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0025 CEM8 Meeting Minutes | FS1018-HBC-XX-XX-T-X-0025
FS1018-HBC-XX-XX-T-X-0026 | CEM8-9A Meeting Minutes | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0026 CEM8-9A Meeting Minutes | FS1018-HBC-XX-XX-T-X-0026
FS1018-HBC-XX-XX-T-X-0027 | CEM09 Meeting Minutes | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0027 CEM09 Meeting Minutes | FS1018-HBC-XX-XX-T-X-0027
FS1018-HBC-XX-XX-T-X-0028 | CEM10 Meeting Minutes | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0028 CEM10 Meeting Minutes | FS1018-HBC-XX-XX-T-X-0028
FS1018-HBC-XX-XX-T-X-0029 | CEM10A Meeting Minutes | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0029 CEM10A Meeting Minutes | FS1018-HBC-XX-XX-T-X-0029
FS1018-HBC-XX-XX-T-X-0030 | CEM11 Meeting Minutes | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0030 CEM11 Meeting Minutes | FS1018-HBC-XX-XX-T-X-0030
FS1018-HBC-XX-XX-T-X-0031 | CEM12 Meeting Minutes | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0031 CEM12 Meeting Minutes | FS1018-HBC-XX-XX-T-X-0031
FS1018-HBC-XX-XX-T-X-0033 | CEM07 Agenda | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0033 CEM07 Agenda | FS1018-HBC-XX-XX-T-X-0033
FS1018-HBC-XX-XX-T-X-0034 | CEM08 Agenda | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0034 CEM08 Agenda | FS1018-HBC-XX-XX-T-X-0034
FS1018-HBC-XX-XX-T-X-0035 | CEM09 Agenda | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0035 CEM09 Agenda | FS1018-HBC-XX-XX-T-X-0035
FS1018-HBC-XX-XX-T-X-0036 | CEM08-9A Agenda | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0036 CEM08-9A Agenda | FS1018-HBC-XX-XX-T-X-0036
FS1018-HBC-XX-XX-T-X-0037 | CEM10 Meeting Agenda | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0037 CEM10 Meeting Agenda | FS1018-HBC-XX-XX-T-X-0037
FS1018-HBC-XX-XX-T-X-0038 | CEM10A Agenda | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0038 CEM10A Agenda | FS1018-HBC-XX-XX-T-X-0038
FS1018-HBC-XX-XX-T-X-0039 | CEM11 Agenda | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0039 CEM11 Agenda | FS1018-HBC-XX-XX-T-X-0039
FS1018-HBC-XX-XX-T-X-0040 | CEM12 Agenda | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0040 CEM12 Agenda | FS1018-HBC-XX-XX-T-X-0040
FS1018-HBC-XX-XX-T-X-0042 | Employer Necessary Consents | P01 | In Progress | 2025-03-13 | DFE Review | B - Partially Accepted with Comments | 2025-03-21 | ENCs are unclear at present as the land transaction has yet to be completed with CCC and also the planning approval has yet to be concluded which may result in s278 or other legal agreements. As these processes are concluded ENCs may arise and this document will need to be updated | FALSE | FS1018-HBC-XX-XX-T-X-0042 Employer Necessary Consents | FS1018-HBC-XX-XX-T-X-0042
FS1018-HBC-XX-XX-T-X-0042 | Employer Necessary Consents | P01 | In Progress | 2025-03-21 | Designer Response | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0042 Employer Necessary Consents | FS1018-HBC-XX-XX-T-X-0042
FS1018-HBC-XX-XX-T-X-0043 | Construction Method Statement | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0043 Construction Method Statement | FS1018-HBC-XX-XX-T-X-0043
FS1018-HBC-XX-XX-T-X-0044 | Handover Strategy | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0044 Handover Strategy | FS1018-HBC-XX-XX-T-X-0044
FS1018-HBC-XX-XX-T-X-0045 | Thermal Assessment | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HBC-XX-XX-T-X-0045 Thermal Assessment | FS1018-HBC-XX-XX-T-X-0045
FS1018-HEX-XX-00-T-H-0002 | Framework School Travel Plan | P01 | Completed | 2024-08-08 | Civil Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-HEX-XX-00-T-H-0002 Framework School Travel Plan | FS1018-HEX-XX-00-T-H-0002
FS1018-HEX-XX-XX-T-C-0001 | Flood Risk Assessment | P02 | Completed | 2024-08-28 | Civil Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-HEX-XX-XX-T-C-0001 Flood Risk Assessment | FS1018-HEX-XX-XX-T-C-0001
FS1018-HEX-XX-XX-T-C-0002 | SuDS Operations and Maintenance Manual | P01 | Completed | 2024-08-08 | Civil Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-HEX-XX-XX-T-C-0002 SuDS Operations and Maintenance Manual | FS1018-HEX-XX-XX-T-C-0002
FS1018-HEX-XX-XX-T-C-0004 | CIVIL DESIGN PHILOSOPHY | P01 | Completed | 2023-09-06 | Civil Review | A3 - Accepted | 2023-09-26 |  | FALSE | FS1018-HEX-XX-XX-T-C-0004 CIVIL DESIGN PHILOSOPHY | FS1018-HEX-XX-XX-T-C-0004
FS1018-HEX-XX-XX-T-C-0004 | Civil Design Philosophy | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HEX-XX-XX-T-C-0004 Civil Design Philosophy | FS1018-HEX-XX-XX-T-C-0004
FS1018-HEX-XX-XX-T-C-0010 | Risk Register | P01 | Completed | 2023-09-06 | CDM Review | C - Rejected | 2023-09-25 | KB Comments:  have these been provided to the Principal Designer for comment?  Have the Designers been provided with Pre-Construction Information to inform their Design and DRA’s?  Is the Principal Designer satisfied that the Designers have used the general principles of prevention to eliminate/reduce risk in their design?  Confusing as some of the potential hazards identified aren’t “hazards” e.g. Additional Site Investigation;  Have the Designers been provided with Pre-Construction Information to inform their Design and DRA’s?  What actions has been taken by Design at Stage 3 level to eliminate/reduce risk  Identify appropriate information from the design that the Principal Designer will need to include in the H&S file for completion. | FALSE | FS1018-HEX-XX-XX-T-C-0010 Risk Register | FS1018-HEX-XX-XX-T-C-0010
FS1018-HEX-XX-XX-T-C-0010 | Risk Register | P02 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-HEX-XX-XX-T-C-0010 Risk Register | FS1018-HEX-XX-XX-T-C-0010
FS1018-HEX-XX-XX-T-C-0010 | Risk Register | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-XX-XX-T-C-0010 Risk Register | FS1018-HEX-XX-XX-T-C-0010
FS1018-HEX-XX-XX-T-C-0011 | Drainage Specification | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-XX-XX-T-C-0011 Drainage Specification | FS1018-HEX-XX-XX-T-C-0011
FS1018-HEX-XX-XX-T-C-0012 | Earthworks Specification | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-XX-XX-T-C-0012 Earthworks Specification | FS1018-HEX-XX-XX-T-C-0012
FS1018-HEX-XX-XX-T-H-0001 | Transport Assessment | P01 | Completed | 2024-08-08 | Civil Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-HEX-XX-XX-T-H-0001 Transport Assessment | FS1018-HEX-XX-XX-T-H-0001
FS1018-HEX-XX-XX-T-H-0001 | Transport Assessment | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HEX-XX-XX-T-H-0001 Transport Assessment | FS1018-HEX-XX-XX-T-H-0001
FS1018-HEX-XX-XX-T-S-0003 | Structural Design Philosophy | P01 | Completed | 2023-09-06 | Structural Review | B3 - Partially Accepted with Comments | 2023-09-25 | MT Comments: PV loading on roof mentioned but no description how fixing is achieved or lefection tollerance for cells | FALSE | FS1018-HEX-XX-XX-T-S-0003 Structural Design Philosophy | FS1018-HEX-XX-XX-T-S-0003
FS1018-HEX-XX-XX-T-S-0003 | Structural Design Philosophy | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HEX-XX-XX-T-S-0003 Structural Design Philosophy | FS1018-HEX-XX-XX-T-S-0003
FS1018-HEX-XX-XX-T-S-0004 | Concrete Specification | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-XX-XX-T-S-0004 Concrete Specification | FS1018-HEX-XX-XX-T-S-0004
FS1018-HEX-XX-XX-T-S-0005 | Steelwork Specification | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-XX-XX-T-S-0005 Steelwork Specification | FS1018-HEX-XX-XX-T-S-0005
FS1018-HEX-XX-XX-T-S-0006 | Piling Specification | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-XX-XX-T-S-0006 Piling Specification | FS1018-HEX-XX-XX-T-S-0006
FS1018-HEX-ZZ-00-D-S-0101 | FOUNDATION LAYOUT | P02 | Completed | 2023-09-06 | Structural Review | B3 - Partially Accepted with Comments | 2023-09-25 | MT Comments: What is the purpose of the internal slab thickenings over the GB'S? | TRUE | FS1018-HEX-ZZ-00-D-S-0101 FOUNDATION LAYOUT | FS1018-HEX-ZZ-00-D-S-0101
FS1018-HEX-ZZ-00-D-S-0101 | Foundation Layout | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-00-D-S-0101 Foundation Layout | FS1018-HEX-ZZ-00-D-S-0101
FS1018-HEX-ZZ-00-D-S-0102 | Foundation Details | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-00-D-S-0102 Foundation Details | FS1018-HEX-ZZ-00-D-S-0102
FS1018-HEX-ZZ-00-D-S-0200 | GROUND FLOOR COLUMN PLAN | P02 | Completed | 2023-09-06 | Structural Review | A3 - Accepted | 2023-09-25 |  | TRUE | FS1018-HEX-ZZ-00-D-S-0200 GROUND FLOOR COLUMN PLAN | FS1018-HEX-ZZ-00-D-S-0200
FS1018-HEX-ZZ-00-D-S-0200 | Ground Floor Column Plan | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-00-D-S-0200 Ground Floor Column Plan | FS1018-HEX-ZZ-00-D-S-0200
FS1018-HEX-ZZ-01-D-S-0201 | FIRST FLOOR STEELWORK LAYOUT | P02 | Completed | 2023-09-06 | Structural Review | A3 - Accepted | 2023-09-25 |  | TRUE | FS1018-HEX-ZZ-01-D-S-0201 FIRST FLOOR STEELWORK LAYOUT | FS1018-HEX-ZZ-01-D-S-0201
FS1018-HEX-ZZ-01-D-S-0201 | First Floor Steelwork Layout | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-01-D-S-0201 First Floor Steelwork Layout | FS1018-HEX-ZZ-01-D-S-0201
FS1018-HEX-ZZ-02-D-S-0202 | SECOND FLOOR STEELWORK LAYOUT | P02 | Completed | 2023-09-06 | Structural Review | A3 - Accepted | 2023-09-25 |  | TRUE | FS1018-HEX-ZZ-02-D-S-0202 SECOND FLOOR STEELWORK LAYOUT | FS1018-HEX-ZZ-02-D-S-0202
FS1018-HEX-ZZ-02-D-S-0202 | Second Floor Steelwork Layout | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-02-D-S-0202 Second Floor Steelwork Layout | FS1018-HEX-ZZ-02-D-S-0202
FS1018-HEX-ZZ-RF-D-S-0203 | MAIN ROOF STEELWORK LAYOUT | P02 | Completed | 2023-09-06 | Structural Review | A3 - Accepted | 2023-09-25 |  | TRUE | FS1018-HEX-ZZ-RF-D-S-0203 MAIN ROOF STEELWORK LAYOUT | FS1018-HEX-ZZ-RF-D-S-0203
FS1018-HEX-ZZ-RF-D-S-0203 | Main Roof Steelwork Layout | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-RF-D-S-0203 Main Roof Steelwork Layout | FS1018-HEX-ZZ-RF-D-S-0203
FS1018-HEX-ZZ-RF-D-S-0204 | HALL ROOF STEELWORK LAYOUTS | P02 | Completed | 2023-09-06 | Structural Review | A3 - Accepted | 2023-09-25 |  | TRUE | FS1018-HEX-ZZ-RF-D-S-0204 HALL ROOF STEELWORK LAYOUTS | FS1018-HEX-ZZ-RF-D-S-0204
FS1018-HEX-ZZ-RF-D-S-0204 | Hall Roof Steelwork Layouts | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-RF-D-S-0204 Hall Roof Steelwork Layouts | FS1018-HEX-ZZ-RF-D-S-0204
FS1018-HEX-ZZ-RF-D-S-0205 | PARAPET STEELWORK LAYOUT | P02 | Completed | 2023-09-06 | Structural Review | A3 - Accepted | 2023-09-25 |  | TRUE | FS1018-HEX-ZZ-RF-D-S-0205 PARAPET STEELWORK LAYOUT | FS1018-HEX-ZZ-RF-D-S-0205
FS1018-HEX-ZZ-RF-D-S-0205 | Parapet Steelwork Layout | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-RF-D-S-0205 Parapet Steelwork Layout | FS1018-HEX-ZZ-RF-D-S-0205
FS1018-HEX-ZZ-XX-D-S-0001 | PROJECT NOTES | P01 | Completed | 2023-09-06 | Structural Review | B3 - Partially Accepted with Comments | 2023-09-25 | MT Comments: uplift seams high on all piles will this exist? | FALSE | FS1018-HEX-ZZ-XX-D-S-0001 PROJECT NOTES | FS1018-HEX-ZZ-XX-D-S-0001
FS1018-HEX-ZZ-XX-D-S-0001 | Project Notes | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HEX-ZZ-XX-D-S-0001 Project Notes | FS1018-HEX-ZZ-XX-D-S-0001
FS1018-HEX-ZZ-ZZ-D-C-5200 | SURFACE WATER DRAINAGE LAYOUT SHEET 1 | P01 | Completed | 2023-09-06 | Civil Review | A3 - Accepted | 2023-09-26 | Flow arrows on pipelines would make it easier to read the drawing and understand the philosophy | FALSE | FS1018-HEX-ZZ-ZZ-D-C-5200 SURFACE WATER DRAINAGE LAYOUT SHEET 1 | FS1018-HEX-ZZ-ZZ-D-C-5200
FS1018-HEX-ZZ-ZZ-D-C-5200 | Surface Water Drainage Layout Sheet 1 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-D-C-5200 Surface Water Drainage Layout Sheet 1 | FS1018-HEX-ZZ-ZZ-D-C-5200
FS1018-HEX-ZZ-ZZ-D-C-5201 | SURFACE WATER DRAINAGE LAYOUT SHEET 2 | P01 | Completed | 2023-09-06 | Civil Review | A3 - Accepted | 2023-09-26 | Flow arrows on pipelines would make it easier to read the drawing and understand the philosophy | FALSE | FS1018-HEX-ZZ-ZZ-D-C-5201 SURFACE WATER DRAINAGE LAYOUT SHEET 2 | FS1018-HEX-ZZ-ZZ-D-C-5201
FS1018-HEX-ZZ-ZZ-D-C-5201 | Surface Water Drainage Layout Sheet 2 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-D-C-5201 Surface Water Drainage Layout Sheet 2 | FS1018-HEX-ZZ-ZZ-D-C-5201
FS1018-HEX-ZZ-ZZ-D-C-5205 | FOUL WATER DRAINAGE LAYOUT | P01 | Completed | 2023-09-06 | Civil Review | C - Rejected | 2023-09-26 | Foul network gradients are very slack, 1:100-1:150. The connection to the sewer in Weasenham Lane should be investigated. | FALSE | FS1018-HEX-ZZ-ZZ-D-C-5205 FOUL WATER DRAINAGE LAYOUT | FS1018-HEX-ZZ-ZZ-D-C-5205
FS1018-HEX-ZZ-ZZ-D-C-5205 | Foul Water Drainage Layout | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-D-C-5205 Foul Water Drainage Layout | FS1018-HEX-ZZ-ZZ-D-C-5205
FS1018-HEX-ZZ-ZZ-D-C-5210 | DRAINAGE CONSTRUCTION DETAILS SHEET 1 | P01 | Completed | 2023-10-03 | Civil Review | A3 - Accepted | 2023-10-09 |  | FALSE | FS1018-HEX-ZZ-ZZ-D-C-5210 DRAINAGE CONSTRUCTION DETAILS SHEET 1 | FS1018-HEX-ZZ-ZZ-D-C-5210
FS1018-HEX-ZZ-ZZ-D-C-5210 | Drainage Construction Details Sheet 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-D-C-5210 Drainage Construction Details Sheet 1 | FS1018-HEX-ZZ-ZZ-D-C-5210
FS1018-HEX-ZZ-ZZ-D-C-5211 | DRAINAGE CONSTRUCTION DETAILS SHEET 2 | P01 | Completed | 2023-10-03 | Civil Review | A3 - Accepted | 2023-10-09 |  | FALSE | FS1018-HEX-ZZ-ZZ-D-C-5211 DRAINAGE CONSTRUCTION DETAILS SHEET 2 | FS1018-HEX-ZZ-ZZ-D-C-5211
FS1018-HEX-ZZ-ZZ-D-C-5211 | Drainage Construction Details Sheet 2 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-D-C-5211 Drainage Construction Details Sheet 2 | FS1018-HEX-ZZ-ZZ-D-C-5211
FS1018-HEX-ZZ-ZZ-D-C-9000 | Earthworks Analysis | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-D-C-9000 Earthworks Analysis | FS1018-HEX-ZZ-ZZ-D-C-9000
FS1018-HEX-ZZ-ZZ-D-C-9020 | EXTERNAL WORKS LAYOUT SHEET 1 | P01 | Completed | 2023-09-06 | Civil Review | A3 - Accepted | 2023-09-26 |  | FALSE | FS1018-HEX-ZZ-ZZ-D-C-9020 EXTERNAL WORKS LAYOUT SHEET 1 | FS1018-HEX-ZZ-ZZ-D-C-9020
FS1018-HEX-ZZ-ZZ-D-C-9020 | External Works Layout Sheet 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HEX-ZZ-ZZ-D-C-9020 External Works Layout Sheet 1 | FS1018-HEX-ZZ-ZZ-D-C-9020
FS1018-HEX-ZZ-ZZ-D-C-9021 | EXTERNAL WORKS LAYOUT SHEET 2 | P01 | Completed | 2023-09-06 | Civil Review | A3 - Accepted | 2023-09-26 |  | FALSE | FS1018-HEX-ZZ-ZZ-D-C-9021 EXTERNAL WORKS LAYOUT SHEET 2 | FS1018-HEX-ZZ-ZZ-D-C-9021
FS1018-HEX-ZZ-ZZ-D-C-9021 | External Works Layout Sheet 2 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HEX-ZZ-ZZ-D-C-9021 External Works Layout Sheet 2 | FS1018-HEX-ZZ-ZZ-D-C-9021
FS1018-HEX-ZZ-ZZ-D-C-9025 | EXTERNAL WORKS CONSTRUCTION DETAILS | P01 | Completed | 2023-09-06 | Civil Review | A3 - Accepted | 2023-09-26 |  | FALSE | FS1018-HEX-ZZ-ZZ-D-C-9025 EXTERNAL WORKS CONSTRUCTION DETAILS | FS1018-HEX-ZZ-ZZ-D-C-9025
FS1018-HEX-ZZ-ZZ-D-C-9025 | External Works Construction Details | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HEX-ZZ-ZZ-D-C-9025 External Works Construction Details | FS1018-HEX-ZZ-ZZ-D-C-9025
FS1018-HEX-ZZ-ZZ-D-S-0501 | BUILDING ELEVATIONS SHEET 01 OF 02 | P02 | Completed | 2023-09-06 | Structural Review | B3 - Partially Accepted with Comments | 2023-09-25 | MT/IH Comments: Add drawing showing 3D views of the building frame including the the bracing system | TRUE | FS1018-HEX-ZZ-ZZ-D-S-0501 BUILDING ELEVATIONS SHEET 01 OF 02 | FS1018-HEX-ZZ-ZZ-D-S-0501
FS1018-HEX-ZZ-ZZ-D-S-0501 | Building Elevations Sheet 01 Of 02 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-D-S-0501 Building Elevations Sheet 01 Of 02 | FS1018-HEX-ZZ-ZZ-D-S-0501
FS1018-HEX-ZZ-ZZ-D-S-0502 | BUILDING ELEVATIONS SHEET 02 OF 02 | P02 | Completed | 2023-09-06 | Structural Review | B3 - Partially Accepted with Comments | 2023-09-25 | MT/IH Comments: Add drawing showing 3D views of the building frame including the the bracing system | TRUE | FS1018-HEX-ZZ-ZZ-D-S-0502 BUILDING ELEVATIONS SHEET 02 OF 02 | FS1018-HEX-ZZ-ZZ-D-S-0502
FS1018-HEX-ZZ-ZZ-D-S-0502 | Building Elevations Sheet 02 Of 02 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-D-S-0502 Building Elevations Sheet 02 Of 02 | FS1018-HEX-ZZ-ZZ-D-S-0502
FS1018-HEX-ZZ-ZZ-D-S-0503 | BRACING ELEVATIONS | P02 | Completed | 2023-09-06 | Structural Review | B3 - Partially Accepted with Comments | 2023-09-25 | MT /IHComments: Add drawing showing 3D views of the building frame including the the bracing system | TRUE | FS1018-HEX-ZZ-ZZ-D-S-0503 BRACING ELEVATIONS | FS1018-HEX-ZZ-ZZ-D-S-0503
FS1018-HEX-ZZ-ZZ-D-S-0503 | Bracing Elevations | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-D-S-0503 Bracing Elevations | FS1018-HEX-ZZ-ZZ-D-S-0503
FS1018-HEX-ZZ-ZZ-D-S-0601 | BUILDING SECTIONS | P02 | Completed | 2023-09-06 | Structural Review | A3 - Accepted | 2023-09-25 |  | TRUE | FS1018-HEX-ZZ-ZZ-D-S-0601 BUILDING SECTIONS | FS1018-HEX-ZZ-ZZ-D-S-0601
FS1018-HEX-ZZ-ZZ-D-S-0601 | Building Sections | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-D-S-0601 Building Sections | FS1018-HEX-ZZ-ZZ-D-S-0601
FS1018-HEX-ZZ-ZZ-D-S-0602 | STRUCTURAL SECTIONS & DETAILS | P02 | Completed | 2023-09-06 | Structural Review | B3 - Partially Accepted with Comments | 2023-09-25 | MT/IH Comments: Confirm the detail showing cranked rebar welded on the top flange of the UC Beam is adequate and in the zone the shear plane of the UC section- the rebar appears high and cracked further back from the shear plane. Tie beam can also be slim flor by being grounted in parralel to PCC units | TRUE | FS1018-HEX-ZZ-ZZ-D-S-0602 STRUCTURAL SECTIONS & DETAILS | FS1018-HEX-ZZ-ZZ-D-S-0602
FS1018-HEX-ZZ-ZZ-D-S-0602 | Structural Sections and Details | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-D-S-0602 Structural Sections and Details | FS1018-HEX-ZZ-ZZ-D-S-0602
FS1018-HEX-ZZ-ZZ-D-S-0801 | 3D Views | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-D-S-0801 3D Views | FS1018-HEX-ZZ-ZZ-D-S-0801
FS1018-HEX-ZZ-ZZ-M-C-0001 | Native Civil Model | P01 | Completed | 2023-09-06 | Civil Review | A3 - Accepted | 2023-09-26 |  | FALSE | FS1018-HEX-ZZ-ZZ-M-C-0001 Native Civil Model | FS1018-HEX-ZZ-ZZ-M-C-0001
FS1018-HEX-ZZ-ZZ-M-C-0001 | Native Civil Model | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HEX-ZZ-ZZ-M-C-0001 Native Civil Model | FS1018-HEX-ZZ-ZZ-M-C-0001
FS1018-HEX-ZZ-ZZ-M-C-0002 | IFC SPF Civil Model | P01 | Completed | 2023-09-06 | Civil Review | A3 - Accepted | 2023-09-26 |  | FALSE | FS1018-HEX-ZZ-ZZ-M-C-0002 IFC SPF Civil Model | FS1018-HEX-ZZ-ZZ-M-C-0002
FS1018-HEX-ZZ-ZZ-M-C-0002 | IFC SPF Civil Model | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HEX-ZZ-ZZ-M-C-0002 IFC SPF Civil Model | FS1018-HEX-ZZ-ZZ-M-C-0002
FS1018-HEX-ZZ-ZZ-M-C-0003 | Navisowrks Civil Model | P01 | Completed | 2023-09-06 | Civil Review | B3 - Partially Accepted with Comments | 2023-09-26 | Status on Flysheet is at S1 Work in Progress and revision 1. Should be updated to match requirements set out in Project Information Standard. File name reference on splash screen does not match file name. Unnecessary site floor plan view. | FALSE | FS1018-HEX-ZZ-ZZ-M-C-0003 Navisowrks Civil Model | FS1018-HEX-ZZ-ZZ-M-C-0003
FS1018-HEX-ZZ-ZZ-M-C-0003 | Navisworks Civil Model | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HEX-ZZ-ZZ-M-C-0003 Navisworks Civil Model | FS1018-HEX-ZZ-ZZ-M-C-0003
FS1018-HEX-ZZ-ZZ-M-S-0001 | Native Structural Model | P03 | Completed | 2023-09-06 | Structural Review | B3 - Partially Accepted with Comments | 2023-09-25 | Model reference on flysheet not aligned to file name. | FALSE | FS1018-HEX-ZZ-ZZ-M-S-0001 Native Structural Model | FS1018-HEX-ZZ-ZZ-M-S-0001
FS1018-HEX-ZZ-ZZ-M-S-0001 | Native Structural Model | P04 | Completed | 2024-08-29 | Structural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-HEX-ZZ-ZZ-M-S-0001 Native Structural Model | FS1018-HEX-ZZ-ZZ-M-S-0001
FS1018-HEX-ZZ-ZZ-M-S-0001 | Native Structural Model | P09 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-M-S-0001 Native Structural Model | FS1018-HEX-ZZ-ZZ-M-S-0001
FS1018-HEX-ZZ-ZZ-M-S-0002 | IFC SPF Structural Model | P03 | Completed | 2023-09-06 | Structural Review | B3 - Partially Accepted with Comments | 2023-09-25 | COBie & IFC Issues evident. 783 elements have USERDEFINED or NOTDEFINED predefined type and 392 elements with empty field. Object assignment to correct levels requires review (in level 00 there are objects that should be assigned to other levels). | FALSE | FS1018-HEX-ZZ-ZZ-M-S-0002 IFC SPF Structural Model | FS1018-HEX-ZZ-ZZ-M-S-0002
FS1018-HEX-ZZ-ZZ-M-S-0002 | IFC SPF Structural Model | P04 | Completed | 2024-08-29 | Structural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-HEX-ZZ-ZZ-M-S-0002 IFC SPF Structural Model | FS1018-HEX-ZZ-ZZ-M-S-0002
FS1018-HEX-ZZ-ZZ-M-S-0002 | IFC SPF Structural Model | P09 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-M-S-0002 IFC SPF Structural Model | FS1018-HEX-ZZ-ZZ-M-S-0002
FS1018-HEX-ZZ-ZZ-M-S-0003 | Navis Structural Model | P03 | Completed | 2023-09-06 | Structural Review | B3 - Partially Accepted with Comments | 2023-09-25 | Objects not assigned to correct levels - requires review (eg. level 00 there are objects that should be assigned to other levels), naming of levels should align to Project Information Standard. | FALSE | FS1018-HEX-ZZ-ZZ-M-S-0003 Navis Structural Model | FS1018-HEX-ZZ-ZZ-M-S-0003
FS1018-HEX-ZZ-ZZ-M-S-0003 | Navis Structural Model | P04 | Completed | 2024-08-29 | Structural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-HEX-ZZ-ZZ-M-S-0003 Navis Structural Model | FS1018-HEX-ZZ-ZZ-M-S-0003
FS1018-HEX-ZZ-ZZ-M-S-0003 | Navis Structural Model | P09 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-HEX-ZZ-ZZ-M-S-0003 Navis Structural Model | FS1018-HEX-ZZ-ZZ-M-S-0003
FS1018-HEX-ZZ-ZZ-T-C-0001 | GENERAL NOTES | P01 | Completed | 2023-09-06 | Civil Review | A3 - Accepted | 2023-09-26 |  | FALSE | FS1018-HEX-ZZ-ZZ-T-C-0001 GENERAL NOTES | FS1018-HEX-ZZ-ZZ-T-C-0001
FS1018-HEX-ZZ-ZZ-T-C-0001 | General Notes | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-HEX-ZZ-ZZ-T-C-0001 General Notes | FS1018-HEX-ZZ-ZZ-T-C-0001
FS1018-MAJ-XX-XX-L-X-0090 | DetailedResponsibilityMatrix | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | A3 - Accepted | 2023-09-25 |  | FALSE | FS1018-MAJ-XX-XX-L-X-0090 DetailedResponsibilityMatrix | FS1018-MAJ-XX-XX-L-X-0090
FS1018-MAJ-XX-XX-L-X-0090 | Detailed Responsibility Matrix | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-MAJ-XX-XX-L-X-0090 Detailed Responsibility Matrix | FS1018-MAJ-XX-XX-L-X-0090
FS1018-MAJ-XX-XX-L-X-8001 | AssetRegister | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | C - Rejected | 2023-09-25 | Asset Register only contains contact information for STR & CVL engineer, no architectural. No other Contact, No Facility, Floor, Space or Zone data. Architectural was submitted separately but should be included in this file. | FALSE | FS1018-MAJ-XX-XX-L-X-8001 AssetRegister | FS1018-MAJ-XX-XX-L-X-8001
FS1018-MAJ-XX-XX-L-X-8001 | Asset Register | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-MAJ-XX-XX-L-X-8001 Asset Register | FS1018-MAJ-XX-XX-L-X-8001
FS1018-MAJ-XX-XX-L-X-8002 | COBieQCReport | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | C - Rejected | 2023-09-25 | Rejected on the basis of quality of COBie data in the submission in the Federated Model and Asset Register. | FALSE | FS1018-MAJ-XX-XX-L-X-8002 COBieQCReport | FS1018-MAJ-XX-XX-L-X-8002
FS1018-MAJ-XX-XX-L-X-8002 | COBie QC Report | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-MAJ-XX-XX-L-X-8002 COBie QC Report | FS1018-MAJ-XX-XX-L-X-8002
FS1018-MAJ-XX-XX-T-X-0001 | BIM Execution Plan | P02 | Completed | 2023-09-06 | Client / Contractor / BIM Review | C - Rejected | 2023-09-25 | File is in WIP word format with WIP Comments from HBC contained within the file. Requires correcting all document refs - remnants of SRP1062 which is not this project. Project Directory incomplete. 5.5 CDE Configuration section is incomplete. 5.7 Security section is incomplete. 5.8 Federation Strategy incomplete. 7.5 Capability & Capacity references Willmott Dixon?. 8.1 Software Requirements references solibri/Navisworks for federation - but Federation strategy also mentions Dalux? 8.5 Coordinates - all tbc. 8.7 L.O.I Need - incomplete. 9.7 Role Codes - I is spare but has been used for Interior Architecture in the P.I.S. 10.2 Management of OBie section and 10.3 Asset Register are incomplete. 3.1 Project Details require review to align with Project Information Standard. 5.6 PM Uniclass Table Version for file metadata should be specified in BEP. 6.6 Clash management and resolution progress should detail clash detection identification process; issue management process, clash resolution workshops. 6.8 Native model files for each discipline should be identified in BEP to confirm software compatibility. 8.6 PM Uniclass Table Version for file metadata should be specified in BEP to align with Project Information Standard. 9.5 Level elevations should be confirmed in the BEP. | TRUE | FS1018-MAJ-XX-XX-T-X-0001 BIM Execution Plan | FS1018-MAJ-XX-XX-T-X-0001
FS1018-MAJ-XX-XX-T-X-0001 | BIM Execution Plan | P06 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-MAJ-XX-XX-T-X-0001 BIM Execution Plan | FS1018-MAJ-XX-XX-T-X-0001
FS1018-MAJ-XX-XX-T-X-1001 | InformationManagersReport | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2023-09-25 | Report footer block contains wrong document number. | FALSE | FS1018-MAJ-XX-XX-T-X-1001 InformationManagersReport | FS1018-MAJ-XX-XX-T-X-1001
FS1018-MAJ-XX-XX-T-X-1001 | Information Managers Report | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-MAJ-XX-XX-T-X-1001 Information Managers Report | FS1018-MAJ-XX-XX-T-X-1001
FS1018-MAJ-ZZ-ZZ-M-X-0001 | FederatedInformationModel | P01 | Completed | 2023-09-06 | Client / Contractor / BIM Review | B3 - Partially Accepted with Comments | 2023-09-25 | Model contains no classifications, COBie settings or checking rules to evidence checks. | FALSE | FS1018-MAJ-ZZ-ZZ-M-X-0001 FederatedInformationModel | FS1018-MAJ-ZZ-ZZ-M-X-0001
FS1018-MAJ-ZZ-ZZ-M-X-0001 | Federated Information Model | P06 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-MAJ-ZZ-ZZ-M-X-0001 Federated Information Model | FS1018-MAJ-ZZ-ZZ-M-X-0001
FS1018-OFR-XX-00-D-K-0001 | Fire Safety Mark | P01 | Completed | 2023-09-07 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawings. Significant strategy requirements from fire engineer have not been addressed in layouts. Layouts to be updated as a matter of priority. | FALSE | FS1018-OFR-XX-00-D-K-0001 Fire Safety Mark | FS1018-OFR-XX-00-D-K-0001
FS1018-OFR-XX-00-D-K-0001 | Fire Strategy Markup | P02 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-OFR-XX-00-D-K-0001 Fire Strategy Markup | FS1018-OFR-XX-00-D-K-0001
FS1018-OFR-XX-01-D-K-0001 | Fire Safety Mark | P01 | Completed | 2023-09-07 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawings. Significant strategy requirements from fire engineer have not been addressed in layouts. Layouts to be updated as a matter of priority. | FALSE | FS1018-OFR-XX-01-D-K-0001 Fire Safety Mark | FS1018-OFR-XX-01-D-K-0001
FS1018-OFR-XX-01-D-K-0001 | Fire Strategy Markup | P02 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-OFR-XX-01-D-K-0001 Fire Strategy Markup | FS1018-OFR-XX-01-D-K-0001
FS1018-OFR-XX-02-D-K-0001 | Fire Safety Mark | P01 | Completed | 2023-09-07 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawings. Significant strategy requirements from fire engineer have not been addressed in layouts. Layouts to be updated as a matter of priority. | FALSE | FS1018-OFR-XX-02-D-K-0001 Fire Safety Mark | FS1018-OFR-XX-02-D-K-0001
FS1018-OFR-XX-02-D-K-0001 | Fire Strategy Markup | P02 | Completed | 2024-09-06 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-OFR-XX-02-D-K-0001 Fire Strategy Markup | FS1018-OFR-XX-02-D-K-0001
FS1018-OFR-XX-RF-D-K-0001 | Fire Strategy Markup | P01 | Completed | 2024-09-06 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-OFR-XX-RF-D-K-0001 Fire Strategy Markup | FS1018-OFR-XX-RF-D-K-0001
FS1018-OFR-XX-XX-D-K-0001 | Fire Safety Mark | P01 | Completed | 2023-09-07 | Architectural Review | C - Rejected | 2023-09-21 | See comments on drawings. Significant strategy requirements from fire engineer have not been addressed in layouts. Layouts to be updated as a matter of priority. | FALSE | FS1018-OFR-XX-XX-D-K-0001 Fire Safety Mark | FS1018-OFR-XX-XX-D-K-0001
FS1018-OFR-XX-XX-D-K-0001 | Fire Strategy Markup | P02 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-OFR-XX-XX-D-K-0001 Fire Strategy Markup | FS1018-OFR-XX-XX-D-K-0001
FS1018-OFR-XX-ZZ-G-K-0001 | Fire Strategy Report | P01 | Completed | 2023-09-07 | Architectural Review | C - Rejected | 2023-09-21 | See comments on document. | FALSE | FS1018-OFR-XX-ZZ-G-K-0001 Fire Strategy Report | FS1018-OFR-XX-ZZ-G-K-0001
FS1018-OFR-XX-ZZ-G-K-0001 | Fire Strategy Report | P02 | Completed | 2024-09-06 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-OFR-XX-ZZ-G-K-0001 Fire Strategy Report | FS1018-OFR-XX-ZZ-G-K-0001
FS1018-OFR-XX-ZZ-G-K-0001 | Fire Strategy Report | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-OFR-XX-ZZ-G-K-0001 Fire Strategy Report | FS1018-OFR-XX-ZZ-G-K-0001
FS1018-ONE-00-XX-T-L-0001 | OutlineSpecification | P01 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | Please provide detail re Canopies finishes, if they are required for PV's; More detail needed on Sprinkler tank: '4.5m high close board timber cladding attached to galvanised steel frame with matching manually lockable gates. Concrete base.'; More detail needed on Bin Store: 1.8m high close board timber cladding attached to galvanised steel frame with matching manually lockable gates. Concrete base'; Please show Bin Store gate detail ; Please show detail of proposed Door Guard | FALSE | FS1018-ONE-00-XX-T-L-0001 OutlineSpecification | FS1018-ONE-00-XX-T-L-0001
FS1018-ONE-XX-XX-T-L-0001 | Outline Specification | P02 | Completed | 2024-08-01 | Landscape Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-ONE-XX-XX-T-L-0001 Outline Specification | FS1018-ONE-XX-XX-T-L-0001
FS1018-ONE-XX-XX-T-L-0001 | Outline Specification | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-XX-T-L-0001 Outline Specification | FS1018-ONE-XX-XX-T-L-0001
FS1018-ONE-XX-XX-T-L-0002 | Design Development Schedule | P01 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | Confirm retention of existing fences is acceptable for Trust. | FALSE | FS1018-ONE-XX-XX-T-L-0002 Design Development Schedule | FS1018-ONE-XX-XX-T-L-0002
FS1018-ONE-XX-XX-T-L-0002 | Design Development Schedule | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ONE-XX-XX-T-L-0002 Design Development Schedule | FS1018-ONE-XX-XX-T-L-0002
FS1018-ONE-XX-XX-T-L-0003 | Risk Register | P01 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-XX-T-L-0003 Risk Register | FS1018-ONE-XX-XX-T-L-0003
FS1018-ONE-XX-ZZ-D-L-0001 | Location Plan | P02 | Completed | 2023-09-06 | Landscape Review | A3 - Accepted | 2023-09-21 |  | TRUE | FS1018-ONE-XX-ZZ-D-L-0001 Location Plan | FS1018-ONE-XX-ZZ-D-L-0001
FS1018-ONE-XX-ZZ-D-L-0001 | Location Plan | P02 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-ONE-XX-ZZ-D-L-0001 Location Plan | FS1018-ONE-XX-ZZ-D-L-0001
FS1018-ONE-XX-ZZ-D-L-0001 | Location Plan | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0001 Location Plan | FS1018-ONE-XX-ZZ-D-L-0001
FS1018-ONE-XX-ZZ-D-L-0002 | Existing Site Plan | P05 | Completed | 2023-09-06 | Landscape Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0002 Existing Site Plan | FS1018-ONE-XX-ZZ-D-L-0002
FS1018-ONE-XX-ZZ-D-L-0002 | Existing Site Plan | P05 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0002 Existing Site Plan | FS1018-ONE-XX-ZZ-D-L-0002
FS1018-ONE-XX-ZZ-D-L-0002 | Existing Site Plan | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0002 Existing Site Plan | FS1018-ONE-XX-ZZ-D-L-0002
FS1018-ONE-XX-ZZ-D-L-0003 | Whole Site Plan | P07 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing | FALSE | FS1018-ONE-XX-ZZ-D-L-0003 Whole Site Plan | FS1018-ONE-XX-ZZ-D-L-0003
FS1018-ONE-XX-ZZ-D-L-0003 | Whole Site Plan | P10 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0003 Whole Site Plan | FS1018-ONE-XX-ZZ-D-L-0003
FS1018-ONE-XX-ZZ-D-L-0003 | Whole Site Plan | P14 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0003 Whole Site Plan | FS1018-ONE-XX-ZZ-D-L-0003
FS1018-ONE-XX-ZZ-D-L-0004 | Site Landscaping Plan 1 of 5 | P02 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | Please show an overall legend plan and a box call out to indicate this part drawings relative location. Comment Applies to all 5 part drawings; Confirm heights of all existing Fencing and denote on drawing. Comment Applies to all 5 part drawings; How does 2m high security fencing satisfy ER's? Annex 2C 8.1.2 Secure Line fencing shall be designed to meet the security requirements in the SSB. Secure line fencing shall: a) be a minimum of 2.4m in height in Mainstream Schools and Special Schools unless specified otherwise in the SSB [Ss_25_14] | TRUE | FS1018-ONE-XX-ZZ-D-L-0004 Site Landscaping Plan 1 of 5 | FS1018-ONE-XX-ZZ-D-L-0004
FS1018-ONE-XX-ZZ-D-L-0004 | Site Landscaping Plan 1 of 5 | P04 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0004 Site Landscaping Plan 1 of 5 | FS1018-ONE-XX-ZZ-D-L-0004
FS1018-ONE-XX-ZZ-D-L-0004 | Site Landscaping Plan 1 of 5 | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0004 Site Landscaping Plan 1 of 5 | FS1018-ONE-XX-ZZ-D-L-0004
FS1018-ONE-XX-ZZ-D-L-0005 | Site Landscaping Plan 2 of 5 | P02 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | Please show an overall legend plan and a box call out to indicate this part drawings relative location. Comment Applies to all 5 part drawings; Confirm heights of all existing Fencing and denote on drawing. Comment Applies to all 5 part drawings; How does 2m high security fencing satisfy ER's? Annex 2C 8.1.2 Secure Line fencing shall be designed to meet the security requirements in the SSB. Secure line fencing shall: a) be a minimum of 2.4m in height in Mainstream Schools and Special Schools unless specified otherwise in the SSB [Ss_25_14] | TRUE | FS1018-ONE-XX-ZZ-D-L-0005 Site Landscaping Plan 2 of 5 | FS1018-ONE-XX-ZZ-D-L-0005
FS1018-ONE-XX-ZZ-D-L-0005 | Site Landscaping Plan 2 of 5 | P04 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0005 Site Landscaping Plan 2 of 5 | FS1018-ONE-XX-ZZ-D-L-0005
FS1018-ONE-XX-ZZ-D-L-0005 | Site Landscaping Plan 2 of 5 | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0005 Site Landscaping Plan 2 of 5 | FS1018-ONE-XX-ZZ-D-L-0005
FS1018-ONE-XX-ZZ-D-L-0006 | Site Landscaping Plan 3 of 5 | P02 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | Please show an overall legend plan and a box call out to indicate this part drawings relative location. Comment Applies to all 5 part drawings; Confirm heights of all existing Fencing and denote on drawing. Comment Applies to all 5 part drawings; How does 2m high security fencing satisfy ER's? Annex 2C 8.1.2 Secure Line fencing shall be designed to meet the security requirements in the SSB. Secure line fencing shall: a) be a minimum of 2.4m in height in Mainstream Schools and Special Schools unless specified otherwise in the SSB [Ss_25_14] | TRUE | FS1018-ONE-XX-ZZ-D-L-0006 Site Landscaping Plan 3 of 5 | FS1018-ONE-XX-ZZ-D-L-0006
FS1018-ONE-XX-ZZ-D-L-0006 | Site Landscaping Plan 3 of 5 | P04 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0006 Site Landscaping Plan 3 of 5 | FS1018-ONE-XX-ZZ-D-L-0006
FS1018-ONE-XX-ZZ-D-L-0006 | Site Landscaping Plan 3 of 5 | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0006 Site Landscaping Plan 3 of 5 | FS1018-ONE-XX-ZZ-D-L-0006
FS1018-ONE-XX-ZZ-D-L-0007 | Site Landscaping Plan 4 of 5 | P02 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | Please show an overall legend plan and a box call out to indicate this part drawings relative location. Comment Applies to all 5 part drawings; Confirm heights of all existing Fencing and denote on drawing. Comment Applies to all 5 part drawings; How does 2m high security fencing satisfy ER's? Annex 2C 8.1.2 Secure Line fencing shall be designed to meet the security requirements in the SSB. Secure line fencing shall: a) be a minimum of 2.4m in height in Mainstream Schools and Special Schools unless specified otherwise in the SSB [Ss_25_14] | TRUE | FS1018-ONE-XX-ZZ-D-L-0007 Site Landscaping Plan 4 of 5 | FS1018-ONE-XX-ZZ-D-L-0007
FS1018-ONE-XX-ZZ-D-L-0007 | Site Landscaping Plan 4 of 5 | P04 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0007 Site Landscaping Plan 4 of 5 | FS1018-ONE-XX-ZZ-D-L-0007
FS1018-ONE-XX-ZZ-D-L-0007 | Site Landscaping Plan 4 of 5 | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0007 Site Landscaping Plan 4 of 5 | FS1018-ONE-XX-ZZ-D-L-0007
FS1018-ONE-XX-ZZ-D-L-0008 | Site Landscaping Plan 5 of 5 | P02 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | Please show an overall legend plan and a box call out to indicate this part drawings relative location. Comment Applies to all 5 part drawings; Confirm heights of all existing Fencing and denote on drawing. Comment Applies to all 5 part drawings; How does 2m high security fencing satisfy ER's? Annex 2C 8.1.2 Secure Line fencing shall be designed to meet the security requirements in the SSB. Secure line fencing shall: a) be a minimum of 2.4m in height in Mainstream Schools and Special Schools unless specified otherwise in the SSB [Ss_25_14] | TRUE | FS1018-ONE-XX-ZZ-D-L-0008 Site Landscaping Plan 5 of 5 | FS1018-ONE-XX-ZZ-D-L-0008
FS1018-ONE-XX-ZZ-D-L-0008 | Site Landscaping Plan 5 of 5 | P04 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0008 Site Landscaping Plan 5 of 5 | FS1018-ONE-XX-ZZ-D-L-0008
FS1018-ONE-XX-ZZ-D-L-0008 | Site Landscaping Plan 5 of 5 | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0008 Site Landscaping Plan 5 of 5 | FS1018-ONE-XX-ZZ-D-L-0008
FS1018-ONE-XX-ZZ-D-L-0009 | Access Security Strategy | P04 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. Please indicate Entrances for Staff / Pupils / Public / Community; Can Sports Hall be used by Community Use as a standalone facility after hours? If so, how does access strategy help this? Is gate to North East to be used or do users have to use the Main Building Entrance? ; Is a continuous clear access width to rear of school achievable from within school grounds? eg gate to north east of school provides the primary point of entry to the back of the school (secondary double gate access from Weasenham lane), yet is by means of a single gate - however gates within this secure area are double. How does this narrowing satisfy access / egress requirements for fire / maintenance etc? Can a MEWP get through the outer single secure gate? | FALSE | FS1018-ONE-XX-ZZ-D-L-0009 Access Security Strategy | FS1018-ONE-XX-ZZ-D-L-0009
FS1018-ONE-XX-ZZ-D-L-0009 | Access and Security Strategy (with external fences) | P06 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0009 Access and Security Strategy (with external fences) | FS1018-ONE-XX-ZZ-D-L-0009
FS1018-ONE-XX-ZZ-D-L-0009 | Access and Security Strategy | P08 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0009 Access and Security Strategy | FS1018-ONE-XX-ZZ-D-L-0009
FS1018-ONE-XX-ZZ-D-L-0010 | Circulation Strategy | P03 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | Subject to updates to base drawing following action of comments on overall site plan. | FALSE | FS1018-ONE-XX-ZZ-D-L-0010 Circulation Strategy | FS1018-ONE-XX-ZZ-D-L-0010
FS1018-ONE-XX-ZZ-D-L-0010 | Circulation Strategy | P04 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0010 Circulation Strategy | FS1018-ONE-XX-ZZ-D-L-0010
FS1018-ONE-XX-ZZ-D-L-0010 | Circulation Strategy | P06 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0010 Circulation Strategy | FS1018-ONE-XX-ZZ-D-L-0010
FS1018-ONE-XX-ZZ-D-L-0011 | External Sports Provision | P03 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | Subject to updates to base drawing following action of comments on overall site plan. | FALSE | FS1018-ONE-XX-ZZ-D-L-0011 External Sports Provision | FS1018-ONE-XX-ZZ-D-L-0011
FS1018-ONE-XX-ZZ-D-L-0011 | External Sports Provision | P05 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0011 External Sports Provision | FS1018-ONE-XX-ZZ-D-L-0011
FS1018-ONE-XX-ZZ-D-L-0011 | External Sports Provision | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0011 External Sports Provision | FS1018-ONE-XX-ZZ-D-L-0011
FS1018-ONE-XX-ZZ-D-L-0012 | Green Infrastructure Plan | P04 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. How do proposals satisfy the BNG requirements contained in the ER's and/or those of the statutory guidance required from Nov 2023? No Green Roof contribution included in UGF calculations. Extensive green roof entry needs including. No evidence of how proposed approach meets BNG requirements in comparison with baseline (i.e. what UGF baseline is). Where are any solar PV canopies (if required) going to be accommodated? | FALSE | FS1018-ONE-XX-ZZ-D-L-0012 Green Infrastructure Plan | FS1018-ONE-XX-ZZ-D-L-0012
FS1018-ONE-XX-ZZ-D-L-0012 | Green Infrastructure Plan | P06 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0012 Green Infrastructure Plan | FS1018-ONE-XX-ZZ-D-L-0012
FS1018-ONE-XX-ZZ-D-L-0012 | Green Infrastructure Plan | P08 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0012 Green Infrastructure Plan | FS1018-ONE-XX-ZZ-D-L-0012
FS1018-ONE-XX-ZZ-D-L-0013 | BB103 Guidance | P02 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | Confirm how stated proposals of 24073 sq m satisfy BB103 minimum requirement of 35000 sq m? | TRUE | FS1018-ONE-XX-ZZ-D-L-0013 BB103 Guidance | FS1018-ONE-XX-ZZ-D-L-0013
FS1018-ONE-XX-ZZ-D-L-0013 | BB103 Guidance | P03 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0013 BB103 Guidance | FS1018-ONE-XX-ZZ-D-L-0013
FS1018-ONE-XX-ZZ-D-L-0013 | BB103 Guidance | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0013 BB103 Guidance | FS1018-ONE-XX-ZZ-D-L-0013
FS1018-ONE-XX-ZZ-D-L-0014 | Hazard Identification Plan | P02 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | "Are the hazards mentioned specific to this site? Eg 2.2 Risk: Pedestrians at risk from moving vehicles, Mitigation: Pedestrian routes set back from carriageways - as mentioned previously, wouldn't another mitigation be to provide pedestrian crossings from all car spaces? Eg 2.3 Pupils (injury), Contact with Dogs (aggressive) - is contact with dogs a specific risk on this site? " | TRUE | FS1018-ONE-XX-ZZ-D-L-0014 Hazard Identification Plan | FS1018-ONE-XX-ZZ-D-L-0014
FS1018-ONE-XX-ZZ-D-L-0014 | Hazard Identification Plan | P04 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0014 Hazard Identification Plan | FS1018-ONE-XX-ZZ-D-L-0014
FS1018-ONE-XX-ZZ-D-L-0014 | Hazard Identification Plan | P06 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0014 Hazard Identification Plan | FS1018-ONE-XX-ZZ-D-L-0014
FS1018-ONE-XX-ZZ-D-L-0015 | Refurbishment Remodelling Strategy | P03 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on existing trees, car spaces, fencing and proposed bin store | FALSE | FS1018-ONE-XX-ZZ-D-L-0015 Refurbishment Remodelling Strategy | FS1018-ONE-XX-ZZ-D-L-0015
FS1018-ONE-XX-ZZ-D-L-0015 | Refurbishment Remodelling Strategy | P07 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0015 Refurbishment Remodelling Strategy | FS1018-ONE-XX-ZZ-D-L-0015
FS1018-ONE-XX-ZZ-D-L-0015 | Refurbishment Remodelling Strategy | P09 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0015 Refurbishment Remodelling Strategy | FS1018-ONE-XX-ZZ-D-L-0015
FS1018-ONE-XX-ZZ-D-L-0017 | Site Sections | P01 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0017 Site Sections | FS1018-ONE-XX-ZZ-D-L-0017
FS1018-ONE-XX-ZZ-D-L-0017 | Site Sections | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0017 Site Sections | FS1018-ONE-XX-ZZ-D-L-0017
FS1018-ONE-XX-ZZ-D-L-0021 | Existing Site Plan 1 of 5 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ONE-XX-ZZ-D-L-0021 Existing Site Plan 1 of 5 | FS1018-ONE-XX-ZZ-D-L-0021
FS1018-ONE-XX-ZZ-D-L-0022 | Existing Site Plan 2 of 5 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ONE-XX-ZZ-D-L-0022 Existing Site Plan 2 of 5 | FS1018-ONE-XX-ZZ-D-L-0022
FS1018-ONE-XX-ZZ-D-L-0023 | Existing Site Plan 3 of 5 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ONE-XX-ZZ-D-L-0023 Existing Site Plan 3 of 5 | FS1018-ONE-XX-ZZ-D-L-0023
FS1018-ONE-XX-ZZ-D-L-0024 | Existing Site Plan 4 of 5 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ONE-XX-ZZ-D-L-0024 Existing Site Plan 4 of 5 | FS1018-ONE-XX-ZZ-D-L-0024
FS1018-ONE-XX-ZZ-D-L-0025 | Existing Site Plan 5 of 5 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ONE-XX-ZZ-D-L-0025 Existing Site Plan 5 of 5 | FS1018-ONE-XX-ZZ-D-L-0025
FS1018-ONE-XX-ZZ-D-L-0201 | Detailed Planting Plan Sheet 1of 5 | P01 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0201 Detailed Planting Plan Sheet 1of 5 | FS1018-ONE-XX-ZZ-D-L-0201
FS1018-ONE-XX-ZZ-D-L-0201 | Detailed Planting Plan Sheet 1 of 5 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0201 Detailed Planting Plan Sheet 1 of 5 | FS1018-ONE-XX-ZZ-D-L-0201
FS1018-ONE-XX-ZZ-D-L-0202 | Detailed Planting Plan Sheet 2of 5 | P01 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0202 Detailed Planting Plan Sheet 2of 5 | FS1018-ONE-XX-ZZ-D-L-0202
FS1018-ONE-XX-ZZ-D-L-0202 | Detailed Planting Plan Sheet 2 of 5 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0202 Detailed Planting Plan Sheet 2 of 5 | FS1018-ONE-XX-ZZ-D-L-0202
FS1018-ONE-XX-ZZ-D-L-0203 | Detailed Planting Plan Sheet 3of 5 | P01 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0203 Detailed Planting Plan Sheet 3of 5 | FS1018-ONE-XX-ZZ-D-L-0203
FS1018-ONE-XX-ZZ-D-L-0203 | Detailed Planting Plan Sheet 3 of 5 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0203 Detailed Planting Plan Sheet 3 of 5 | FS1018-ONE-XX-ZZ-D-L-0203
FS1018-ONE-XX-ZZ-D-L-0204 | Detailed Planting Plan Sheet 4of 5 | P01 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0204 Detailed Planting Plan Sheet 4of 5 | FS1018-ONE-XX-ZZ-D-L-0204
FS1018-ONE-XX-ZZ-D-L-0204 | Detailed Planting Plan Sheet 4 of 5 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0204 Detailed Planting Plan Sheet 4 of 5 | FS1018-ONE-XX-ZZ-D-L-0204
FS1018-ONE-XX-ZZ-D-L-0205 | Detailed Planting Plan Sheet 5of 5 | P02 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-ONE-XX-ZZ-D-L-0205 Detailed Planting Plan Sheet 5of 5 | FS1018-ONE-XX-ZZ-D-L-0205
FS1018-ONE-XX-ZZ-D-L-0205 | Detailed Planting Plan Sheet 5 of 5 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0205 Detailed Planting Plan Sheet 5 of 5 | FS1018-ONE-XX-ZZ-D-L-0205
FS1018-ONE-XX-ZZ-D-L-0401 | Outline Levels Plan 1 of 5 | P02 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-21 | TA Civil engineer to review levels for suitability for drainage | TRUE | FS1018-ONE-XX-ZZ-D-L-0401 Outline Levels Plan 1 of 5 | FS1018-ONE-XX-ZZ-D-L-0401
FS1018-ONE-XX-ZZ-D-L-0401 | Outline Levels Plan 1of 5 | P04 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0401 Outline Levels Plan 1of 5 | FS1018-ONE-XX-ZZ-D-L-0401
FS1018-ONE-XX-ZZ-D-L-0401 | Outline Levels Plan 1 of 5 | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0401 Outline Levels Plan 1 of 5 | FS1018-ONE-XX-ZZ-D-L-0401
FS1018-ONE-XX-ZZ-D-L-0402 | Outline Levels Plan 2 of 5 | P02 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-10-09 | To be updated following overall landscape revisions | TRUE | FS1018-ONE-XX-ZZ-D-L-0402 Outline Levels Plan 2 of 5 | FS1018-ONE-XX-ZZ-D-L-0402
FS1018-ONE-XX-ZZ-D-L-0402 | Outline Levels Plan 2of 5 | P04 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0402 Outline Levels Plan 2of 5 | FS1018-ONE-XX-ZZ-D-L-0402
FS1018-ONE-XX-ZZ-D-L-0402 | Outline Levels Plan 2 of 5 | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0402 Outline Levels Plan 2 of 5 | FS1018-ONE-XX-ZZ-D-L-0402
FS1018-ONE-XX-ZZ-D-L-0403 | Outline Levels Plan 3 of 5 | P02 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-10-09 | To be updated with overall landscape revisions | TRUE | FS1018-ONE-XX-ZZ-D-L-0403 Outline Levels Plan 3 of 5 | FS1018-ONE-XX-ZZ-D-L-0403
FS1018-ONE-XX-ZZ-D-L-0403 | Outline Levels Plan 3of 5 | P04 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0403 Outline Levels Plan 3of 5 | FS1018-ONE-XX-ZZ-D-L-0403
FS1018-ONE-XX-ZZ-D-L-0403 | Outline Levels Plan 3 of 5 | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0403 Outline Levels Plan 3 of 5 | FS1018-ONE-XX-ZZ-D-L-0403
FS1018-ONE-XX-ZZ-D-L-0404 | Outline Levels Plan 4 of 5 | P02 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-10-09 | To be updated along with overall landscape revisions | TRUE | FS1018-ONE-XX-ZZ-D-L-0404 Outline Levels Plan 4 of 5 | FS1018-ONE-XX-ZZ-D-L-0404
FS1018-ONE-XX-ZZ-D-L-0404 | Outline Levels Plan 4of 5 | P04 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0404 Outline Levels Plan 4of 5 | FS1018-ONE-XX-ZZ-D-L-0404
FS1018-ONE-XX-ZZ-D-L-0404 | Outline Levels Plan 4 of 5 | P06 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0404 Outline Levels Plan 4 of 5 | FS1018-ONE-XX-ZZ-D-L-0404
FS1018-ONE-XX-ZZ-D-L-0405 | Outline Levels Plan 5 of 5 | P02 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-10-09 | To be updated following overall landscape revisions | TRUE | FS1018-ONE-XX-ZZ-D-L-0405 Outline Levels Plan 5 of 5 | FS1018-ONE-XX-ZZ-D-L-0405
FS1018-ONE-XX-ZZ-D-L-0405 | Outline Levels Plan 5of 5 | P04 | Completed | 2024-09-09 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-XX-ZZ-D-L-0405 Outline Levels Plan 5of 5 | FS1018-ONE-XX-ZZ-D-L-0405
FS1018-ONE-XX-ZZ-D-L-0405 | Outline Levels Plan 5 of 5 | P06 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0405 Outline Levels Plan 5 of 5 | FS1018-ONE-XX-ZZ-D-L-0405
FS1018-ONE-XX-ZZ-D-L-0601 | Landscape Details Sheet 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0601 Landscape Details Sheet 1 | FS1018-ONE-XX-ZZ-D-L-0601
FS1018-ONE-XX-ZZ-D-L-0602 | Landscape Details Sheet 2 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0602 Landscape Details Sheet 2 | FS1018-ONE-XX-ZZ-D-L-0602
FS1018-ONE-XX-ZZ-D-L-0603 | Landscape Details Sheet 3 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-XX-ZZ-D-L-0603 Landscape Details Sheet 3 | FS1018-ONE-XX-ZZ-D-L-0603
FS1018-ONE-ZZ-XX-T-L-0004 | Security Statement | P01 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-ONE-ZZ-XX-T-L-0004 Security Statement | FS1018-ONE-ZZ-XX-T-L-0004
FS1018-ONE-ZZ-XX-T-L-0004 | Security Statement | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-ONE-ZZ-XX-T-L-0004 Security Statement | FS1018-ONE-ZZ-XX-T-L-0004
FS1018-ONE-ZZ-ZZ-M-L-0001 | Landscape ModelLandscapeModel | P01 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-26 | Some surfacing missing at Library entrance. | FALSE | FS1018-ONE-ZZ-ZZ-M-L-0001 Landscape ModelLandscapeModel | FS1018-ONE-ZZ-ZZ-M-L-0001
FS1018-ONE-ZZ-ZZ-M-L-0001 | Landscape Model | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-ZZ-ZZ-M-L-0001 Landscape Model | FS1018-ONE-ZZ-ZZ-M-L-0001
FS1018-ONE-ZZ-ZZ-M-L-0002 | LandscapeModel | P01 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-26 | Some surfacing missing at Library entrance. Some planting is visible in the Nwc model but not in the Ifc model. 348 elements have USERDEFINED or NOTDEFINED predefined type and 20 elements with empty field. Model should only contain 1 site instance. | FALSE | FS1018-ONE-ZZ-ZZ-M-L-0002 LandscapeModel | FS1018-ONE-ZZ-ZZ-M-L-0002
FS1018-ONE-ZZ-ZZ-M-L-0002 | Landscape Model | P02 | Completed | 2024-08-01 | Landscape Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-ONE-ZZ-ZZ-M-L-0002 Landscape Model | FS1018-ONE-ZZ-ZZ-M-L-0002
FS1018-ONE-ZZ-ZZ-M-L-0002 | Landscape Model | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-ZZ-ZZ-M-L-0002 Landscape Model | FS1018-ONE-ZZ-ZZ-M-L-0002
FS1018-ONE-ZZ-ZZ-M-L-0003 | LandscapeModel | P01 | Completed | 2023-09-06 | Landscape Review | B3 - Partially Accepted with Comments | 2023-09-26 | Model reference on flysheet not aligned to file name. Status code missing and splash screen sheet is missing. Unnecessary views not removed from model. Some surfacing missing at Library entrance. Some planting is visible in the Nwc model but not in the Ifc model. | FALSE | FS1018-ONE-ZZ-ZZ-M-L-0003 LandscapeModel | FS1018-ONE-ZZ-ZZ-M-L-0003
FS1018-ONE-ZZ-ZZ-M-L-0003 | Landscape Model | P02 | Completed | 2024-08-28 | Architectural Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-ONE-ZZ-ZZ-M-L-0003 Landscape Model | FS1018-ONE-ZZ-ZZ-M-L-0003
FS1018-ONE-ZZ-ZZ-M-L-0003 | Landscape Model | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-ONE-ZZ-ZZ-M-L-0003 Landscape Model | FS1018-ONE-ZZ-ZZ-M-L-0003
FS1018-PIN-XX-XX-L-O-0003 | Task Team Risk Register | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-XX-XX-L-O-0003 Task Team Risk Register | FS1018-PIN-XX-XX-L-O-0003
FS1018-PIN-ZZ-00-D-O-0001 | GROUND FLOOR GA (1 OF 2) | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing | FALSE | FS1018-PIN-ZZ-00-D-O-0001 GROUND FLOOR GA (1 OF 2) | FS1018-PIN-ZZ-00-D-O-0001
FS1018-PIN-ZZ-00-D-O-0001 | Ground Floor GA (1 Of 2) | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-00-D-O-0001 Ground Floor GA (1 Of 2) | FS1018-PIN-ZZ-00-D-O-0001
FS1018-PIN-ZZ-00-D-O-0001 | Ground Floor GA 1 Of 2 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-0001 Ground Floor GA 1 Of 2 | FS1018-PIN-ZZ-00-D-O-0001
FS1018-PIN-ZZ-00-D-O-0002 | GROUND FLOOR GA (2 OF 2) | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-00-D-O-0002 GROUND FLOOR GA (2 OF 2) | FS1018-PIN-ZZ-00-D-O-0002
FS1018-PIN-ZZ-00-D-O-0002 | Ground Floor GA (2 Of 2) | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-00-D-O-0002 Ground Floor GA (2 Of 2) | FS1018-PIN-ZZ-00-D-O-0002
FS1018-PIN-ZZ-00-D-O-0002 | Ground Floor GA 2 Of 2 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-0002 Ground Floor GA 2 Of 2 | FS1018-PIN-ZZ-00-D-O-0002
FS1018-PIN-ZZ-00-D-O-0006 | Lobby 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-0006 Lobby 1 | FS1018-PIN-ZZ-00-D-O-0006
FS1018-PIN-ZZ-00-D-O-0006 | Lobby 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-0006 Lobby 1 | FS1018-PIN-ZZ-00-D-O-0006
FS1018-PIN-ZZ-00-D-O-0601 | Food Prep Area, Kitchen (Servery And Wash Up) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-0601 Food Prep Area, Kitchen (Servery And Wash Up) 1 | FS1018-PIN-ZZ-00-D-O-0601
FS1018-PIN-ZZ-00-D-O-0601 | Food Prep Area, Kitchen Servery And Wash Up 1 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-0601 Food Prep Area, Kitchen Servery And Wash Up 1 | FS1018-PIN-ZZ-00-D-O-0601
FS1018-PIN-ZZ-00-D-O-1109 | MUSIC ROOM | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-00-D-O-1109 MUSIC ROOM | FS1018-PIN-ZZ-00-D-O-1109
FS1018-PIN-ZZ-00-D-O-1109 | Music Room | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-00-D-O-1109 Music Room | FS1018-PIN-ZZ-00-D-O-1109
FS1018-PIN-ZZ-00-D-O-1109 | Music Room | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-1109 Music Room | FS1018-PIN-ZZ-00-D-O-1109
FS1018-PIN-ZZ-00-D-O-1110 | DT WORKSHOP 1 | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-00-D-O-1110 DT WORKSHOP 1 | FS1018-PIN-ZZ-00-D-O-1110
FS1018-PIN-ZZ-00-D-O-1110 | DT WORKSHOP 1 | P03 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-1110 DT WORKSHOP 1 | FS1018-PIN-ZZ-00-D-O-1110
FS1018-PIN-ZZ-00-D-O-1110 | DT Workshop 1 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-1110 DT Workshop 1 | FS1018-PIN-ZZ-00-D-O-1110
FS1018-PIN-ZZ-00-D-O-1111 | FOOD ROOM 1 | S5-P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-00-D-O-1111 FOOD ROOM 1 | FS1018-PIN-ZZ-00-D-O-1111
FS1018-PIN-ZZ-00-D-O-1111 | Food Room 1 Option 1 | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-00-D-O-1111 Food Room 1 Option 1 | FS1018-PIN-ZZ-00-D-O-1111
FS1018-PIN-ZZ-00-D-O-1111 | Food Room 1 Option 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-1111 Food Room 1 Option 1 | FS1018-PIN-ZZ-00-D-O-1111
FS1018-PIN-ZZ-00-D-O-1112 | DT STUDIO (GRAPHIC PRODUCTS) | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-00-D-O-1112 DT STUDIO (GRAPHIC PRODUCTS) | FS1018-PIN-ZZ-00-D-O-1112
FS1018-PIN-ZZ-00-D-O-1112 | DT STUDIO (GRAPHIC PRODUCTS) | P03 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-1112 DT STUDIO (GRAPHIC PRODUCTS) | FS1018-PIN-ZZ-00-D-O-1112
FS1018-PIN-ZZ-00-D-O-1112 | DT Studio Graphic Products | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-1112 DT Studio Graphic Products | FS1018-PIN-ZZ-00-D-O-1112
FS1018-PIN-ZZ-00-D-O-1113 | DT STUDIO (ELECTRONICS & CONTROL) | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-00-D-O-1113 DT STUDIO (ELECTRONICS & CONTROL) | FS1018-PIN-ZZ-00-D-O-1113
FS1018-PIN-ZZ-00-D-O-1113 | DT STUDIO (ELECTRONICS & CONTROL) | P03 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-1113 DT STUDIO (ELECTRONICS & CONTROL) | FS1018-PIN-ZZ-00-D-O-1113
FS1018-PIN-ZZ-00-D-O-1113 | DT Studio Electronics And Control | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-1113 DT Studio Electronics And Control | FS1018-PIN-ZZ-00-D-O-1113
FS1018-PIN-ZZ-00-D-O-1211 | FOOD ROOM 1 | S5-P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-00-D-O-1211 FOOD ROOM 1 | FS1018-PIN-ZZ-00-D-O-1211
FS1018-PIN-ZZ-00-D-O-1211 | Food Room 1 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-1211 Food Room 1 | FS1018-PIN-ZZ-00-D-O-1211
FS1018-PIN-ZZ-00-D-O-2001 | ASSEMBLY HALL, SECONDARY | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-00-D-O-2001 ASSEMBLY HALL, SECONDARY | FS1018-PIN-ZZ-00-D-O-2001
FS1018-PIN-ZZ-00-D-O-2001 | ASSEMBLY HALL, SECONDARY | P03 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-2001 ASSEMBLY HALL, SECONDARY | FS1018-PIN-ZZ-00-D-O-2001
FS1018-PIN-ZZ-00-D-O-2001 | Assembly Hall, Dining Layout | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-2001 Assembly Hall, Dining Layout | FS1018-PIN-ZZ-00-D-O-2001
FS1018-PIN-ZZ-00-D-O-2002 | SPORTS HALL (EXAM LAYOUT) | P01 | Completed | 2023-09-06 | FFE Review | A3 - Accepted | 2023-09-21 |  | FALSE | FS1018-PIN-ZZ-00-D-O-2002 SPORTS HALL (EXAM LAYOUT) | FS1018-PIN-ZZ-00-D-O-2002
FS1018-PIN-ZZ-00-D-O-2002 | Sports Hall (Exam Layout) | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-00-D-O-2002 Sports Hall (Exam Layout) | FS1018-PIN-ZZ-00-D-O-2002
FS1018-PIN-ZZ-00-D-O-2002 | Sports Hall Exam Layout | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-2002 Sports Hall Exam Layout | FS1018-PIN-ZZ-00-D-O-2002
FS1018-PIN-ZZ-00-D-O-2003 | ASSEMBLY HALL, SECONDARY LAYOUT 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-2003 ASSEMBLY HALL, SECONDARY LAYOUT 2 | FS1018-PIN-ZZ-00-D-O-2003
FS1018-PIN-ZZ-00-D-O-2003 | Assembly Hall, Assembly Layout | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-2003 Assembly Hall, Assembly Layout | FS1018-PIN-ZZ-00-D-O-2003
FS1018-PIN-ZZ-00-D-O-3001 | LRC OPTION 1 | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-00-D-O-3001 LRC OPTION 1 | FS1018-PIN-ZZ-00-D-O-3001
FS1018-PIN-ZZ-00-D-O-3001 | LRC Option 1 | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-00-D-O-3001 LRC Option 1 | FS1018-PIN-ZZ-00-D-O-3001
FS1018-PIN-ZZ-00-D-O-3002 | Sports Hall (Sport Layout) | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-3002 Sports Hall (Sport Layout) | FS1018-PIN-ZZ-00-D-O-3002
FS1018-PIN-ZZ-00-D-O-3002 | Sports Hall Sport Layout | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-3002 Sports Hall Sport Layout | FS1018-PIN-ZZ-00-D-O-3002
FS1018-PIN-ZZ-00-D-O-3004 | LRC | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-3004 LRC | FS1018-PIN-ZZ-00-D-O-3004
FS1018-PIN-ZZ-00-D-O-4003 | Enclosed Office, Admin (Head) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-4003 Enclosed Office, Admin (Head) 1 | FS1018-PIN-ZZ-00-D-O-4003
FS1018-PIN-ZZ-00-D-O-4003 | Enclosed Office, Admin Head 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-4003 Enclosed Office, Admin Head 1 | FS1018-PIN-ZZ-00-D-O-4003
FS1018-PIN-ZZ-00-D-O-4004 | Enclosed Office, Admin (Pa)1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-4004 Enclosed Office, Admin (Pa)1 | FS1018-PIN-ZZ-00-D-O-4004
FS1018-PIN-ZZ-00-D-O-4004 | Enclosed Office, Admin PA 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-4004 Enclosed Office, Admin PA 1 | FS1018-PIN-ZZ-00-D-O-4004
FS1018-PIN-ZZ-00-D-O-4005 | Reprographics Room 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-4005 Reprographics Room 1 | FS1018-PIN-ZZ-00-D-O-4005
FS1018-PIN-ZZ-00-D-O-4005 | Reprographics Room 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-4005 Reprographics Room 1 | FS1018-PIN-ZZ-00-D-O-4005
FS1018-PIN-ZZ-00-D-O-4006 | Enclosed Office, With Recep Desk (And Window) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-4006 Enclosed Office, With Recep Desk (And Window) 1 | FS1018-PIN-ZZ-00-D-O-4006
FS1018-PIN-ZZ-00-D-O-4006 | Enclosed Office, With Recep Desk And Window 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-4006 Enclosed Office, With Recep Desk And Window 1 | FS1018-PIN-ZZ-00-D-O-4006
FS1018-PIN-ZZ-00-D-O-4008 | Reception Area, Entrance (50% Circulation) | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-4008 Reception Area, Entrance (50% Circulation) | FS1018-PIN-ZZ-00-D-O-4008
FS1018-PIN-ZZ-00-D-O-4008 | Reception Area, Entrance 50% Circulation | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-4008 Reception Area, Entrance 50% Circulation | FS1018-PIN-ZZ-00-D-O-4008
FS1018-PIN-ZZ-00-D-O-4009 | Confidential Meeting Room (Interview) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-4009 Confidential Meeting Room (Interview) 1 | FS1018-PIN-ZZ-00-D-O-4009
FS1018-PIN-ZZ-00-D-O-4009 | Confidential Meeting Room Interview 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-4009 Confidential Meeting Room Interview 1 | FS1018-PIN-ZZ-00-D-O-4009
FS1018-PIN-ZZ-00-D-O-4015 | Office (With Meeting Area, 2 Person) 4 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-4015 Office (With Meeting Area, 2 Person) 4 | FS1018-PIN-ZZ-00-D-O-4015
FS1018-PIN-ZZ-00-D-O-4015 | Office With Meeting Area, 2 Person 4 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-4015 Office With Meeting Area, 2 Person 4 | FS1018-PIN-ZZ-00-D-O-4015
FS1018-PIN-ZZ-00-D-O-4018 | Staff Workroom (Premises) 1 And Equipment Store, Maintenance 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-4018 Staff Workroom (Premises) 1 And Equipment Store, Maintenance 1 | FS1018-PIN-ZZ-00-D-O-4018
FS1018-PIN-ZZ-00-D-O-4018 | Staff Workroom Premises 1 And Equipment Store, Maintenance 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-4018 Staff Workroom Premises 1 And Equipment Store, Maintenance 1 | FS1018-PIN-ZZ-00-D-O-4018
FS1018-PIN-ZZ-00-D-O-5001 | Assembly Hall, Secondary Option 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-5001 Assembly Hall, Secondary Option 2 | FS1018-PIN-ZZ-00-D-O-5001
FS1018-PIN-ZZ-00-D-O-5003 | Confidential Meeting Room (Interview) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-5003 Confidential Meeting Room (Interview) 1 | FS1018-PIN-ZZ-00-D-O-5003
FS1018-PIN-ZZ-00-D-O-5003 | Confidential Meeting Room Interview 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-5003 Confidential Meeting Room Interview 1 | FS1018-PIN-ZZ-00-D-O-5003
FS1018-PIN-ZZ-00-D-O-5007 | Dt Prep Room 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-5007 Dt Prep Room 1 | FS1018-PIN-ZZ-00-D-O-5007
FS1018-PIN-ZZ-00-D-O-5007 | DT Prep Room 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-5007 DT Prep Room 1 | FS1018-PIN-ZZ-00-D-O-5007
FS1018-PIN-ZZ-00-D-O-5008 | Food Prep Room 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-5008 Food Prep Room 1 | FS1018-PIN-ZZ-00-D-O-5008
FS1018-PIN-ZZ-00-D-O-5008 | Food Prep Room 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-5008 Food Prep Room 1 | FS1018-PIN-ZZ-00-D-O-5008
FS1018-PIN-ZZ-00-D-O-5009 | Teaching Resources Store (Off Dt Studio) | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-5009 Teaching Resources Store (Off Dt Studio) | FS1018-PIN-ZZ-00-D-O-5009
FS1018-PIN-ZZ-00-D-O-5009 | Teaching Resources Store Off DT Studio | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-5009 Teaching Resources Store Off DT Studio | FS1018-PIN-ZZ-00-D-O-5009
FS1018-PIN-ZZ-00-D-O-5011 | Teaching Resources Store (Off Dt Studio) | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-5011 Teaching Resources Store (Off Dt Studio) | FS1018-PIN-ZZ-00-D-O-5011
FS1018-PIN-ZZ-00-D-O-5011 | Teaching Resources Store Off DT Studio | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-5011 Teaching Resources Store Off DT Studio | FS1018-PIN-ZZ-00-D-O-5011
FS1018-PIN-ZZ-00-D-O-5013 | Teaching Resources Store (Music) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-5013 Teaching Resources Store (Music) 1 | FS1018-PIN-ZZ-00-D-O-5013
FS1018-PIN-ZZ-00-D-O-5013 | Teaching Resources Store Music 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-5013 Teaching Resources Store Music 1 | FS1018-PIN-ZZ-00-D-O-5013
FS1018-PIN-ZZ-00-D-O-5018 | Sports Equipment Store, Internal (Sports Hall) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-5018 Sports Equipment Store, Internal (Sports Hall) 1 | FS1018-PIN-ZZ-00-D-O-5018
FS1018-PIN-ZZ-00-D-O-5018 | Sports Equipment Store, Internal Sports Hall 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-5018 Sports Equipment Store, Internal Sports Hall 1 | FS1018-PIN-ZZ-00-D-O-5018
FS1018-PIN-ZZ-00-D-O-5019 | Sports Equipment Store, External 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-5019 Sports Equipment Store, External 1 | FS1018-PIN-ZZ-00-D-O-5019
FS1018-PIN-ZZ-00-D-O-5019 | Sports Equipment Store, External 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-5019 Sports Equipment Store, External 1 | FS1018-PIN-ZZ-00-D-O-5019
FS1018-PIN-ZZ-00-D-O-5021 | DT STUDIO (GRAPHIC PRODUCTS) OPTION 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-5021 DT STUDIO (GRAPHIC PRODUCTS) OPTION 2 | FS1018-PIN-ZZ-00-D-O-5021
FS1018-PIN-ZZ-00-D-O-5103 | Secure Storeroom 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-5103 Secure Storeroom 1 | FS1018-PIN-ZZ-00-D-O-5103
FS1018-PIN-ZZ-00-D-O-5103 | Secure Storeroom 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-5103 Secure Storeroom 1 | FS1018-PIN-ZZ-00-D-O-5103
FS1018-PIN-ZZ-00-D-O-5109 | Coats And Bag Store (Lockers) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-5109 Coats And Bag Store (Lockers) 1 | FS1018-PIN-ZZ-00-D-O-5109
FS1018-PIN-ZZ-00-D-O-5109 | Coats And Bag Store Lockers 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-5109 Coats And Bag Store Lockers 1 | FS1018-PIN-ZZ-00-D-O-5109
FS1018-PIN-ZZ-00-D-O-5114 | Cleaners Store | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-5114 Cleaners Store | FS1018-PIN-ZZ-00-D-O-5114
FS1018-PIN-ZZ-00-D-O-5117 | Cleaners Store | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-5117 Cleaners Store | FS1018-PIN-ZZ-00-D-O-5117
FS1018-PIN-ZZ-00-D-O-6001 | DINING AND CATERING | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. "Many observations on Kitchen layout: •Can a walk in freezer be accessed from a cold store under Healthy & Safety legislation? •How does door to walk in freezer open if racking is in the way>? •How does the user gain access to the rear of racking in Dry Store? •Are there some power sockets on top of the central prep area? •Is there an additional fridge under a worktop? •Is there sufficient work surface for preparation? •Do distances between eqipment satisfy requirement for safe working? •Toilet and changing area not resolved - all shown in one space, but toilet and lockers need to be separate. •Are there any chemicals being used? Is there an external chemical store? Do these satisfy COSSH requirements? ; Can further dining seating be provided, if required? " | FALSE | FS1018-PIN-ZZ-00-D-O-6001 DINING AND CATERING | FS1018-PIN-ZZ-00-D-O-6001
FS1018-PIN-ZZ-00-D-O-6001 | Dining And Catering | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-00-D-O-6001 Dining And Catering | FS1018-PIN-ZZ-00-D-O-6001
FS1018-PIN-ZZ-00-D-O-6001 | Dining And Catering | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-6001 Dining And Catering | FS1018-PIN-ZZ-00-D-O-6001
FS1018-PIN-ZZ-00-D-O-6002 | Office, Kitchen 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-6002 Office, Kitchen 1 | FS1018-PIN-ZZ-00-D-O-6002
FS1018-PIN-ZZ-00-D-O-6002 | Office, Kitchen 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-6002 Office, Kitchen 1 | FS1018-PIN-ZZ-00-D-O-6002
FS1018-PIN-ZZ-00-D-O-6003 | Food Store, Kitchen (Dry) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-6003 Food Store, Kitchen (Dry) 1 | FS1018-PIN-ZZ-00-D-O-6003
FS1018-PIN-ZZ-00-D-O-6003 | Food Store, Kitchen Dry 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-6003 Food Store, Kitchen Dry 1 | FS1018-PIN-ZZ-00-D-O-6003
FS1018-PIN-ZZ-00-D-O-6004 | Cold Store, Kitchen 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-6004 Cold Store, Kitchen 1 | FS1018-PIN-ZZ-00-D-O-6004
FS1018-PIN-ZZ-00-D-O-6004 | Cold Store, Kitchen 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-6004 Cold Store, Kitchen 1 | FS1018-PIN-ZZ-00-D-O-6004
FS1018-PIN-ZZ-00-D-O-6005 | Cold Store, Kithen (Freezer) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-6005 Cold Store, Kithen (Freezer) 1 | FS1018-PIN-ZZ-00-D-O-6005
FS1018-PIN-ZZ-00-D-O-6005 | Cold Store, Kitchen Freezer 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-6005 Cold Store, Kitchen Freezer 1 | FS1018-PIN-ZZ-00-D-O-6005
FS1018-PIN-ZZ-00-D-O-6006 | Toilet, Kitchen (With Changing Area) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-6006 Toilet, Kitchen (With Changing Area) 1 | FS1018-PIN-ZZ-00-D-O-6006
FS1018-PIN-ZZ-00-D-O-6006 | Toilet (With Changing Area) 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-6006 Toilet (With Changing Area) 1 | FS1018-PIN-ZZ-00-D-O-6006
FS1018-PIN-ZZ-00-D-O-6007 | Changing Room, With Showers (Pupils) 1 And Toilets, Suite (Pupils, Other) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-6007 Changing Room, With Showers (Pupils) 1 And Toilets, Suite (Pupils, Other) 1 | FS1018-PIN-ZZ-00-D-O-6007
FS1018-PIN-ZZ-00-D-O-6007 | Changing Room, With Showers Pupils 1 And Toilets, Suite Pupils, Other 1 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-6007 Changing Room, With Showers Pupils 1 And Toilets, Suite Pupils, Other 1 | FS1018-PIN-ZZ-00-D-O-6007
FS1018-PIN-ZZ-00-D-O-6008 | Changing Room, With Showers (Pupils) 2 And Toilets, Suite (Pupils, Other) 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-6008 Changing Room, With Showers (Pupils) 2 And Toilets, Suite (Pupils, Other) 2 | FS1018-PIN-ZZ-00-D-O-6008
FS1018-PIN-ZZ-00-D-O-6008 | Changing Room, With Showers Pupils 2 And Toilets, Suite Pupils, Other 2 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-6008 Changing Room, With Showers Pupils 2 And Toilets, Suite Pupils, Other 2 | FS1018-PIN-ZZ-00-D-O-6008
FS1018-PIN-ZZ-00-D-O-6009 | Music Practice Room 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-6009 Music Practice Room 2 | FS1018-PIN-ZZ-00-D-O-6009
FS1018-PIN-ZZ-00-D-O-6009 | Music Practice Room 2 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-6009 Music Practice Room 2 | FS1018-PIN-ZZ-00-D-O-6009
FS1018-PIN-ZZ-00-D-O-6011 | Hygiene Room 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-6011 Hygiene Room 1 | FS1018-PIN-ZZ-00-D-O-6011
FS1018-PIN-ZZ-00-D-O-6042 | First Aid Post (Sick Bay) 1 And Stairway 7 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-6042 First Aid Post (Sick Bay) 1 And Stairway 7 | FS1018-PIN-ZZ-00-D-O-6042
FS1018-PIN-ZZ-00-D-O-6042 | First Aid Post Sick Bay 1 And Stairway 7 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-6042 First Aid Post Sick Bay 1 And Stairway 7 | FS1018-PIN-ZZ-00-D-O-6042
FS1018-PIN-ZZ-00-D-O-6069 | Circulation Space (Horizontal) On And Coats And Bag Store (Lockers) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-6069 Circulation Space (Horizontal) On And Coats And Bag Store (Lockers) 1 | FS1018-PIN-ZZ-00-D-O-6069
FS1018-PIN-ZZ-00-D-O-6069 | Circulation Space Horizontal On And Coats And Bag Store Lockers 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-00-D-O-6069 Circulation Space Horizontal On And Coats And Bag Store Lockers 1 | FS1018-PIN-ZZ-00-D-O-6069
FS1018-PIN-ZZ-00-D-O-7001 | DINING AND CATERING 3D | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-00-D-O-7001 DINING AND CATERING 3D | FS1018-PIN-ZZ-00-D-O-7001
FS1018-PIN-ZZ-00-D-O-7001 | Dining And Catering 3D | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-00-D-O-7001 Dining And Catering 3D | FS1018-PIN-ZZ-00-D-O-7001
FS1018-PIN-ZZ-00-D-O-7001 | Dining And Catering 3D | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-7001 Dining And Catering 3D | FS1018-PIN-ZZ-00-D-O-7001
FS1018-PIN-ZZ-00-D-O-7003 | Dishwashing | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-7003 Dishwashing | FS1018-PIN-ZZ-00-D-O-7003
FS1018-PIN-ZZ-00-D-O-7003 | Dishwashing | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-7003 Dishwashing | FS1018-PIN-ZZ-00-D-O-7003
FS1018-PIN-ZZ-00-D-O-7101 | Food Prep Area, Kitchen Servery And Wash Up 1 Electrical Plan | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-7101 Food Prep Area, Kitchen Servery And Wash Up 1 Electrical Plan | FS1018-PIN-ZZ-00-D-O-7101
FS1018-PIN-ZZ-00-D-O-7201 | Food Prep Area, Kitchen Servery And Wash Up 1 Electrical Elevations | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-7201 Food Prep Area, Kitchen Servery And Wash Up 1 Electrical Elevations | FS1018-PIN-ZZ-00-D-O-7201
FS1018-PIN-ZZ-00-D-O-7301 | Food Prep Area, Kitchen Servery And Wash Up 1 Mechanical Plan | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-7301 Food Prep Area, Kitchen Servery And Wash Up 1 Mechanical Plan | FS1018-PIN-ZZ-00-D-O-7301
FS1018-PIN-ZZ-00-D-O-7401 | Food Prep Area, Kitchen Servery And Wash Up 1 Mechanical Elevations | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-7401 Food Prep Area, Kitchen Servery And Wash Up 1 Mechanical Elevations | FS1018-PIN-ZZ-00-D-O-7401
FS1018-PIN-ZZ-00-D-O-7501 | Dishwash Services Requirements | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-7501 Dishwash Services Requirements | FS1018-PIN-ZZ-00-D-O-7501
FS1018-PIN-ZZ-00-D-O-8001 | Music Practice Room 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-8001 Music Practice Room 1 | FS1018-PIN-ZZ-00-D-O-8001
FS1018-PIN-ZZ-00-D-O-8001 | Music Practice Room 1 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-8001 Music Practice Room 1 | FS1018-PIN-ZZ-00-D-O-8001
FS1018-PIN-ZZ-00-D-O-8003 | Music Practice Room (Extensive) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-8003 Music Practice Room (Extensive) 1 | FS1018-PIN-ZZ-00-D-O-8003
FS1018-PIN-ZZ-00-D-O-8003 | Music Practice Room Extensive 1 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-8003 Music Practice Room Extensive 1 | FS1018-PIN-ZZ-00-D-O-8003
FS1018-PIN-ZZ-00-D-O-9001 | Classroom Store, Room (Off Sen Room) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-9001 Classroom Store, Room (Off Sen Room) 1 | FS1018-PIN-ZZ-00-D-O-9001
FS1018-PIN-ZZ-00-D-O-9001 | Classroom Store, Room Off Sen Room 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-9001 Classroom Store, Room Off Sen Room 1 | FS1018-PIN-ZZ-00-D-O-9001
FS1018-PIN-ZZ-00-D-O-9003 | Teaching Resources Store (Music) 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-00-D-O-9003 Teaching Resources Store (Music) 2 | FS1018-PIN-ZZ-00-D-O-9003
FS1018-PIN-ZZ-00-D-O-9003 | Teaching Resources Store Music 2 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-00-D-O-9003 Teaching Resources Store Music 2 | FS1018-PIN-ZZ-00-D-O-9003
FS1018-PIN-ZZ-01-D-O-1000 | FIRST FLOOR GA (1 OF 2) | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-01-D-O-1000 FIRST FLOOR GA (1 OF 2) | FS1018-PIN-ZZ-01-D-O-1000
FS1018-PIN-ZZ-01-D-O-1000 | First Floor GA (1 Of 2) | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-01-D-O-1000 First Floor GA (1 Of 2) | FS1018-PIN-ZZ-01-D-O-1000
FS1018-PIN-ZZ-01-D-O-1000 | First Floor GA 1 Of 2 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1000 First Floor GA 1 Of 2 | FS1018-PIN-ZZ-01-D-O-1000
FS1018-PIN-ZZ-01-D-O-1001 | FIRST FLOOR GA (2 OF 2) | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-01-D-O-1001 FIRST FLOOR GA (2 OF 2) | FS1018-PIN-ZZ-01-D-O-1001
FS1018-PIN-ZZ-01-D-O-1001 | First Floor GA (2 Of 2) | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-01-D-O-1001 First Floor GA (2 Of 2) | FS1018-PIN-ZZ-01-D-O-1001
FS1018-PIN-ZZ-01-D-O-1001 | First Floor GA 2 Of 2 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1001 First Floor GA 2 Of 2 | FS1018-PIN-ZZ-01-D-O-1001
FS1018-PIN-ZZ-01-D-O-1002 | Classroom (General) 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-1002 Classroom (General) 2 | FS1018-PIN-ZZ-01-D-O-1002
FS1018-PIN-ZZ-01-D-O-1002 | Classroom General 2 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1002 Classroom General 2 | FS1018-PIN-ZZ-01-D-O-1002
FS1018-PIN-ZZ-01-D-O-1003 | Classroom (General) 3 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-1003 Classroom (General) 3 | FS1018-PIN-ZZ-01-D-O-1003
FS1018-PIN-ZZ-01-D-O-1003 | Classroom General 3 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1003 Classroom General 3 | FS1018-PIN-ZZ-01-D-O-1003
FS1018-PIN-ZZ-01-D-O-1004 | Classroom (General) 4 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-1004 Classroom (General) 4 | FS1018-PIN-ZZ-01-D-O-1004
FS1018-PIN-ZZ-01-D-O-1004 | Classroom General 4 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1004 Classroom General 4 | FS1018-PIN-ZZ-01-D-O-1004
FS1018-PIN-ZZ-01-D-O-1005 | Classroom (General) 5 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-1005 Classroom (General) 5 | FS1018-PIN-ZZ-01-D-O-1005
FS1018-PIN-ZZ-01-D-O-1005 | Classroom General 5 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1005 Classroom General 5 | FS1018-PIN-ZZ-01-D-O-1005
FS1018-PIN-ZZ-01-D-O-1006 | Classroom (General) 6 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-1006 Classroom (General) 6 | FS1018-PIN-ZZ-01-D-O-1006
FS1018-PIN-ZZ-01-D-O-1006 | Classroom General 6 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1006 Classroom General 6 | FS1018-PIN-ZZ-01-D-O-1006
FS1018-PIN-ZZ-01-D-O-1007 | GENERAL CLASSROOM | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-01-D-O-1007 GENERAL CLASSROOM | FS1018-PIN-ZZ-01-D-O-1007
FS1018-PIN-ZZ-01-D-O-1007 | Classroom (General) 7 | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-01-D-O-1007 Classroom (General) 7 | FS1018-PIN-ZZ-01-D-O-1007
FS1018-PIN-ZZ-01-D-O-1007 | Classroom General 7 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1007 Classroom General 7 | FS1018-PIN-ZZ-01-D-O-1007
FS1018-PIN-ZZ-01-D-O-1008 | Classroom (General) 8 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-1008 Classroom (General) 8 | FS1018-PIN-ZZ-01-D-O-1008
FS1018-PIN-ZZ-01-D-O-1008 | Classroom General 8 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1008 Classroom General 8 | FS1018-PIN-ZZ-01-D-O-1008
FS1018-PIN-ZZ-01-D-O-1009 | Classroom (General) 9 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-1009 Classroom (General) 9 | FS1018-PIN-ZZ-01-D-O-1009
FS1018-PIN-ZZ-01-D-O-1009 | Classroom General 9 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1009 Classroom General 9 | FS1018-PIN-ZZ-01-D-O-1009
FS1018-PIN-ZZ-01-D-O-1021 | CLASSROOM (GENERAL) 1 | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-01-D-O-1021 CLASSROOM (GENERAL) 1 | FS1018-PIN-ZZ-01-D-O-1021
FS1018-PIN-ZZ-01-D-O-1021 | Classroom General 1 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1021 Classroom General 1 | FS1018-PIN-ZZ-01-D-O-1021
FS1018-PIN-ZZ-01-D-O-1101 | ICT RICH CLASSROOM 1 | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-01-D-O-1101 ICT RICH CLASSROOM 1 | FS1018-PIN-ZZ-01-D-O-1101
FS1018-PIN-ZZ-01-D-O-1101 | Ict Rich Classroom 1 | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-01-D-O-1101 Ict Rich Classroom 1 | FS1018-PIN-ZZ-01-D-O-1101
FS1018-PIN-ZZ-01-D-O-1101 | ICT Rich Classroom 1 | P06 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1101 ICT Rich Classroom 1 | FS1018-PIN-ZZ-01-D-O-1101
FS1018-PIN-ZZ-01-D-O-1102 | ICT RICH CLASSROOM 2 | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-01-D-O-1102 ICT RICH CLASSROOM 2 | FS1018-PIN-ZZ-01-D-O-1102
FS1018-PIN-ZZ-01-D-O-1102 | Ict Rich Classroom 2 | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-01-D-O-1102 Ict Rich Classroom 2 | FS1018-PIN-ZZ-01-D-O-1102
FS1018-PIN-ZZ-01-D-O-1102 | ICT Rich Classroom 2 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1102 ICT Rich Classroom 2 | FS1018-PIN-ZZ-01-D-O-1102
FS1018-PIN-ZZ-01-D-O-1108 | ART ROOM (GENERAL) | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-01-D-O-1108 ART ROOM (GENERAL) | FS1018-PIN-ZZ-01-D-O-1108
FS1018-PIN-ZZ-01-D-O-1108 | Art Room (General) | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-01-D-O-1108 Art Room (General) | FS1018-PIN-ZZ-01-D-O-1108
FS1018-PIN-ZZ-01-D-O-1108 | Art Room General | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-1108 Art Room General | FS1018-PIN-ZZ-01-D-O-1108
FS1018-PIN-ZZ-01-D-O-3006 | Medical Treatment (Mi) Room 1 & 3007 Sen Resource Space 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-3006 Medical Treatment (Mi) Room 1 & 3007 Sen Resource Space 1 | FS1018-PIN-ZZ-01-D-O-3006
FS1018-PIN-ZZ-01-D-O-3006 | Medical Treatment Mi Room 1 And 3007 Sen Resource Space 1 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-3006 Medical Treatment Mi Room 1 And 3007 Sen Resource Space 1 | FS1018-PIN-ZZ-01-D-O-3006
FS1018-PIN-ZZ-01-D-O-3009 | Small Group Room (Large Sen Etc.) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-3009 Small Group Room (Large Sen Etc.) 1 | FS1018-PIN-ZZ-01-D-O-3009
FS1018-PIN-ZZ-01-D-O-3009 | Small Group Room Large Sen Etc. 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-3009 Small Group Room Large Sen Etc. 1 | FS1018-PIN-ZZ-01-D-O-3009
FS1018-PIN-ZZ-01-D-O-4002 | Meeting Room (Conference) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-4002 Meeting Room (Conference) 1 | FS1018-PIN-ZZ-01-D-O-4002
FS1018-PIN-ZZ-01-D-O-4002 | Meeting Room Conference 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-4002 Meeting Room Conference 1 | FS1018-PIN-ZZ-01-D-O-4002
FS1018-PIN-ZZ-01-D-O-4007 | Office (Pastoral) 1 And 5002 Teaching Resources Store (Itgt Off Corridor) 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-4007 Office (Pastoral) 1 And 5002 Teaching Resources Store (Itgt Off Corridor) 2 | FS1018-PIN-ZZ-01-D-O-4007
FS1018-PIN-ZZ-01-D-O-4007 | Office Pastoral 1 And 5002 Teaching Resources Store It Gt Off Corridor 2 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-4007 Office Pastoral 1 And 5002 Teaching Resources Store It Gt Off Corridor 2 | FS1018-PIN-ZZ-01-D-O-4007
FS1018-PIN-ZZ-01-D-O-4012 | Office (With Meeting Area, 2 Person) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-4012 Office (With Meeting Area, 2 Person) 1 | FS1018-PIN-ZZ-01-D-O-4012
FS1018-PIN-ZZ-01-D-O-4012 | Office With Meeting Area, 2 Person 1 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-4012 Office With Meeting Area, 2 Person 1 | FS1018-PIN-ZZ-01-D-O-4012
FS1018-PIN-ZZ-01-D-O-4013 | Office (With Meeting Area, 2 Person) 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-4013 Office (With Meeting Area, 2 Person) 2 | FS1018-PIN-ZZ-01-D-O-4013
FS1018-PIN-ZZ-01-D-O-4013 | Office With Meeting Area, 2 Person 2 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-4013 Office With Meeting Area, 2 Person 2 | FS1018-PIN-ZZ-01-D-O-4013
FS1018-PIN-ZZ-01-D-O-4016 | Office (Senco, Learning Support) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-4016 Office (Senco, Learning Support) 1 | FS1018-PIN-ZZ-01-D-O-4016
FS1018-PIN-ZZ-01-D-O-4016 | Office Senco, Learning Support 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-4016 Office Senco, Learning Support 1 | FS1018-PIN-ZZ-01-D-O-4016
FS1018-PIN-ZZ-01-D-O-4017 | Staff Workroom (Ict Technicians) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-4017 Staff Workroom (Ict Technicians) 1 | FS1018-PIN-ZZ-01-D-O-4017
FS1018-PIN-ZZ-01-D-O-4017 | Staff Workroom ICT Technicians 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-01-D-O-4017 Staff Workroom ICT Technicians 1 | FS1018-PIN-ZZ-01-D-O-4017
FS1018-PIN-ZZ-01-D-O-5006 | Teaching Resources Store (Off Art Room) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-5006 Teaching Resources Store (Off Art Room) 1 | FS1018-PIN-ZZ-01-D-O-5006
FS1018-PIN-ZZ-01-D-O-5006 | Teaching Resources Store Off Art Room 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-01-D-O-5006 Teaching Resources Store Off Art Room 1 | FS1018-PIN-ZZ-01-D-O-5006
FS1018-PIN-ZZ-01-D-O-5017 | Classroom Store, Room (Off Sen Room) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-5017 Classroom Store, Room (Off Sen Room) 1 | FS1018-PIN-ZZ-01-D-O-5017
FS1018-PIN-ZZ-01-D-O-5017 | Classroom Store, Room Off Sen Room 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-5017 Classroom Store, Room Off Sen Room 1 | FS1018-PIN-ZZ-01-D-O-5017
FS1018-PIN-ZZ-01-D-O-5042 | 66042K Stairway 7 And 5112 Coats And Bag Store (Lockers) 4 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-5042 66042K Stairway 7 And 5112 Coats And Bag Store (Lockers) 4 | FS1018-PIN-ZZ-01-D-O-5042
FS1018-PIN-ZZ-01-D-O-5104 | Secure Storeroom 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-5104 Secure Storeroom 2 | FS1018-PIN-ZZ-01-D-O-5104
FS1018-PIN-ZZ-01-D-O-5104 | Secure Storeroom 2 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-5104 Secure Storeroom 2 | FS1018-PIN-ZZ-01-D-O-5104
FS1018-PIN-ZZ-01-D-O-5110 | Coats And Bag Store (Lockers) 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-5110 Coats And Bag Store (Lockers) 2 | FS1018-PIN-ZZ-01-D-O-5110
FS1018-PIN-ZZ-01-D-O-5110 | Coats And Bag Store Lockers 2 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-5110 Coats And Bag Store Lockers 2 | FS1018-PIN-ZZ-01-D-O-5110
FS1018-PIN-ZZ-01-D-O-5111 | Coats And Bag Store (Lockers) 3 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-5111 Coats And Bag Store (Lockers) 3 | FS1018-PIN-ZZ-01-D-O-5111
FS1018-PIN-ZZ-01-D-O-5111 | Coats And Bag Store Lockers 3 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-5111 Coats And Bag Store Lockers 3 | FS1018-PIN-ZZ-01-D-O-5111
FS1018-PIN-ZZ-01-D-O-5112 | Coats And Bag Store (Lockers) 4 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-5112 Coats And Bag Store (Lockers) 4 | FS1018-PIN-ZZ-01-D-O-5112
FS1018-PIN-ZZ-01-D-O-5112 | Coats And Bag Store Lockers 4 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-5112 Coats And Bag Store Lockers 4 | FS1018-PIN-ZZ-01-D-O-5112
FS1018-PIN-ZZ-01-D-O-5113 | Coats And Bag Store (Lockers) 5 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-5113 Coats And Bag Store (Lockers) 5 | FS1018-PIN-ZZ-01-D-O-5113
FS1018-PIN-ZZ-01-D-O-5113 | Coats And Bag Store Lockers 5 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-01-D-O-5113 Coats And Bag Store Lockers 5 | FS1018-PIN-ZZ-01-D-O-5113
FS1018-PIN-ZZ-01-D-O-5116 | Cleaners' Store 3 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-01-D-O-5116 Cleaners' Store 3 | FS1018-PIN-ZZ-01-D-O-5116
FS1018-PIN-ZZ-01-D-O-7042 | 66042L Stairway 7 And 5113 Coats And Bag Store (Lockers) 5 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-7042 66042L Stairway 7 And 5113 Coats And Bag Store (Lockers) 5 | FS1018-PIN-ZZ-01-D-O-7042
FS1018-PIN-ZZ-01-D-O-8042 | 66042I Stairway 7 And 5110 Coats And Bag Store (Lockers) 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-8042 66042I Stairway 7 And 5110 Coats And Bag Store (Lockers) 2 | FS1018-PIN-ZZ-01-D-O-8042
FS1018-PIN-ZZ-01-D-O-9042 | 66042J Circulation Space (Horizontal) On And 5111 Coats And Bag Store (Lockers) 3 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-01-D-O-9042 66042J Circulation Space (Horizontal) On And 5111 Coats And Bag Store (Lockers) 3 | FS1018-PIN-ZZ-01-D-O-9042
FS1018-PIN-ZZ-02-D-O-1010 | Classroom (General) 10 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-1010 Classroom (General) 10 | FS1018-PIN-ZZ-02-D-O-1010
FS1018-PIN-ZZ-02-D-O-1010 | Classroom General 10 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1010 Classroom General 10 | FS1018-PIN-ZZ-02-D-O-1010
FS1018-PIN-ZZ-02-D-O-1011 | Classroom (General) 11 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-1011 Classroom (General) 11 | FS1018-PIN-ZZ-02-D-O-1011
FS1018-PIN-ZZ-02-D-O-1011 | Classroom General 11 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1011 Classroom General 11 | FS1018-PIN-ZZ-02-D-O-1011
FS1018-PIN-ZZ-02-D-O-1012 | Classroom (General) 12 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-1012 Classroom (General) 12 | FS1018-PIN-ZZ-02-D-O-1012
FS1018-PIN-ZZ-02-D-O-1012 | Classroom General 12 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1012 Classroom General 12 | FS1018-PIN-ZZ-02-D-O-1012
FS1018-PIN-ZZ-02-D-O-1013 | Classroom (General) 13 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-1013 Classroom (General) 13 | FS1018-PIN-ZZ-02-D-O-1013
FS1018-PIN-ZZ-02-D-O-1013 | Classroom General 13 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1013 Classroom General 13 | FS1018-PIN-ZZ-02-D-O-1013
FS1018-PIN-ZZ-02-D-O-1014 | Classroom (General) 14 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-1014 Classroom (General) 14 | FS1018-PIN-ZZ-02-D-O-1014
FS1018-PIN-ZZ-02-D-O-1014 | Classroom General 14 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1014 Classroom General 14 | FS1018-PIN-ZZ-02-D-O-1014
FS1018-PIN-ZZ-02-D-O-1015 | Classroom (General) 15 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-1015 Classroom (General) 15 | FS1018-PIN-ZZ-02-D-O-1015
FS1018-PIN-ZZ-02-D-O-1015 | Classroom General 15 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1015 Classroom General 15 | FS1018-PIN-ZZ-02-D-O-1015
FS1018-PIN-ZZ-02-D-O-1016 | Classroom (General) 16 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-1016 Classroom (General) 16 | FS1018-PIN-ZZ-02-D-O-1016
FS1018-PIN-ZZ-02-D-O-1016 | Classroom General 16 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1016 Classroom General 16 | FS1018-PIN-ZZ-02-D-O-1016
FS1018-PIN-ZZ-02-D-O-1042 | 66042P Stairway 7 & 5113A Coats And Bag Store (Lockers) 5 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-1042 66042P Stairway 7 & 5113A Coats And Bag Store (Lockers) 5 | FS1018-PIN-ZZ-02-D-O-1042
FS1018-PIN-ZZ-02-D-O-1042 | 6042P Stairway 7 And 5113A Coats And Bag Store Lockers 5 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1042 6042P Stairway 7 And 5113A Coats And Bag Store Lockers 5 | FS1018-PIN-ZZ-02-D-O-1042
FS1018-PIN-ZZ-02-D-O-1103 | SCIENCE LABORATORIES (RESTRICTIVE, EXTG) 1 | P03 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-1103 SCIENCE LABORATORIES (RESTRICTIVE, EXTG) 1 | FS1018-PIN-ZZ-02-D-O-1103
FS1018-PIN-ZZ-02-D-O-1103 | Science Laboratories Restrictive, Extg 1 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1103 Science Laboratories Restrictive, Extg 1 | FS1018-PIN-ZZ-02-D-O-1103
FS1018-PIN-ZZ-02-D-O-1104 | Science Laboratories (Restrictive, Extg) 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-1104 Science Laboratories (Restrictive, Extg) 2 | FS1018-PIN-ZZ-02-D-O-1104
FS1018-PIN-ZZ-02-D-O-1104 | Science Laboratories Restrictive, Extg 2 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1104 Science Laboratories Restrictive, Extg 2 | FS1018-PIN-ZZ-02-D-O-1104
FS1018-PIN-ZZ-02-D-O-1105 | Science Laboratories (Restrictive, Extg) 3 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-1105 Science Laboratories (Restrictive, Extg) 3 | FS1018-PIN-ZZ-02-D-O-1105
FS1018-PIN-ZZ-02-D-O-1105 | Science Laboratories Restrictive, Extg 3 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1105 Science Laboratories Restrictive, Extg 3 | FS1018-PIN-ZZ-02-D-O-1105
FS1018-PIN-ZZ-02-D-O-1106 | SCIENCE LAB | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-02-D-O-1106 SCIENCE LAB | FS1018-PIN-ZZ-02-D-O-1106
FS1018-PIN-ZZ-02-D-O-1106 | Science Laboratories (Restrictive, Extg) 4 | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-02-D-O-1106 Science Laboratories (Restrictive, Extg) 4 | FS1018-PIN-ZZ-02-D-O-1106
FS1018-PIN-ZZ-02-D-O-1106 | Science Laboratories Restrictive, Extg 4 | P04 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1106 Science Laboratories Restrictive, Extg 4 | FS1018-PIN-ZZ-02-D-O-1106
FS1018-PIN-ZZ-02-D-O-1107 | Science Laboratories (Restrictive, Extg) 5 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-1107 Science Laboratories (Restrictive, Extg) 5 | FS1018-PIN-ZZ-02-D-O-1107
FS1018-PIN-ZZ-02-D-O-1107 | Science Laboratories Restrictive, Extg 5 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-1107 Science Laboratories Restrictive, Extg 5 | FS1018-PIN-ZZ-02-D-O-1107
FS1018-PIN-ZZ-02-D-O-2000 | SECOND FLOOR GA | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-02-D-O-2000 SECOND FLOOR GA | FS1018-PIN-ZZ-02-D-O-2000
FS1018-PIN-ZZ-02-D-O-2000 | Second Floor GA | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-02-D-O-2000 Second Floor GA | FS1018-PIN-ZZ-02-D-O-2000
FS1018-PIN-ZZ-02-D-O-2000 | Second Floor GA | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-2000 Second Floor GA | FS1018-PIN-ZZ-02-D-O-2000
FS1018-PIN-ZZ-02-D-O-2042 | 6042O Stairway 7 & 5113B Coats And Bag Store (Lockers) 5 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-2042 6042O Stairway 7 & 5113B Coats And Bag Store (Lockers) 5 | FS1018-PIN-ZZ-02-D-O-2042
FS1018-PIN-ZZ-02-D-O-2042 | 6042O Stairway 7 And 5113B Coats And Bag Store Lockers 5 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-2042 6042O Stairway 7 And 5113B Coats And Bag Store Lockers 5 | FS1018-PIN-ZZ-02-D-O-2042
FS1018-PIN-ZZ-02-D-O-3008 | Small Group Room (Medium) 1 and 6042T Stairway 7 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-3008 Small Group Room (Medium) 1 and 6042T Stairway 7 | FS1018-PIN-ZZ-02-D-O-3008
FS1018-PIN-ZZ-02-D-O-3008 | Small Group Room Medium 1 And 6042T Stairway 7 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-02-D-O-3008 Small Group Room Medium 1 And 6042T Stairway 7 | FS1018-PIN-ZZ-02-D-O-3008
FS1018-PIN-ZZ-02-D-O-3042 | 6042N Stairway 7, 5113C and 5113D Coats And Bag Store (Lockers) 5 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-3042 6042N Stairway 7, 5113C and 5113D Coats And Bag Store (Lockers) 5 | FS1018-PIN-ZZ-02-D-O-3042
FS1018-PIN-ZZ-02-D-O-3042 | 6042N Stairway 7, 5113C And 5113D Coats And Bag Store Lockers 5 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-3042 6042N Stairway 7, 5113C And 5113D Coats And Bag Store Lockers 5 | FS1018-PIN-ZZ-02-D-O-3042
FS1018-PIN-ZZ-02-D-O-4001 | STAFF WORKROOM | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-02-D-O-4001 STAFF WORKROOM | FS1018-PIN-ZZ-02-D-O-4001
FS1018-PIN-ZZ-02-D-O-4001 | Staff Workroom (Teaching Staff) 1 And Teaching Resources Store (Itgt Off Corridor) 3 | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-02-D-O-4001 Staff Workroom (Teaching Staff) 1 And Teaching Resources Store (Itgt Off Corridor) 3 | FS1018-PIN-ZZ-02-D-O-4001
FS1018-PIN-ZZ-02-D-O-4001 | Staff Workroom Teaching Staff 1 And Teaching Resources Store It Gt Off Corridor 3 | P05 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-4001 Staff Workroom Teaching Staff 1 And Teaching Resources Store It Gt Off Corridor 3 | FS1018-PIN-ZZ-02-D-O-4001
FS1018-PIN-ZZ-02-D-O-4011 | Office (2 Person) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-4011 Office (2 Person) 1 | FS1018-PIN-ZZ-02-D-O-4011
FS1018-PIN-ZZ-02-D-O-4014 | Office (With Meeting Area, 2 Person) 3 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-4014 Office (With Meeting Area, 2 Person) 3 | FS1018-PIN-ZZ-02-D-O-4014
FS1018-PIN-ZZ-02-D-O-4014 | Office With Meeting Area, 2 Person 3 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-02-D-O-4014 Office With Meeting Area, 2 Person 3 | FS1018-PIN-ZZ-02-D-O-4014
FS1018-PIN-ZZ-02-D-O-5004 | SCIENCE PREP | P01 | Completed | 2023-09-06 | FFE Review | B3 - Partially Accepted with Comments | 2023-09-21 | See comments on drawing. | FALSE | FS1018-PIN-ZZ-02-D-O-5004 SCIENCE PREP | FS1018-PIN-ZZ-02-D-O-5004
FS1018-PIN-ZZ-02-D-O-5004 | Science Prep Option 1 | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-02-D-O-5004 Science Prep Option 1 | FS1018-PIN-ZZ-02-D-O-5004
FS1018-PIN-ZZ-02-D-O-5004 | Science Prep Option 1 | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-5004 Science Prep Option 1 | FS1018-PIN-ZZ-02-D-O-5004
FS1018-PIN-ZZ-02-D-O-5005 | Chemical Store 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-5005 Chemical Store 1 | FS1018-PIN-ZZ-02-D-O-5005
FS1018-PIN-ZZ-02-D-O-5005 | Chemical Store 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-02-D-O-5005 Chemical Store 1 | FS1018-PIN-ZZ-02-D-O-5005
FS1018-PIN-ZZ-02-D-O-5020 | Science Prep Option 2 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-5020 Science Prep Option 2 | FS1018-PIN-ZZ-02-D-O-5020
FS1018-PIN-ZZ-02-D-O-5020 | Science Prep | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-02-D-O-5020 Science Prep | FS1018-PIN-ZZ-02-D-O-5020
FS1018-PIN-ZZ-02-D-O-5102 | General Storeroom (Central Stock) 1 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-5102 General Storeroom (Central Stock) 1 | FS1018-PIN-ZZ-02-D-O-5102
FS1018-PIN-ZZ-02-D-O-5102 | General Storeroom Central Stock 1 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-02-D-O-5102 General Storeroom Central Stock 1 | FS1018-PIN-ZZ-02-D-O-5102
FS1018-PIN-ZZ-02-D-O-5115 | Cleaners' Store 2 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-02-D-O-5115 Cleaners' Store 2 | FS1018-PIN-ZZ-02-D-O-5115
FS1018-PIN-ZZ-02-D-O-6113 | Coats And Bags Store (Lockers) 5 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-6113 Coats And Bags Store (Lockers) 5 | FS1018-PIN-ZZ-02-D-O-6113
FS1018-PIN-ZZ-02-D-O-6113 | Coats And Bags Store Lockers 5 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-02-D-O-6113 Coats And Bags Store Lockers 5 | FS1018-PIN-ZZ-02-D-O-6113
FS1018-PIN-ZZ-02-D-O-7113 | Coats And Bags Store (Lockers) 5 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-7113 Coats And Bags Store (Lockers) 5 | FS1018-PIN-ZZ-02-D-O-7113
FS1018-PIN-ZZ-02-D-O-7113 | Coats And Bags Store Lockers 5 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-02-D-O-7113 Coats And Bags Store Lockers 5 | FS1018-PIN-ZZ-02-D-O-7113
FS1018-PIN-ZZ-02-D-O-8113 | Coats And Bags Store (Lockers) 5 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-8113 Coats And Bags Store (Lockers) 5 | FS1018-PIN-ZZ-02-D-O-8113
FS1018-PIN-ZZ-02-D-O-8113 | Coats And Bags Store Lockers 5 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-02-D-O-8113 Coats And Bags Store Lockers 5 | FS1018-PIN-ZZ-02-D-O-8113
FS1018-PIN-ZZ-02-D-O-9113 | Coats And Bags Store (Lockers) 5 | P01 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-02-D-O-9113 Coats And Bags Store (Lockers) 5 | FS1018-PIN-ZZ-02-D-O-9113
FS1018-PIN-ZZ-02-D-O-9113 | Coats And Bags Store Lockers 5 | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-02-D-O-9113 Coats And Bags Store Lockers 5 | FS1018-PIN-ZZ-02-D-O-9113
FS1018-PIN-ZZ-ZZ-L-O-0005 | Wisbech Secondary School Occupancy Schedule | P01 | Completed | 2024-12-12 | Client Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-ZZ-L-O-0005 Wisbech Secondary School Occupancy Schedule | FS1018-PIN-ZZ-ZZ-L-O-0005
FS1018-PIN-ZZ-ZZ-L-O-0005 | FFE Gap Analysis and Occupancy Schedule | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-ZZ-L-O-0005 FFE Gap Analysis and Occupancy Schedule | FS1018-PIN-ZZ-ZZ-L-O-0005
FS1018-PIN-ZZ-ZZ-L-O-0006 | Catering Equipment Schedule | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-ZZ-L-O-0006 Catering Equipment Schedule | FS1018-PIN-ZZ-ZZ-L-O-0006
FS1018-PIN-ZZ-ZZ-L-O-0007 | FFE Cost Plan | P01 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-ZZ-L-O-0007 FFE Cost Plan | FS1018-PIN-ZZ-ZZ-L-O-0007
FS1018-PIN-ZZ-ZZ-M-O-0001 | FFE REVIT MODEL | P03 | Completed | 2023-09-15 | FFE Review | C - Rejected | 2023-09-25 | Model reference on starting sheet not aligned to file name. Only typical rooms appear to be modelled with many spaces on upper levels empty. Space objects to be modelled to align with room extents (Ie space should be contained between surrounding walls, floor and ceiling). Esp. Space height must be paid attention to. Space objects should not be clashing with each other. Object assignment to correct levels requires review (in Level 01 there are objects that should be assigned to Level 02), naming of levels should align to Project Information Standard. | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0001 FFE REVIT MODEL | FS1018-PIN-ZZ-ZZ-M-O-0001
FS1018-PIN-ZZ-ZZ-M-O-0001 | FFE REVIT MODEL | P04 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0001 FFE REVIT MODEL | FS1018-PIN-ZZ-ZZ-M-O-0001
FS1018-PIN-ZZ-ZZ-M-O-0001 | FFE Revit Model | P11 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0001 FFE Revit Model | FS1018-PIN-ZZ-ZZ-M-O-0001
FS1018-PIN-ZZ-ZZ-M-O-0002 | FFE IFC MODEL | P03 | Completed | 2023-09-15 | FFE Review | C - Rejected | 2023-09-25 | Only typical rooms appear to be modelled with many spaces on upper levels empty. Space objects to be modelled to align with room extents (Ie space should be contained between surrounding walls, floor and ceiling). Esp. Space height must be paid attention to. Space objects should not be clashing with each other. None of the modelled elements have IFC predefined types assigned (2485 elements). Object assignment to correct levels requires review (in Level 01 there are objects that should be assigned to Level 02), naming of levels should align to Project Information Standard. | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0002 FFE IFC MODEL | FS1018-PIN-ZZ-ZZ-M-O-0002
FS1018-PIN-ZZ-ZZ-M-O-0002 | FFE IFC MODEL | P04 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0002 FFE IFC MODEL | FS1018-PIN-ZZ-ZZ-M-O-0002
FS1018-PIN-ZZ-ZZ-M-O-0002 | FFE IFC Model | P09 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0002 FFE IFC Model | FS1018-PIN-ZZ-ZZ-M-O-0002
FS1018-PIN-ZZ-ZZ-M-O-0003 | FFE NAVIS MODEL | P03 | Completed | 2023-09-15 | FFE Review | C - Rejected | 2023-09-25 | nly typical rooms appear to be modelled with many spaces on upper levels empty. Space objects to be modelled to align with room extents (Ie space should be contained between surrounding walls, floor and ceiling). Esp. Space height must be paid attention to. Space objects should not be clashing with each other. Object assignment to correct levels requires review (in Level 01 there are objects that should be assigned to Level 02), naming of levels should align to Project Information Standard. | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0003 FFE NAVIS MODEL | FS1018-PIN-ZZ-ZZ-M-O-0003
FS1018-PIN-ZZ-ZZ-M-O-0003 | FFE NAVIS MODEL | P04 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0003 FFE NAVIS MODEL | FS1018-PIN-ZZ-ZZ-M-O-0003
FS1018-PIN-ZZ-ZZ-M-O-0003 | FFE Navis Model | P07 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0003 FFE Navis Model | FS1018-PIN-ZZ-ZZ-M-O-0003
FS1018-PIN-ZZ-ZZ-M-O-0004 | CATERING IFC MODEL | P01 | Completed | 2023-09-15 | FFE Review | C - Rejected | 2023-09-25 | The whole model is duplicated within FS1018-PIN-ZZ-ZZ-M-O-0002 FFE IFC MODEL. This either requires omitting this model and mapping the DEIR deliverables of both to this file. Or splitting the model into two - one with catering and one with FFE | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0004 CATERING IFC MODEL | FS1018-PIN-ZZ-ZZ-M-O-0004
FS1018-PIN-ZZ-ZZ-M-O-0004 | CATERING IFC MODEL | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-ZZ-M-O-0004 CATERING IFC MODEL | FS1018-PIN-ZZ-ZZ-M-O-0004
FS1018-PIN-ZZ-ZZ-M-O-0004 | Catering IFC Model | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0004 Catering IFC Model | FS1018-PIN-ZZ-ZZ-M-O-0004
FS1018-PIN-ZZ-ZZ-M-O-0005 | CATERING REVIT MODEL | P01 | Completed | 2023-09-15 | FFE Review | C - Rejected | 2023-09-25 | The whole model is duplicated within FS1018-PIN-ZZ-ZZ-M-O-0002 FFE IFC MODEL. This either requires omitting this model and mapping the DEIR deliverables of both to this file. Or splitting the model into two - one with catering and one with FFE | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0005 CATERING REVIT MODEL | FS1018-PIN-ZZ-ZZ-M-O-0005
FS1018-PIN-ZZ-ZZ-M-O-0005 | CATERING REVIT MODEL | P02 | Completed | 2024-08-29 | FFE Review | B3 - Partially Accepted with Comments | 2025-01-12 | To be closed out in Stage 4 review - added to Clarifications log to ensure review is complete in Stage 4 | TRUE | FS1018-PIN-ZZ-ZZ-M-O-0005 CATERING REVIT MODEL | FS1018-PIN-ZZ-ZZ-M-O-0005
FS1018-PIN-ZZ-ZZ-M-O-0005 | Catering Revit Model | P03 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0005 Catering Revit Model | FS1018-PIN-ZZ-ZZ-M-O-0005
FS1018-PIN-ZZ-ZZ-M-O-0006 | CATERING NWC MODEL | P01 | Completed | 2023-11-08 | FFE Review | A3 - Accepted | 2024-08-12 |  | FALSE | FS1018-PIN-ZZ-ZZ-M-O-0006 CATERING NWC MODEL | FS1018-PIN-ZZ-ZZ-M-O-0006
FS1018-PIN-ZZ-ZZ-M-O-0006 | CATERING NWC MODEL | P02 | In Progress | 2025-03-13 | DFE Review | Pending |  |  | TRUE | FS1018-PIN-ZZ-ZZ-M-O-0006 CATERING NWC MODEL | FS1018-PIN-ZZ-ZZ-M-O-0006