## ProjectInfo
Project Name | Date Generated
HB Test | 19/03/2026 17:39

## RawData
Status | Ball in Court | Reference Number | Subject | Originally From | RFI Description | Discipline(s) | Date RFI Sent | RFI Response | Date RFI Responded | Latest Correspondence | Comments | Date Closed | (Helper) Hyperlink | Mail Number
Overdue | Henry Brothers | CS-TRFI-000001 | Access Control to MRI Equipment Room | Creative Spaces Ltd | Arup's design specifies that the door leading into the MRI equipment room is equipped with access control, including a mag lock. However, since the mag lock will be ferrous, we do not believe it can be installed on the equipment room door. Given that the control room is already secure, could you confirm whether access control is necessary for the equipment room? If not, we can proceed with removing access control from this door. |  | 01/04/2025 06:34 |  |  | CS-TRFI-000001 |  |  | https://ea1.aconex.com/hub/index.html?mainTarget=%2FViewCorrespondence%3FPROJECT_ID%3D1879048648%26CORRESPONDENCE_MAILBOX%3D0%26Correspondence_ID%3D1880227469 | CS-TRFI-000001
Overdue | Skyhigh Seating Systems Pty Ltd | CS-TRFI-000002 | Confirmation of Cladding Spec | Creative Spaces Ltd | Specification clause Ss_25_20_14/255 states that the wall cladding will achieve 0.26W/m2K. The thickness is specified as 150mm in clause Pr_25_71_14_22. Our proposed Steelwork Sub-Contractor have priced on 175mm thick panels, achieving a “U” value of 0.24W/m2K. Eurobond website confirms that: 150mm thick Rockspan panel achieves 0.28W/m2K 175mm thick Rockspan panel achieves 0.24W/m2K |  | 01/04/2025 16:12 |  |  | HBC-RFI-000004 |  |  | https://ea1.aconex.com/hub/index.html?mainTarget=%2FViewCorrespondence%3FPROJECT_ID%3D1879048648%26CORRESPONDENCE_MAILBOX%3D0%26Correspondence_ID%3D1880227486 | HBC-RFI-000004
Responded | Company A | HBC-RFI-000001 | FF Floor Finishes Construction drawings still reads tbc on both Drawings | Henry Brothers | Construction drawings still reads TBC for finish type DR-A-430007 & 430009 |  | 25/03/2025 21:33 | Drawings 430007 and should be 430008 were first floor finish 1:50 details, due to uncomplicated setting out I propose to omit those two pages. Page 430007 first floor finishes - overall would suffice and will be updated in line with recent floor specialist recommendation which has been approved by client. | 25/03/2025 21:35 | HBC-RFI-000007 |  |  | https://ea1.aconex.com/hub/index.html?mainTarget=%2FViewCorrespondence%3FPROJECT_ID%3D1879048648%26CORRESPONDENCE_MAILBOX%3D0%26Correspondence_ID%3D1880227163 | HBC-RFI-000007
Responded | Company B | HBC-RFI-000002 | Entrance Ceiling Details | Henry Brothers | As requested previously, we require sections through the entrance door to confirm the ceiling arrangements to suit coordination with the overdoor heater, and revised RCP's with ceiling level lowered to suit previous stage 4 coordination with M&E. |  | 25/03/2025 21:37 | Ceiling layout page provided 6 March - see attached email and drawing | 25/03/2025 21:38 | HBC-RFI-000008 |  |  | https://ea1.aconex.com/hub/index.html?mainTarget=%2FViewCorrespondence%3FPROJECT_ID%3D1879048648%26CORRESPONDENCE_MAILBOX%3D0%26Correspondence_ID%3D1880227166 | HBC-RFI-000008
Overdue | Company B | HBC-RFI-000003 | External Metal door fixing detail | Henry Brothers | Further to the design meeting with Ascot and P+HS 10/03/25, it was identified that there is no structure provided in the design to accommodate the door fixing based on the Consultant design. The only way suggested to achieve this by Ascot is to install full height steel plates to the jambs back to the SFS. Can the detail/design please be revised/clarified to show a suitable fixing solution sufficient for costing/instruction. Doors require sign-off for manufacture ASAP to avoid programme delay. Frame sizes may be impacted depending on Consultant solution. |  | 25/03/2025 21:49 |  |  | HBC-RFI-000003 |  |  | https://ea1.aconex.com/hub/index.html?mainTarget=%2FViewCorrespondence%3FPROJECT_ID%3D1879048648%26CORRESPONDENCE_MAILBOX%3D0%26Correspondence_ID%3D1880227171 | HBC-RFI-000003
Overdue | Fabulous Architects | HBC-RFI-000003 | External Metal door fixing detail | Henry Brothers | Further to the design meeting with Ascot and P+HS 10/03/25, it was identified that there is no structure provided in the design to accommodate the door fixing based on the Consultant design. The only way suggested to achieve this by Ascot is to install full height steel plates to the jambs back to the SFS. Can the detail/design please be revised/clarified to show a suitable fixing solution sufficient for costing/instruction. Doors require sign-off for manufacture ASAP to avoid programme delay. Frame sizes may be impacted depending on Consultant solution. |  | 25/03/2025 21:49 |  |  | HBC-RFI-000003 |  |  | https://ea1.aconex.com/hub/index.html?mainTarget=%2FViewCorrespondence%3FPROJECT_ID%3D1879048648%26CORRESPONDENCE_MAILBOX%3D0%26Correspondence_ID%3D1880227171 | HBC-RFI-000003
Closed-Out | N/A | HBC-RFI-000005 | Western Power Underground Utility Survey | Henry Brothers | Please can we have a copy of the Western Power underground utility survey showing the existing services, ref number 26544116. |  | 06/04/2025 18:54 | I am a creative space ᓚᘏᗢ | 21/05/2025 18:49 | CS-RFIR-000001 |  | 06/04/2025 18:56 | https://ea1.aconex.com/hub/index.html?mainTarget=%2FViewCorrespondence%3FPROJECT_ID%3D1879048648%26CORRESPONDENCE_MAILBOX%3D0%26Correspondence_ID%3D1880227838 | HBC-RFI-000005
Overdue | Company B | HBC-TRFI-000001 | ABC | Henry Brothers | sorted(data.items(), key=lambda x: (x[1][1] * -1, x[1][0])) print(res) sorted(data.items(), key=lambda x: (x[1][1] * -1, x[1][0])) print(res) |  | 21/05/2025 14:05 |  |  | HBC-RFI-000006 |  |  | https://ea1.aconex.com/hub/index.html?mainTarget=%2FViewCorrespondence%3FPROJECT_ID%3D1879048648%26CORRESPONDENCE_MAILBOX%3D0%26Correspondence_ID%3D1880231304 | HBC-RFI-000006
Overdue | Company A | HBC-WTRAN-000010 | Re: Final (WF-000004) RFI off the back of a transmittal | Creative Spaces Ltd | Cardinality refers to the number of repetitions a field can have. A cardinality that allows zero (0) means the field is optional and may not appear in the response. |  | 21/05/2025 18:03 |  |  | CS-RFI-000001 |  |  | https://ea1.aconex.com/hub/index.html?mainTarget=%2FViewCorrespondence%3FPROJECT_ID%3D1879048648%26CORRESPONDENCE_MAILBOX%3D0%26Correspondence_ID%3D1880231322 | HBC-WTRAN-000010
Responded | Skyhigh Seating Systems Pty Ltd | Skyhigh-TRFI-000001 | Fallow Areas Design | Skyhigh Seating Systems Pty Ltd | Are the Fallow areas design to be included & feature in the Stage 4.2 / Stage 5 design submissions for this scheme. |  | 06/04/2025 18:51 | No, as discussed in yesterdays meeting, leave as fallow until we are instructed. | 06/04/2025 18:52 | HBC-RFIR-000001 |  |  | https://ea1.aconex.com/hub/index.html?mainTarget=%2FViewCorrespondence%3FPROJECT_ID%3D1879048648%26CORRESPONDENCE_MAILBOX%3D0%26Correspondence_ID%3D1880227836 | Skyhigh-TRFI-000001